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LEGAL NOTICE

The Oil Region Alliance will accept proposals until 2 p.m. on Tuesday, December 1, 2026 for the Demolition of the Fuchs Industrial Site at 105 8th Street, Emlenton, PA 16373. For information and full instructions, contact Debbie Sobina, Project Manager, 217 Elm Street, Oil City, PA 16301; (814) 677-3152, Ext. 109; dsobina@oilregion.org. The full Invitation For Bids (IFB) is available at oilregion.org/the-alliance/rfps/.
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LEGAL NOTICE	LN - 1
ANNOUNCEMENT OF INVITATION FOR BIDS
Demolition — 105 8th Street, Emlenton, PA 16373, Fuchs Industrial Site

The Oil Region Alliance will receive sealed bids until 2 p.m. local time on Tuesday, December 1, 2026 for the Demolition of the former Fuchs Industrial Site at 105 8th Street, Emlenton, PA 16373. The electronic bid set is posted at https://oilregion.org/the-alliance/rfps/. Bid documents may be obtained from the Oil Region Alliance at 217 Elm Street, Oil City PA 16301, 814-677-3152, for a non-refundable fee of forty dollars ($40) per set payable to the Oil Region Alliance. A $10 mailing fee will also be required for Bid Documents that are mailed. The project contract period is from approximately January 1, 2027 – April 15, 2027.
A mandatory pre-bid meeting will be held November 17, 2026 at 2 p.m. at the Fuchs Industrial Site, 105 8th Street, Emlenton, PA 16373. This will be the only opportunity given to contractors to access and view the site with the project manager.
Address bids to the Oil Region Alliance, 217 Elm Street, Oil City, PA 16301. The bid package should be clearly marked "Bid for Demolition of Fuchs Industrial Site. DO NOT OPEN UNTIL 2 p.m. Tuesday, December 1, 2026." Bids will not be accepted by fax or e-mail.
A certified check, bank cashier's check or bid bond in an amount equal to ten (10) percent of the bid, payable to the Oil Region Alliance, shall be submitted with the bid to guarantee the bidder's entrance into a contract if given the award. Surety companies executing the Bid Bond must be listed in the U.S. Treasury Department Circular 570, as currently amended, and be authorized to transact business in the Commonwealth of Pennsylvania.
Bids may be held by the Oil Region Alliance for a period not to exceed 60 days from the date of opening for the purpose of reviewing the bids and investigating the qualifications of bidders, prior to awarding the contract. The Oil Region Alliance reserves the right to refuse any or all bids, and to waive any technicalities or informalities in bidding.
Bids must be made in accordance with the Pennsylvania State Prevailing Wage Act (PWA) for state-funded construction projects exceeding $25,000. The PWA applies to work completed by paid contractors and subcontractors. Prevailing minimum wages are determined by the PA Department of Labor and Industry.
The scope of work includes the removal and proper offsite disposal of the asbestos-containing materials, PCB light ballasts, universal wastes and other hazardous materials identified in the Pre-Demolition Hazardous Building Materials Survey; cleanup of graphite dust; disconnection of all existing utilities and capping of sanitary sewer laterals; demolition of the building designated as Building 1 on the Demolition Plans, including its contents, foundations and concrete slabs, with proper offsite disposal; backfilling of the building footprint with clean fill; site grading, topsoil, seeding and mulching; erosion and sedimentation controls; establishing ingress and egress to the site; and restoration as required or directed. The buildings, walls, asphalt and gravel areas designated on the Demolition Plans to remain shall be protected.
This project is funded through the Industrial Sites Reuse Program Keystone Communities Program Grant through the Pennsylvania Department of Community and Economic Development. Minimum salaries and wages as set forth in the Bid/Contract Documents must be paid. The contractor must ensure that employees and applicants for employment are not discriminated against because of their race, age, color, religion, sex, gender, sexual orientation, national origin, creed, disabilities, or handicap. Contractor must make and document efforts to include Disadvantaged Business Enterprise (DBE) among the list of subcontractors assembled to conduct this Commonwealth-funded building demolition project. Direct questions to Debbie Sobina, Project Manager, at dsobina@oilregion.org.
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ANNOUNCEMENT OF INVITATION FOR BIDS	AIB - 1
INSTRUCTIONS TO BIDDERS
DEMOLITION OF THE FUCHS INDUSTRIAL SITE
1.  DEFINED TERMS
1.1	Terms used in these Instructions to Bidders are defined and have the meanings assigned to them in the General Conditions.
2.  BIDDING DOCUMENTS
2.1	Complete sets of Bidding Documents may be obtained from the Oil Region Alliance, 217 Elm Street, Oil City, PA 16301, as stated in the Announcement of Invitation for Bids, or downloaded at https://oilregion.org/the-alliance/rfps/.
2.2	These Contract Documents include a complete set of bidding and contract forms which are for the convenience of Bidders and are not to be detached from the Contract Documents, filled out, or executed. Separate copies of Bid Forms are furnished for that purpose; however, the Oil Region Alliance or its Consultant assumes no responsibility for errors or misinterpretations resulting from the use of incomplete sets of Bidding Documents.
3.  QUALIFICATIONS OF BIDDERS
3.1	To demonstrate qualifications to perform the work, each bidder must be prepared to submit, as part of the bid, written evidence of his qualifications, including his previous experience, organization and equipment available for the project, financial data, and authority to conduct business in the jurisdiction where the project is located.
3.2	The right is reserved to reject any Bid where an investigation of the available evidence or information does not satisfy the Oil Region Alliance that the Bidder is qualified to carry out properly the terms of the Contract.
4.  EXAMINATION OF CONTRACT DOCUMENTS AND SITE
4.1	Before submitting a Bid, each Bidder must examine the Contract Documents thoroughly, including the Demolition Plans and the Pre-Demolition Hazardous Building Materials Survey; visit the site and familiarize himself with local conditions that may in any manner affect cost, progress, or performance of the work; familiarize himself with Federal, State, and local laws, ordinances, rules and regulations that may in any manner affect cost, progress, or performance of the work; and study and carefully correlate his observations with the Contract Documents. A mandatory pre-bid meeting will be held at 2:00 pm on November 17, at the Fuchs Industrial Site Building, 105 8th Street, Emlenton, PA. Contractors will be given the opportunity to access and view the project at this meeting only. Representation at the meeting will be required of every prime bidder, and bids from other companies will not be opened.
4.2	The lands upon which the work is to be performed, rights-of-way for access thereto, and lands designated for use by Contractor in performing the work are identified in the Drawings included in the Contract Documents.
4.3	The submission of a Bid will constitute a representation by the Bidder that he has complied with every requirement of this Article 4 and that the Contract Documents are sufficient in scope and detail to indicate and convey understanding of all terms and conditions for performance of the Work.
5.  INTERPRETATIONS
5.1	No oral interpretation will be made to any Bidder as to the meaning of the Contract Documents or any part thereof. Every request for such an interpretation shall be made in writing to Oil Region Alliance. Any inquiry received seven (7) or more days prior to the date fixed for opening of Bids will be given consideration. Every interpretation made to a Bidder will be in the form of an Addendum to the Contract Documents, and when issued, will be on file in the offices of Oil Region Alliance at least five (5) days before Bids are opened. In addition, all Addenda will be mailed or emailed to each person holding Contract Documents, but it shall be the Bidder's responsibility to make inquiry as to the Addenda issued. All such Addenda shall become part of the Contract and all Bidders shall be bound by such Addenda, whether or not received by the Bidders.
6.  DELETED
7.  BID SECURITY
7.1	Bid Security shall be made payable to the Oil Region Alliance, in an amount of not less than ten (10) percent of the Bidder's maximum Bid price and in the form of a certified check, bank cashier's check, or a Bid Bond issued by a Surety meeting the requirements of paragraph 7.3.
7.2	The Bid Security of the lowest responsible Bidder will be retained until such Bidder has furnished the required Payment and Performance Bonds and certificates of insurance and executed the Agreement, whereupon it will be returned. If the lowest responsible Bidder fails to furnish the required Contract Security within ten (10) days of the Notice of Award or fails to execute and return the Agreement within ten (10) days of the Notice of Award, Owner may annul Notice of Award and the Bid Security of that Bidder will be forfeited. Bid Security of other Bidders will be returned as soon as practical after the Bid opening.
7.3	All bonds submitted as Bid Security shall be executed by surety companies legally authorized to do business in Pennsylvania. Such surety companies shall also be named in the current list of "Companies Holding Certificates of Authority as Acceptable Sureties on Federal Bonds and as Acceptable Reinsuring Companies" as published in current Circular 570 by the Audit Staff Bureau of Accounts, U.S. Treasury Department. Attorneys-In-Fact who sign Bid Bonds must file with each Bond a certified copy of their Power of Attorney to sign said Bonds, bearing the same date as the Bonds.
7.4	Revised Bids submitted before the opening of Bids, if representing an increase in excess of two percent (2%) of the original Bid, must have the Bid Security adjusted accordingly; otherwise the bid will not be considered.
8.  CONTRACT TIME
8.1	The number of days within which, or the date by which, the Work is to be completed (the Contract Time) is set forth in the Agreement.
9.  LIQUIDATED DAMAGES
9.1	Provisions for liquidated damages, if any, are set forth in the Agreement.
10.  DELETED
11.  SUBCONTRACTORS
11.1	If any bidder proposes to use a subcontractor to perform part of work, then he shall submit with his Bid a Statement of Subcontractor's Qualifications completed by the subcontractor being proposed. Failure to submit this Statement from each subcontractor will cause bid to be in default.
11.2	The lowest responsible Bidder, and any other Bidder so requested, will within seven (7) days after the day of the Bid opening submit to the Oil Region Alliance a list of all subcontractors and other persons and organizations (including those who are to furnish the principal items of material and equipment) proposed for those portions of the work as to which such identification is so required. Such list shall be accompanied by an experience statement with pertinent information as to similar projects and other evidence of qualification for each such subcontractor, person, and organization if requested by the Oil Region Alliance. If the Oil Region Alliance after due investigation has reasonable objection to any proposed Subcontractor, other person or organization, it may before giving the Notice of Award, request the lowest responsible Bidder to submit an acceptable substitute without an increase in Bid price. If the lowest responsible Bidder declines to make any such substitution, the contract shall not be awarded to such Bidder, but his declining to make any such substitution will not constitute grounds for sacrificing his Bid Security. For any Subcontractor, other person or organization so listed and to whom the Oil Region Alliance does not make written objection prior to the giving of the Notice of Award it will be deemed there is no objection.
11.3	No Contractor shall be required to contract with any Subcontractor, other person or organization against whom he has reasonable objection.
12.  DELETED
13.  BID FORM
13.1	All Bids must be submitted on the form supplied in the Contract Documents and shall be subject to all requirements of the Contract Documents, including these INSTRUCTIONS TO BIDDERS.
13.2	Bid Forms must be completed in ink or by typewriter. Where unit prices for estimated quantities appear on the Bid Form, the Bid price of each item on the form must be stated and extended; in case of a conflict, the unit price will take precedence and not the totals or extensions.
13.3	DELETED.
13.4	Bids by corporations must be executed in the corporate name by the president or vice-president (or other person having authority to bind the corporation, accompanied by corporate power of attorney) and the corporate seal must be affixed and attested by the secretary or an assistant secretary. The corporate address and state of incorporation shall be shown below the signature.
13.5	Bids by partnerships must be executed in the partnership name and signed by a partner, whose title must appear under the signature and the official address of the partnership must be shown below the signature.
13.6	All names must be typed or printed below the signature.
13.7	The Bid shall contain an acknowledgment of receipt of all Addenda (the numbers and dates of which shall be filled in on the Bid Form).
13.8	The address to which communications regarding the Bids are to be directed must be shown.
14.  SUBMISSION OF BIDS
14.1	Bids shall be submitted to the place and prior to the time indicated in the Invitation for Bids. The person designated to open bids will decide when the specified time has arrived, and no Bid received thereafter will be considered.
14.2	Bidding Documents including the Bid Form, Bid Security, and Statement of Bidder's Qualifications shall be enclosed in envelopes (outer and inner), both of which shall be sealed and clearly labeled with the project title, Contract number, name and address of Bidder, and date and time of Bid opening in order to guard against premature opening of the Bid.
14.3	Bids will not be accepted by facsimile (FAX machine) or e-mail.
15.  ALTERNATIVE BIDS
15.1	No Alternative Bids will be considered unless they are specifically requested.
16.  MODIFICATION AND WITHDRAWAL OF BIDS
16.1	Bids may be modified or withdrawn by an appropriate document duly executed (in the manner that a Bid must be executed) and delivered to the place where Bids are to be submitted at any time prior to the opening of Bids.
17.  OPENING OF BIDS
17.1	Bids will be publicly opened and read aloud, and an abstract of the amounts of the base Bids, unit prices, and major alternates (if any) will be made available after the opening of Bids.
18.  BIDS TO REMAIN OPEN
18.1	Except as otherwise permitted by law, Bids shall remain irrevocable for the period stated in the Announcement of Invitation for Bids.
19.  AWARD OF CONTRACT
19.1	Owner reserves the right to reject any and all Bids, to waive any and all informalities and the right to disregard all nonconforming, nonresponsive or conditional Bids. Owner reserves the right to award the Contract to whomever he chooses, and the award may be to other than the low bidder. Discrepancies between words and figures will be resolved in favor of words. Discrepancies between the indicated sum of any column of figures and the correct sum thereof will be resolved in favor of the correct sum.
19.2	In evaluating Bids, Owner shall consider the qualifications of the Bidders, whether or not the Bids comply with the prescribed requirements, and alternates and unit prices if requested in the Bid Form. It is Owner's intent to accept alternates (if any are accepted) in the order in which they are listed in the Bid Form but Owner may accept them in any order or combination.
19.3	Owner may consider the qualifications and experience of Subcontractors and other persons and organizations (including those who are to furnish the principal items of material or equipment) proposed for those portions of the Work as to which the identity of Subcontractors and other persons and organizations must be submitted. Operating costs, maintenance considerations, performance data and guarantees of materials and equipment may also be considered by Owner.
19.4	Owner may conduct such investigations as he deems necessary to assist in the evaluation of any Bid and to establish the responsibility, qualifications and financial ability of the Bidders, proposed Subcontractors and other persons and organizations to do the Work or furnish equipment in accordance with the Contract Documents to Owner's satisfaction within the prescribed time.
19.5	If the contract is to be awarded it will be awarded to the lowest responsible Bidder whose evaluation by Owner indicates to Owner that the award will be in the best interests of the Project.
19.6	If the contract is to be awarded, Owner will give the lowest responsible Bidder a Notice of Award within the time specified for Bids to remain irrevocable.
20.  PERFORMANCE AND OTHER BONDS
20.1	The lowest responsible Bidder shall, within ten (10) days of the issuance of the Notice of Award, furnish acceptable Performance and Payment Bonds, each in an amount equal to 100% of the Bid, to the Oil Region Alliance Office unless otherwise specified.
21.  SIGNING OF AGREEMENT
21.1	When Owner gives a Notice of Award to the lowest responsible Bidder, it will be accompanied by at least four (4) unsigned duplicate original copies of the Agreement. Within ten (10) days thereafter, Contractor shall sign and deliver said duplicate original copies of the Agreement to Owner. The duplicate original copies will then be signed by Owner. Owner will identify those portions of the Contract Documents not fully signed by Owner and Contractor and such identification shall be binding on all parties. The Owner and the Contractor will each receive an executed duplicate copy of the Contract Documents.
22.  WAGES AND SALARIES
22.1	Particular attention is called to the requirements for payment of Pennsylvania prevailing wage and salary rates, and the conditions of employment with respect to certain categories and classifications of employees.
22.2	The rates of pay set forth under the Wage Requirements are the minimum to be paid during the life of the Contract. It is the responsibility of Bidders to inform themselves as to local labor conditions, such as the length of work day and work week, overtime compensation, health and welfare contributions, labor supply, and prospective changes or adjustments of rates.
23.  DELETED
24.  COMPLIANCE WITH FEDERAL, STATE, AND LOCAL LAWS
24.1	Particular attention is called to the necessity of complying with all Federal, State, and Local laws and regulations.

END OF SECTION
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INSTRUCTIONS TO BIDDERS	ITB - 1
BID FORM
DEMOLITION OF THE FUCHS INDUSTRIAL SITE

	To:
	Oil Region Alliance
217 Elm Street
Oil City, PA 16301
	From:
	______________________________
______________________________
______________________________




1.	The undersigned BIDDER proposes and agrees, if this Bid is accepted, to enter into an Agreement with OWNER in the form included in the Contract Documents to complete all Work as specified or indicated in the Contract Documents for the Contract Price indicated in this Bid within the Contract Time and in accordance with the Contract Documents.
The undersigned BIDDER submits this Bid with the understanding that the OWNER reserves the right to reject any or all bids submitted.
2.	BIDDER accepts all of the terms and conditions of the Instructions to Bidders, including without limitation those dealing with the disposition of Bid Security. This Bid will remain open for sixty (60) days after the day of Bid opening, unless award is delayed due to required approvals of another governmental agency, the sale of bonds, or the award of a grant or grants, in which case Bids shall be irrevocable for one hundred twenty (120) days in compliance with Act No. 317 of 1978 approved November 26, 1978, except as set forth in Pennsylvania Statute, Public Contracts - Withdrawal of Bids, Act of January 23, 1974, (P.L. 9, No. 4).
BIDDER shall submit the required Performance and Payment Bonds and Certificates of Insurance within ten (10) days after the date of OWNER'S Notice of Award.
BIDDER shall sign and return the Agreement within ten (10) days after the date of OWNER's Notice of Award.
3.	In submitting this Bid, BIDDER represents, as more fully set forth in the Agreement, that:
3.1	BIDDER has examined copies of all the Contract Documents, including the Demolition Plans and the Pre-Demolition Hazardous Building Materials Survey, and hereby acknowledges receipt of the following Addenda:
	No.
	Addendum Number
	Date

	1
	
	

	2
	
	

	3
	
	



3.2	This Bid is genuine and not made in the interest of or on behalf of any undisclosed person, firm or corporation and is not submitted in conformity with any agreement or rules of any group, association, organization or corporation; BIDDER has not directly or indirectly induced or solicited any other Bidder to submit a false or sham Bid; BIDDER has not solicited or induced any person, firm or a corporation to refrain from bidding; and BIDDER has not sought by collusion to obtain for himself any advantage over any other Bidder or over OWNER; and
3.3	BIDDER hereby states that Bidder has available adequate equipment and finances to properly and expeditiously prosecute the Work as bid, and is prepared to present further information to substantiate this statement.
4.	BIDDER shall complete the Work for the price(s) shown on the attached Standard Form for Bid Proposal.
BIDDER agrees that the Work will be completed within the Contract Time, on or before the dates or within the number of consecutive calendar days indicated in the Agreement.
BIDDER accepts the provisions of the Agreement as to liquidated damages in the event of failure to complete the Work on time.
5.	The following documents are attached to and made a condition of this Bid:
a.	Bid Form
b.	Required Bid Security
c.	Statement of Bidder's Qualifications with supporting data
d.	Statement of Subcontractor's Qualifications
e.	Other documents as required by the Instructions to Bidders or Contract Documents
f.	Non-Discrimination Disclosure
6.	Communications concerning this Bid may be forwarded to the address of BIDDER indicated below.
7.	The terms used in this Bid have the meanings assigned to them in the General Conditions.
8.	BIDDER covenants and warrants that he has had sufficient time to examine the site of the Work; that he has examined the site of the Work; and that he has based the within Contract Prices on his own independent examination and investigation of the site. BIDDER has examined the legal requirements (federal, state, and local laws, ordinances, rules and regulations) and the conditions affecting cost, progress or performance of the work and has made such independent investigations as BIDDER deems necessary.

BASE BID
The undersigned bidder proposes to perform the work in accordance with the Emlenton Demolition of Fuchs Industrial Site Contract Documents, including all work shown on the Demolition Plans (Sheets C000, C110 and C141 through C143) and all hazardous materials work required by the Pre-Demolition Hazardous Building Materials Survey, for the Lump-Sum Contract amount of:

____________________________________________________________________ Dollars ($________________________).


AN INDIVIDUAL

	By:
	______________________________   ______________________________
(Signature)                                        (Typed Name)

	Doing Business As:
	____________________________________________

	Business Address:
	____________________________________________

	Phone No.:
	____________________________________________

	Fax No.:
	____________________________________________

	Email:
	____________________________________________




A PARTNERSHIP

	Firm Name:
	____________________________________________

	By:
	______________________________   ______________________________
(Partner)                                            (Partner)

	(SEAL)
	

	Business Address:
	____________________________________________

	Phone No.:
	____________________________________________

	Fax No.:
	____________________________________________

	Email:
	____________________________________________




A CORPORATION

	Corporation Name:
	____________________________________________

	State of Incorporation:
	____________________________________________

	By:
	______________________________   ______________________________
(Person Authorized to Sign)                   (Title)

	(CORPORATE SEAL)
	

	Attest:
	______________________________
(Corporate Secretary)

	Business Address:
	____________________________________________

	Phone No.:
	____________________________________________

	Fax:
	____________________________________________

	Email:
	____________________________________________




SUBMITTED this ________ day of ____________________, 20____.
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BID FORM – FUCHS INDUSTRIAL SITE DEMOLITION	BF - 1
BID BOND
KNOW ALL MEN BY THESE PRESENTS:

THAT ________________________________________ of ________________________________________ as Principal, and ________________________________________ a Corporation organized and existing under the laws of the State of ____________________ and authorized to do business in the State of Pennsylvania, as Surety, are held and firmly bound unto the Oil Region Alliance, Venango County, Pennsylvania, as Obligee, in the full and just sum of ____________________________________________ Dollars ($________________), lawful money of the United States of America, for the payment of which sum, well and truly to be made, we bind ourselves, our heirs, executors, administrators, successors and assigns, jointly and severally, firmly by these presents.
WHEREAS, the said Principal is herewith submitting its Bid proposal for the Demolition of the Fuchs Industrial Site.
THE CONDITION OF THIS OBLIGATION is such that if the aforesaid Principal shall be given Notice of Award of the Contract, the said Principal will, within the time required, give good and sufficient Bonds to secure the performance of the terms and conditions of the Contract and enter into an Agreement, then this obligation to be void; otherwise, the Principal and Surety will pay unto the Obligee the full amount of this Bid Security.
Signed, Sealed and Delivered this ________ day of ____________________, 20____.

	Attest:
	PRINCIPAL

	______________________________
Secretary
	By: ______________________________
President/Owner

	
	(SEAL)

	
	SURETY

	______________________________
Witness
	By: ______________________________
Attorney-in-Fact

	
	(SEAL)




NOTES:
1.	Attach an appropriate Power of Attorney, dated as of the same date as the bond, evidencing the authority of the Attorney-in-Fact to act on behalf of the corporation.
2.	If the Contractor is a Partnership, all partners shall execute the bond.
3.	Surety companies executing bonds must appear on the U.S. Department of the Treasury most current Bond List (Circular 570 as amended). Bond amounts are subject to the underwriting limitations listed in the most recent Circular 570.
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BID BOND	BB - 1
STATEMENT OF BIDDER'S QUALIFICATIONS

The following is a list of questions that must be answered clearly and comprehensively by each Bidder. Additional information may be submitted. This statement must be notarized.
1.	Name of Bidder?
2.	Permanent main office address?
3.	When organized?
4.	If a corporation, where incorporated?
5.	How many years have you been engaged in the contracting business under your present firm or trade name?
6.	Contracts on hand: Show a schedule of these, including amounts of each contract and anticipated dates of completion.
7.	General character of work performed by your company?
8.	Have you ever failed to complete any work awarded to you? If so, where and why?
9.	Have you ever defaulted on a contract? If so, where and why?
10.	List the more important projects recently completed by your company, stating the approximate cost for each, and the month and year completed.
11.	List your major equipment available for this contract.
12.	Experience in construction work similar in importance to this project, including demolition and asbestos abatement work.
13.	Background and experience of the principal members of your organization, including the officers.
14.	Credit available?
15.	Bank reference?
16.	Will you, upon request, fill out a detailed financial statement and furnish any other information that may be required?
17.	Enclose list of at least four previous/current clients for reference purposes, including the company name, address, phone, fax and e-mail for each client.
18.	The undersigned hereby authorizes and requests any person, firm, or corporation to furnish any information requested by the Oil Region Alliance in verification of this Statement of Bidder's Qualifications.

SUBMITTED this ________ day of ____________________, 20____.

	Signed
	____________________________________________

	Title
	____________________________________________




State of ____________________ )
County of ____________________ )

______________________________ being duly sworn deposes and says that he is ______________________________ of ______________________________ and that the answers to the foregoing questions and all statements therein contained are true and correct.

Subscribed and sworn to before me this ________ day of ____________________, 20____.

	______________________________
Notary Public
	______________________________
My Commission Expires
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STATEMENT OF BIDDER'S QUALIFICATIONS	SBQ - 1
STATEMENT OF ASSURANCES AND INSURANCE INFORMATION
Enclosure with proposal submitted to Oil Region Alliance of Business, Industry & Tourism

1.  IDENTIFICATION
Proposal Submitted by: ____________________________________________________
(Organization name)
In response to Invitation For Bids issued by Oil Region Alliance (ORA) entitled: Demolition of the Fuchs Industrial Site Work.
Date Statement Signed: ______________________
2.  CERTIFICATION REGARDING DEBARMENT, SUSPENSION AND OTHER RESPONSIBILITY MATTERS
	☐ YES   ☐ NO

If no, elaborate at 8—Comments.
	I certify that the proposing firm and its principals as of today's date are not presently debarred, suspended, proposed for disbarment, declared ineligible, or voluntarily excluded from covered transactions by any Federal department or agency, or by the Commonwealth of Pennsylvania. I also certify that we have not within a three-year period preceding this proposal date been convicted of or had a civil judgment rendered against any of us in connection with obtaining, attempting to obtain, or performing a public transaction or contract under a public transaction; violation of Federal or Commonwealth antitrust statutes or commission of embezzlement, theft, forgery, bribery, falsification or destruction of records, making false statements, or receiving stolen property. I also certify that we are not presently indicted for or otherwise criminally or civilly charged by a governmental entity with commission of any of the offenses listed above. I also certify that within the three-year period preceding this proposal, we have not had one or more public transactions (Federal, Commonwealth, or local) terminated for cause or default. I also certify that the proposing firm is not delinquent in any Commonwealth obligation, including taxes. I further affirm that if, at any time during the term of any contract resulting from this proposal, the firm becomes delinquent, or is debarred, or is suspended, the firm will within 15 days of that date of delinquency, suspension or debarment provide written notice to the Oil Region Alliance.



3.  CERTIFICATION REGARDING DRUG-FREE WORKPLACE
	☐ YES   ☐ NO

If no, elaborate at 8—Comments.
	I certify that the proposing firm will or will continue to provide a drug-free workplace by establishing an ongoing drug-free awareness program to inform employees about the dangers of drug abuse in the workplace, the firm's policy of maintaining a drug-free workplace, any available drug counseling/rehabilitation and employee assistance programs, and the penalties that may be imposed upon employees for drug abuse violations occurring in the workplace.

	☐ YES   ☐ NO

If no, elaborate at 8—Comments.
	The proposing firm and any subcontractors shall establish and maintain a written drug-free workplace policy and shall inform their employees of the policy. Upon request by ORA, a copy shall be furnished for project files.

	☐ YES   ☐ NO

If no, elaborate at 8—Comments.
	I also certify that I will not engage in the unlawful manufacture, distribution, dispensing, possession, or use of a controlled substance in conducting any activity with the funds provided by ORA. If I am convicted of a criminal drug offense, I will report that within 10 calendar days to the ORA-assigned project manager.



4.  CERTIFICATION REGARDING LOBBYING
	☐ YES   ☐ NO

If no, elaborate at 8—Comments.
	I certify that no part of the money paid by ORA to my firm (if selected as a vendor to perform the work as described in the accompanying proposal) shall be used directly or indirectly to pay for any personal service, advertisement, telegram, telephone, letter, printed or written matter, or any other device, intended or designed to influence in any manner a Member of Congress, to favor or oppose, by vote or otherwise, any legislation or appropriation by Congress, whether before or after the introduction of any bill or resolution proposing such legislation or appropriation.



5.  CERTIFICATION REGARDING MINORITY-OWNED BUSINESS ENTERPRISE/WOMAN-OWNED BUSINESS ENTERPRISE
	☐ YES   ☐ NO
	I certify that the firm submitting this proposal is an official Minority-owned Business Enterprise.

	☐ YES   ☐ NO
	I certify that the firm submitting this proposal is an official Woman-owned Business Enterprise.

	☐ YES   ☐ NO

If no, elaborate at 8—Comments.
	I certify that if my firm is selected as the vendor to perform work as described in the accompanying proposal and we determine that part of the scope of work needs to be subcontracted, we will give special favorable consideration to selecting Minority-owned Business Enterprises and/or Woman-owned Business Enterprises as subcontractors.



6.  CERTIFICATION REGARDING NON-DISCRIMINATION/SEXUAL HARASSMENT
	☐ YES   ☐ NO

If no, elaborate at 8—Comments.
	I certify that if my firm is selected as the vendor to perform work as described in the accompanying proposal, we agree to the following non-discrimination clauses: (a) In the hiring of any employees directly or via subcontractors, no one acting on our behalf shall, by reason of gender, age, sexual orientation, national origin, handicap disabilities, religion, race, creed, or color, discriminate against any citizen of the Commonwealth of Pennsylvania who is qualified and available to perform the work to which the employment relates; and (b) The firm and/or any subcontractor or any person on our/their behalf shall not in any manner discriminate against or intimidate any employee involved in this work on account of gender, race, creed, or color.

	☐ YES   ☐ NO

If no, elaborate at 8—Comments.
	The proposing firm and any subcontractors shall establish and maintain a written sexual harassment policy and shall inform their employees of the policy. Upon request by ORA, a copy shall be furnished for project files. The policy must contain a notice that sexual harassment will not be tolerated and employees who practice it will be disciplined.



7.  INSURANCE INFORMATION
My firm has the following insurance policies currently in place:
	Policy Type
	Policy Number
	Insurance Company
	Policy Ending Date

	General Liability
	
	
	

	Property Insurance
	
	
	

	Workmen's Compensation
	
	
	

	Employer's Liability
	
	
	

	Automobile Liability
	
	
	




	☐ YES   ☐ NO
	Our current general liability policy already lists all of the following as additional insured parties: Commonwealth of Pennsylvania; Oil Region Alliance of Business, Industry & Tourism.

	☐ YES   ☐ NO

If no, elaborate at 8—Comments.
	I certify that, upon selection of my firm as a vendor to perform the work described in the accompanying proposal, we will promptly revise our general liability policy to also include as additional insured parties any of the following parties which are not already listed on our current policy: Commonwealth of Pennsylvania; Oil Region Alliance of Business, Industry & Tourism. I understand that ORA will notify selected vendor as to the specific funding streams involved, which may include more entities than those in this list, some of which may also require such coverage as additional insured parties as conditions of their grant support. I further agree to provide ORA with written verification of the new coverage of each required additional insured party.



8.  COMMENTS AND CLARIFICATIONS
See additional attachment(s): ____________________________________________________
9.  SIGNATURE
By my signature below, I certify that I am an authorized agent on behalf of the entity submitting a proposal to ORA, and that I certify the accuracy of the statements and insurance information indicated above.

	______________________________
(Signature of Authorized Agent)
	______________________________
(Title of Authorized Agent)

	
______________________________
(Typed or Printed Name of Authorized Agent)
	
______________________________
(Date Signed)

	
______________________________
(Entity Submitting Proposal)
	
______________________________
(Mailing Address)

	
______________________________
(Authorized Agent's Telephone Number)
	
______________________________
(Agent's E-mail Address)
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STATEMENT OF ASSURANCES	SA - 1
NONDISCRIMINATION / SEXUAL HARASSMENT

1.  REPRESENTATIONS
The Contractor represents that it is presently in compliance with and will remain in compliance with all applicable federal, state, and local laws, regulations, and policies relating to nondiscrimination and sexual harassment for the term of the agreement. The Contractor shall, upon request and within the time periods requested by the Commonwealth, furnish all necessary employment documents and records, including EEO-1 reports, and permit access to its books, records, and accounts by the Commonwealth for the purpose of ascertaining compliance with provisions of this Nondiscrimination/Sexual Harassment Clause.
2.  NONDISCRIMINATION/SEXUAL HARASSMENT OBLIGATIONS
The Contractor shall not:
a.	in any manner discriminate in the hiring of any employee(s) for the performance of the activities required under this agreement or any subgrant agreement, contract, or subcontract, by reason of race, gender, creed, color, sexual orientation, gender identity or expression, or in violation of the Pennsylvania Human Relations Act ("PHRA") and applicable federal laws, against any citizen of this Commonwealth who is qualified and available to perform the work to which the employment relates.
b.	in any manner discriminate by reason of race, gender, creed, color, sexual orientation, gender identity or expression, or in violation of the PHRA and applicable federal laws, against or intimidate any of its employees.
c.	in any manner discriminate by reason of race, gender, creed, color, sexual orientation, gender identity or expression, or in violation of the PHRA and applicable federal laws, in the provision of services under this agreement or any subgrant agreement, contract, or subcontract.
d.	in any manner discriminate by reason of race, gender, creed, color, sexual orientation, gender identity or expression, or in violation of PHRA and applicable federal laws, against any subgrantee, contractor, subcontractor, or supplier who is qualified to perform the work to which this agreement relates.
e.	in any manner discriminate against employees by reason of participation in or decision to refrain from participating in labor activities protected under the Public Employee Relations Act, Pennsylvania Labor Relations Act, or National Labor Relations Act, as applicable, and to the extent determined by entities charged with the Acts' enforcement and shall comply with any provision of law establishing organizations as employees' exclusive representatives.
3.  ESTABLISHMENT OF CONTRACTOR POLICY
The Contractor shall establish and maintain a written nondiscrimination and sexual harassment policy that complies with the applicable law and these Nondiscrimination/Sexual Harassment provisions and shall inform its employees in writing of the policy. The policy must contain a provision that states that sexual harassment will not be tolerated and employees who practice it will be disciplined. For the entire period of this agreement, the Contractor shall: (1) post its written nondiscrimination and sexual harassment policy or these Nondiscrimination/Sexual Harassment provisions conspicuously in easily accessible and well-lighted places customarily frequented by employees at or near where the grant activities are performed; or (2) provide electronic notice of the policy or this clause to its employees not less than annually.
4.  NOTIFICATION OF VIOLATIONS
The Contractor's obligations pursuant to these provisions are ongoing from the effective date and through the termination date of the agreement. Accordingly, the Contractor shall notify the Commonwealth if, at any time during the term of this agreement, it becomes aware of any actions or occurrences that would result in violation of these provisions.
5.  CANCELLATION OR TERMINATION OF AGREEMENT
The Commonwealth may cancel or terminate this agreement and all money due or to become due under this agreement may be forfeited for a violation of the terms and conditions of these Nondiscrimination/Sexual Harassment provisions. In addition, the granting agency may proceed with debarment or suspension and may place the Contractor in the Contractor Responsibility File.
6.  SUBGRANT AGREEMENTS, CONTRACTS, AND SUBCONTRACTS
The Contractor shall include these Nondiscrimination/Sexual Harassment provisions in its contracts and subcontracts with all contractors, and subcontractors providing goods or services under this agreement. The incorporation of these provisions in the contractor's contracts or subcontracts does not create privity of contract between the Commonwealth and any contractor, or subcontractor, and no third-party beneficiaries are created by those provisions. If the Contractor becomes aware of a contractor's or subcontractor's violation of these provisions, the Contractor shall use its best efforts to ensure the contractor's or subcontractor's compliance with these provisions.

END OF SECTION
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NONDISCRIMINATION / SEXUAL HARASSMENT	NDC - 1
SCHEDULE OF PROPOSED SUBCONTRACTORS

SUBCONTRACTOR 1
	Organization
	

	Address
	

	Telephone
	

	Fax
	

	E-mail
	

	Federal Identification Number
	

	Type of Business (Individual; Partnership; or Corporation)
	

	Work to be Performed
	



SUBCONTRACTOR 2
	Organization
	

	Address
	

	Telephone
	

	Fax
	

	E-mail
	

	Federal Identification Number
	

	Type of Business (Individual; Partnership; or Corporation)
	

	Work to be Performed
	



SUBCONTRACTOR 3
	Organization
	

	Address
	

	Telephone
	

	Fax
	

	E-mail
	

	Federal Identification Number
	

	Type of Business (Individual; Partnership; or Corporation)
	

	Work to be Performed
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SCHEDULE OF PROPOSED SUBCONTRACTORS	SPS - 1
SCHEDULE OF PRIOR AND CURRENT CLIENTS

CLIENT 1
	Client
	

	Address
	

	Telephone
	

	Fax
	

	E-mail
	

	Contact's Name and Title
	

	Type of Business (Individual; Partnership; or Corporation)
	



CLIENT 2
	Client
	

	Address
	

	Telephone
	

	Fax
	

	E-mail
	

	Contact's Name and Title
	

	Type of Business (Individual; Partnership; or Corporation)
	



CLIENT 3
	Client
	

	Address
	

	Telephone
	

	Fax
	

	E-mail
	

	Contact's Name and Title
	

	Type of Business (Individual; Partnership; or Corporation)
	



CLIENT 4
	Client
	

	Address
	

	Telephone
	

	Fax
	

	E-mail
	

	Contact's Name and Title
	

	Type of Business (Individual; Partnership; or Corporation)
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SCHEDULE OF PRIOR AND CURRENT CLIENTS	SPC - 1
AGREEMENT

THIS AGREEMENT, is entered into this ________ day of ____________________, 20____ by and between the Oil Region Alliance, Oil City, Venango County, Pennsylvania, hereinafter called OWNER, and
	a Corporation known as
	____________________________________________

	organized and existing under the laws of the State of
	____________________________________________

	or a Partnership known as
	____________________________________________

	consisting of the following members:
	____________________________________________

	or an Individual trading as
	____________________________________________



hereinafter called CONTRACTOR.
WITNESSETH, that OWNER and CONTRACTOR, in consideration of the mutual covenants hereinafter set forth, agree as follows:
Article 1.  WORK
CONTRACTOR shall complete all Work as specified and indicated in the Contract Documents for Demolition of the Fuchs Industrial Site Work.
Article 2.  CONTRACT TIME
2.1	Work shall be complete and ready for final payment in accordance with Paragraph 14.1 of the General Conditions on or before April 15, 2027. All work shall be done Monday through Friday; no work shall be allowed on Saturday or Sunday.
2.2	Liquidated Damages: OWNER and CONTRACTOR recognize that time is of the essence of this Agreement and that OWNER will suffer financial loss if the Work is not substantially complete within the time specified in paragraph 2.1 above, plus any extensions thereof allowed in accordance with Article 12 of the General Conditions. They also recognize the delays, expense and difficulties involved in proving in a legal or arbitration proceeding the actual loss suffered by OWNER if the Work is not substantially complete on time. Accordingly, instead of requiring any such proof, OWNER and CONTRACTOR agree that as liquidated damages for delay (but not as a penalty) CONTRACTOR shall pay OWNER Two Hundred Dollars ($200.00) for each calendar day that expires after the times specified in paragraph 2.1 until the Work is substantially complete.
Article 3.  CONTRACT PRICE
OWNER shall pay CONTRACTOR for performance of the Work in accordance with the Contract Documents in lawful money of the United States of America, and subject to additions and deductions as provided in the General Conditions, the lump-sum Contract Price stated in CONTRACTOR's Bid.
Article 4.  PAYMENT
CONTRACTOR shall submit applications for payment twice a month — one for the 1st through the 15th and one for the 16th through the end of each month — in accordance with Article 14 of the General Conditions. The application will be processed by CONSULTANT as provided in the General Conditions.
Article 5.  LOCATION OF WORK
The project is located at 105 8th Street in the Borough of Emlenton, Venango County, Pennsylvania, as shown on the Drawings included as part of the Contract Documents.
Article 6.  GUARANTEE PERIOD
CONTRACTOR shall warrant and guarantee his Work and materials in accordance with Article 13 of the General Conditions for a period of three years from the date of Substantial Completion.
Article 7.  CONTRACTOR'S REPRESENTATIONS
In order to induce OWNER to enter into this Agreement CONTRACTOR makes the following representations:
7.1	CONTRACTOR has familiarized himself with the nature and extent of the Contract Documents, Work, locality, and with all local conditions and federal, state and local laws, ordinances, rules and regulations that in any manner may affect cost, progress or performance of the Work.
7.2	CONTRACTOR further covenants and warrants that he has had sufficient time to examine the site of the Work; that he has examined the site of the Work; and that he has based the within contract prices on his own independent examination and investigation of the site, and conditions and has not relied on any information furnished to him by OWNER or CONSULTANT.
7.3	CONTRACTOR has correlated the results of such observations, examinations, investigations, tests, reports and data with the terms and conditions of the Contract Documents.
7.4	CONTRACTOR has given CONSULTANT written notice of all conflicts, errors or discrepancies that he has discovered in the Contract Documents and the written resolution thereof by CONSULTANT is acceptable to CONTRACTOR.
Article 8.  CONTRACT DOCUMENTS
The Contract Documents which comprise the entire agreement between OWNER and CONTRACTOR are attached to this Agreement by reference, made a part hereof and consist of the following:
8.1	This Agreement
8.2	Performance, Payment and other Bonds
8.3	Nondiscrimination Clause
8.4	General Conditions – Parts I and II
8.5	Specifications, including the General Technical Specifications and Divisions 01 and 02
8.6	Drawings: Fuchs Lubricants Co. Site Demolition/E&S Plans, Sheets C000, C110 and C141 through C143, prepared by Moody and Associates, Inc., dated October 2026
8.7	Pre-Demolition Hazardous Building Materials Survey, Fuchs Lubricants Co. Site, prepared by Moody and Associates, Inc., dated June 24, 2025
8.8	Addenda numbers ________ through ________, inclusive
8.9	CONTRACTOR's Bid
8.10	Documentation submitted by CONTRACTOR prior to Notice of Award
8.11	Any Modification, including Change Orders, duly delivered after execution of Agreement.
Article 9.  MISCELLANEOUS
9.1	Terms used in this Agreement which are defined in Article 1 of the General Conditions shall have the meanings indicated in the General Conditions.
9.2	OWNER and CONTRACTOR each binds himself, his partners, successors, assigns and legal representatives to the other party hereto, his partners, successors, assigns and legal representatives in respect to all covenants, agreements and obligations contained in the Contract Documents.
Article 10.  OTHER PROVISIONS
10.1	CONTRACTOR agrees that he, and his Subcontractors, will pay each person engaged in the Work not less than the minimum wage determination for the applicable described class of work, in accordance with law, as specified by the Commonwealth of Pennsylvania or the United States Government, under any Pennsylvania or federal law which is made applicable to the Project, by the terms of the Contract Documents or addenda thereto.
10.2	It is understood that CONTRACTOR in signing this Agreement shall employ only competent and first-class workers and mechanics.
10.3	CONTRACTOR agrees that in the case of any conflict between any of the provisions of the Contract Documents, the provisions most beneficial to OWNER shall prevail and govern.
10.4	CONTRACTOR agrees that no verbal agreement or undertaking with any officer, agent or employee of OWNER either before or after the execution of this Agreement shall alter, amend, modify or rescind any of the terms or provisions contained in any of the Contract Documents.
Article 11.  QUALITY OF SERVICE
CONTRACTOR shall perform its services with care, skill and diligence, in accordance with the applicable professional standards currently recognized by such profession. CONTRACTOR shall comply with all applicable federal, state and local laws, ordinances, codes and regulations in performing its services.
Article 12.  INDEPENDENT CONTRACTORS
During performance of this Contract, CONTRACTOR shall be an independent contractor and not an agent of OWNER. CONTRACTOR shall supervise the performance of its own services and shall have control of the manner and means by which services are performed, subject to compliance with this contract.
Article 13.  NON-ASSIGNABILITY
CONTRACTOR shall not subcontract nor assign this Contract or otherwise dispose of its right, title, or interest therein to any other firm without obtaining the prior written consent by OWNER. Consent by OWNER to any assignment or subcontract of the work shall not be deemed to create a contractual relationship between OWNER and the subcontracting party or assignee.
Article 14.  THIRD PARTY INFORMATION
OWNER agrees that CONTRACTOR may solicit and reasonably rely on third party information essential and relative to the performance of CONTRACTOR in carrying out the requirements of this Contract whenever such information is under the control of a third party. CONTRACTOR will be responsible and liable for the direct or indirect consequences of its reasonable reliance on such third party information.
Article 15.  PERSONNEL
All personnel in the employ of CONTRACTOR, or approved subcontractors, who work on this project shall keep a record of time spent. This record of time will be made available upon request to OWNER and/or contract auditors during the period of this contract and until April 15, 2027.
CONTRACTOR and any subcontractors shall make and document diligent efforts to include Disadvantaged Business Enterprises (DBE) among the list of subcontractors assembled to conduct this Commonwealth-funded building demolition project.
Article 16.  SUBCONTRACTORS
If CONTRACTOR determines that services of subcontractors are required, CONTRACTOR will, within 10 days of the execution of this agreement, furnish OWNER with the complete business names, addresses, telephone numbers, fax numbers, e-mail addresses, and contact person's name and title for each new potential subcontractor. OWNER will have the right of prior approval, which shall not be unreasonably withheld.
Article 17.  OWNERSHIP OF PROPERTY INVOLVED
The Oil Region Alliance of Business, Industry & Tourism is the sole owner of the work site property, Fuchs Industrial Site, 105 8th Street, Emlenton, PA 16373. No changes of ownership are envisioned during the contract period.
Article 18.  TERMINATION
Either party upon seven (7) days written notice may terminate this contract. Should termination occur prior to the completion of the scope of work, CONTRACTOR will be paid for labor and expenses incurred through the date of termination, in accordance with the payment schedule referenced at Articles 2, 3, and 4 of this contract.
Article 19.  NONDISCRIMINATION
CONTRACTOR will not discriminate against any employee or applicant for employment because of race, religion, ancestry, income, sex, age, gender, sexual orientation, disabilities, creed, handicap, color or national origin in accordance with the Nondiscrimination Clause (appended as Exhibit A). In that Exhibit, CONTRACTOR means ____________________________________________ for the purposes of this Contract.
Article 20.  HOLD HARMLESS
CONTRACTOR shall hold the U. S. Government, Commonwealth of Pennsylvania, and the ORA harmless from, defend, and indemnify each of these agencies/entities against, any and all claims, demands, and actions which have been determined by a court of competent jurisdiction to have been solely the result of any activities performed by CONTRACTOR and its employees and agents, under this Contract in a matter which is contrary to the direction of the Commonwealth of Pennsylvania or ORA and shall defend any and all actions brought against ORA arising from CONTRACTOR's negligence.
It is understood that CONTRACTOR will have its standard liability insurance policies name as additional insureds the Commonwealth of Pennsylvania and the Oil Region Alliance as relates to claims of bodily injury and or property damage arising out of any services performed by CONTRACTOR or its employees or agents under this Contract including business and non-business invitees and their property and all other property (including vehicles, buildings, vegetation, and/or fixtures) sustaining damage as a direct or indirect result of the execution of this project, whether or not actually engaged in the project at the time the claim arises. Such policies shall not include any provision limiting the then existing sovereign immunity of the Commonwealth of Pennsylvania or the ORA or of its agents or employees. Upon request, CONTRACTOR shall furnish to OWNER proof of insurance as additional parties as required by this Article.
Article 21.  ACKNOWLEDGEMENT OF FEDERAL/STATE/LOCAL ASSISTANCE
CONTRACTOR in every publication and publicity release concerning this project will acknowledge financial assistance as follows: "This project was funded by a grant provided by the Industrial Sites Reuse Program Grant, Department of Community and Economic Development, via the Oil Region Alliance of Business, Industry & Tourism."
Article 22.  COMPLIANCE WITH FEDERAL/STATE/LOCAL REGULATIONS
All activities authorized by this Contract shall be performed in accordance with applicable statutes, applicable conditions, relevant directives, guidelines, application procedures, and requirements as attached hereto or otherwise provided by the Keystone Communities Grant Program agreements with ORA. CONTRACTOR acknowledges that this Contract is subject to all requirements set forth herein and further agrees that it will comply with additional requirements taking effect during this contract period and determined by the Keystone Communities Grant Program as necessary.
Article 23.  AMENDMENTS TO AGREEMENT
Any changes in the Scope of Work (as described in the Invitation for Bids and the CONTRACTOR's bid) to be performed under this Contract or any changes in the amounts or methods of compensation must be incorporated in written amendments to this Contract in order to be considered binding on the parties.
Amendments shall not take effect until they carry the signatures of the authorized agents of OWNER and CONTRACTOR.
Article 24.  COMPLIANCE WITH CONTRACTOR RESPONSIBILITY
CONTRACTOR certifies that it is not currently under suspension or debarment by the Commonwealth, any other state, or the federal government. If CONTRACTOR enters into subcontracts or employs under this Contract any subcontractors/individuals who are currently suspended or debarred by the Commonwealth or the federal government or who become suspended or debarred by the Commonwealth or federal government during the term of this Contract or any extensions or renewals thereof, the Keystone Communities Grant Program or OWNER shall have the right to require CONTRACTOR to terminate such subcontracts or employment.
Article 25.  RECORDS
OWNER and CONTRACTOR at their respective principal offices or places of business, shall maintain, using accepted procedures, complete and accurate records and accounts including documents, correspondence, and other evidence pertaining to costs, and expenses of this Contract, reflecting all matters and activities covered by this Contract. At any time during normal business hours and as often as the Commonwealth of Pennsylvania and/or ORA deems necessary, CONTRACTOR shall make available for inspection by the Commonwealth of Pennsylvania, ORA, or its duly authorized representatives, all of its records with respect to all matters covered by this Contract and will permit the Commonwealth of Pennsylvania and/or ORA to audit, examine and make copies of such records.
All required records shall be maintained by CONTRACTOR for a period of three (3) years from the date of final payment or audit, if required, except in those cases where unresolved audit questions may require maintaining some or all records for a longer period, in which event the records shall be maintained until all pending matters are resolved.
Article 26.  DUPLICATE ORIGINALS
26.1	Four (4) duplicate original copies of the Agreement and all other Contract Documents shall be signed by the Owner and Contractor for the execution of this contract.

SIGNATURES BY AUTHORIZED AGENTS
IN WITNESS WHEREOF, the parties hereto have signed four (4) copies of this Agreement. One duplicate original has been delivered to CONTRACTOR and CONSULTANT, and two duplicate originals have been delivered to OWNER. All portions of the Contract Documents have been signed or identified by OWNER and CONTRACTOR.
This Agreement will be effective on ____________________, 20____.

	OWNER:
Oil Region Alliance
217 Elm Street
Oil City, PA 16301
	CONTRACTOR:
______________________________
______________________________
______________________________

	
______________________________
President
	
______________________________
President

	
______________________________
Chair of Board
	

	
______________________________
Date Signed

(CORPORATE SEAL)
	
______________________________
Date Signed

(CORPORATE SEAL)
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AGREEMENT	AF - 1
PERFORMANCE BOND
KNOW ALL MEN BY THESE PRESENTS:

That We, ________________________________________ as Principal, and ________________________________________ a corporation organized and existing under the laws of the State of ____________________ and authorized to do business in the Commonwealth of Pennsylvania, as Surety, are held and firmly bound unto the Oil Region Alliance, Venango County, Pennsylvania, as Obligee, in the full and just sum of ____________________________________________ ($________________), lawful money of the United States of America, for the payment of which sum, well and truly be made, we bind ourselves, our heirs, executors, administrators, successors and assigns, jointly and severally, firmly by these presents.
THE CONDITIONS OF THIS OBLIGATION are such that
WHEREAS, the Principal contemplates entering into a certain Contract with the Obligee for construction of Contract Demolition of the Fuchs Industrial Site Work pursuant to specifications and other related documents, constituting the Contract Documents, which are incorporated into the Agreement by reference, and
WHEREAS, this bond is given pursuant to the provisions of the Public Works Contractors' Bond Law of 1967, Act No. 385 of the 1967 General Assembly of the Commonwealth of Pennsylvania,
NOW, THEREFORE, if the Principal and Obligee shall enter into an Agreement with respect to performance of such work, and if the Principal shall well, truly and faithfully perform its duties, all the undertakings, covenants, terms, and conditions of the Agreement and the Contract Documents during the original term thereof, and any extensions thereof, then this obligation shall be void; otherwise to remain in full force and effect. The obligation of the Surety hereunder shall extend to all obligations of the Principal in connection with warranty and/or maintenance obligations of the Principal which survive the completion of the work.
If the principal is a foreign corporation (Incorporated under any laws other than those of the Commonwealth of Pennsylvania) then further terms and conditions of this Bond are and shall be that the Principal or the Surety shall not be discharged from liability on this Bond, nor this Bond surrendered until such Principal files with the Obligee a certificate from the Pennsylvania Department of Revenue evidencing the payment in full of all bonus taxes, penalties and interest, and a certificate from the Bureau of Employment and Unemployment Compensation of the Pennsylvania Department of Labor and Industry, evidencing the payment of all Unemployment Compensation, contributions, penalties and interest due the Commonwealth from said Principal or any foreign corporation, subcontractor thereunder or for which liability has accrued but the time for payment has not arrived, all in accordance with provisions of the Act of June 10, 1947, of the Commonwealth of Pennsylvania.
PROVIDED, FURTHER, that the said Surety, for value received hereby agrees that no change, extension of time, alteration or addition to the terms of the Contract or to the work to be performed thereunder or the specifications accompanying the same shall in any way affect the obligation of the Surety on this Bond, and the Surety does hereby waive notice of any such change, extension of time, alteration or addition to the terms of the Contract or to the work or to the specifications.
IN WITNESS WHEREOF, the Principal and Surety cause this instrument to be Signed, Sealed and Delivered this ________ day of ____________________, 20____.

	PRINCIPAL
	

	Attest:

______________________________
Secretary
	

By: ______________________________
(Principal)

	
______________________________
Witness as to Principal
	Address: ______________________________

(SEAL)

	SURETY
	

	Attest:

______________________________
Secretary
	

By: ______________________________
Attorney-in-Fact

	
______________________________
Witness as to Surety
	Address: ______________________________

(SEAL)



NOTES:
1.	Attach an appropriate Power of Attorney, dated as of the same date as the Bond, evidencing the authority of the Attorney-in-Fact to act on behalf of the corporation.
2.	If the Contractor is a Partnership, all partners shall execute the Bond.
3.	Surety companies executing bonds must appear on the U. S. Department of the Treasury most current Bond List (Circular 570 as amended). Bond amounts are subject to the underwriting limitation listed in the most recent Circular 570.
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PERFORMANCE BOND	PB - 1
PAYMENT BOND
KNOW ALL MEN BY THESE PRESENTS:

That We, ________________________________________ as Principal, and ________________________________________ a corporation organized and existing under the laws of the State of ____________________ and authorized to do business in the Commonwealth of Pennsylvania, as surety, are held and firmly bound unto the Oil Region Alliance, Venango County, Pennsylvania, as Obligee, in the full and just sum of ____________________________________________ ($________________) lawful money of the United States of America, for the payment of which sum, well and truly be made, we bind ourselves, our heirs, executors, administrators, successors and assigns, jointly and severally, firmly by these presents.
THE CONDITIONS OF THIS OBLIGATION are such that
WHEREAS, the Principal contemplates entering into a certain contract with the Obligee for construction of Contract Demolition of the Fuchs Industrial Site Work, pursuant to specifications and other related documents, constituting the Contract Documents, which are incorporated into the Agreement by reference, and
WHEREAS, this bond is given pursuant to the provisions of the Public Works Contractor's Bond Law of 1967, Act No. 385 of the 1967 General Assembly of the Commonwealth of Pennsylvania,
NOW, THEREFORE, if the Principal and Obligee shall enter an Agreement with respect to performance of such work, and if the Principal shall promptly make payment to all persons, firms, Subcontractors, associations, partnerships and corporations furnishing materials for or performing labor in prosecution of the work provided for in such Agreement and the Contract Documents during the term thereof, then this obligation shall be void; otherwise to remain in full force and effect.
The obligation of the Surety hereunder shall extend to all indebtedness incurred by the Principal in connection with warranty and/or maintenance obligations of the Principal which survive the completion of the work.
If the Principal is a foreign corporation (incorporated under any laws other than those of the Commonwealth of Pennsylvania) then further terms and conditions of this Bond are and shall be that the Principal or the Surety shall not be discharged from liability on this Bond, nor this Bond surrendered until such Principal files with the Obligee a certificate from the Pennsylvania Department of Revenue evidencing the payment in full of all bonus taxes, penalties and interest, and a certificate from the Bureau of Employment and Unemployment Compensation of the Pennsylvania Department of Labor and Industry, evidencing the payment of all Unemployment Compensation, contributions, penalties and interest due the Commonwealth from said Principal or any foreign corporation, subcontractor thereunder or for which liability has accrued but the time for payment has not arrived, all in accordance with provisions of the Act of June 10, 1947, of the Commonwealth of Pennsylvania.
PROVIDED, FURTHER, that the said Surety, for value received hereby agrees that no change, extension of time, alteration or addition to the terms of the Contract or to the work to be performed thereunder or the specifications accompanying the same shall in any way affect the obligation of the Surety on this Bond, and the Surety does hereby waive notice of any such change, extension of time, alteration or addition to the terms of the Contract or to the work or to the specifications.
IN WITNESS WHEREOF, the Principal and Surety cause this instrument to be Signed, Sealed and Delivered this ________ day of ____________________, 20____.

	PRINCIPAL
	

	Attest:

______________________________
Secretary
	

By: ______________________________
(Principal)

	
______________________________
Witness as to Principal
	Address: ______________________________

(SEAL)

	SURETY
	

	Attest:

______________________________
Secretary
	

By: ______________________________
Attorney-in-Fact

	
______________________________
Witness as to Surety
	Address: ______________________________

(SEAL)



NOTES:
1.	Attach an appropriate Power of Attorney, dated as of the same date as the Bond, evidencing the authority of the Attorney-in-Fact to act on behalf of the corporation.
2.	If the Contractor is a Partnership, all partners shall execute the Bond.
3.	Surety companies executing bonds must appear on the U. S. Department of the Treasury most current Bond List (Circular 570 as amended). Bond amounts are subject to the underwriting limitation listed in the most recent Circular 570.
Demolition of the Fuchs Industrial Site	Project ISRP26
105 8th Street, Emlenton, PA 16373	October 2026

PAYMENT BOND	PAB - 1
2.4.1  GENERAL CONDITIONS

ARTICLE 1 - DEFINITIONS
Wherever used in these General Conditions or in the other Contract Documents, the following terms shall have the meanings indicated which shall be applicable to both the singular and plural thereof:
Addenda - Written or graphic instruments issued prior to the opening of Bids which clarify, correct or change the bidding documents or the Contract Documents.
Agreement - The written agreement between OWNER and CONTRACTOR covering the Work to be performed. The Contract Documents will be attached to and made a part of the Agreement.
Application for Payment - The form accepted by Consultant which is to be used by CONTRACTOR in requesting payment.
Bid - The offer or proposal of the Bidder submitted on the prescribed form setting forth the prices for the Work to be performed.
Bidder - Any person, firm or corporation submitting a Bid for the Work.
Bonds - Bid, Performance, and Payment Bonds and other instruments of security, furnished by CONTRACTOR and his Surety in accordance with the Contract Documents.
Change Order - A written order to CONTRACTOR signed by OWNER authorizing an addition, deletion or revision in the Work, or an adjustment in the Contract Price or the Contract Time issued after the Effective Date of the Agreement.
Contract Documents - The Agreement, Addenda (which pertain to the Contract Documents), CONTRACTOR'S Bid (including documentation accompanying the Bid and any post-Bid documentation submitted prior to the Notice of Award) when attached as an exhibit to the Agreement, the Bonds, these General Conditions, any Supplementary Conditions, the Specifications, the Drawings as the same are more specifically identified in the Agreement, together with all Modifications issued after the execution of the Agreement.
Contract Price - The total moneys payable by OWNER to CONTRACTOR under the Contract Documents as stated in the Agreement.
Contract Time - The number of consecutive calendar days or the date stated in the Agreement for the completion of Work.
CONTRACTOR - The person, firm, or corporation with whom OWNER has entered into the Agreement.
Defective - An adjective which when modifying the word Work refers to Work that is unsatisfactory, faulty or deficient, or does not conform to the Contract Documents or does not meet the requirements of any inspection, test or approval referred to in the Contract Documents.
Drawings - The drawings which show the character and scope of the Work to be performed and which have been prepared or approved by Consultant and are referred to in the Contract Documents.
Effective Date of the Agreement - The date on which the Agreement becomes fully executed by both CONTRACTOR and OWNER.
CONSULTANT - The Owner’s Consultant or any other person, firm or corporation employed by the Owner for the purpose of directing or having charge of any Work embraced in the Contract Documents. For this project, the CONSULTANT is Moody and Associates, Inc.
Field Order - A written order issued by Consultant which clarifies or interprets the Contract Documents in accordance with Paragraph 9.3 or orders minor changes in the Work in accordance with Paragraph 10.2.
Modification - (a) A written amendment of the Contract Documents signed by both parties; (b) a Change Order; or (c) a Field Order. A modification may only be issued after the Effective Date of the Agreement.
Notice of Award - The written notice by OWNER to the lowest responsible Bidder stating that upon compliance by the lowest responsible Bidder with the conditions precedent enumerated therein, within the time specified, OWNER may deliver the Agreement to him for execution.
Notice to Proceed - A written notice given by OWNER to CONTRACTOR fixing the date on which the Contract Time will commence to run and on which CONTRACTOR shall start to perform his obligation under the Contract Documents.
OWNER - The Oil Region Alliance of Business, Industry & Tourism (ORA).
Project - The total construction of which the Work to be provided under the Contract Documents may be the whole, or a part, as indicated elsewhere in the Contract Documents.
Shop Drawings - All drawings, diagrams, illustrations, brochures, schedules, and other data which are prepared by CONTRACTOR, a Subcontractor, manufacturer, supplier, or distributor to illustrate the equipment, material or some portion of the Work.
Specifications - Those portions of the Contract Documents consisting of written technical descriptions of materials, equipment, construction systems, standards and workmanship as applied to the Work and certain administrative details applicable thereto.
Subcontractor - An individual, firm or corporation having a direct contract with CONTRACTOR or with any other Subcontractor for the performance of a part of the Work at the site.
Substantial Completion - The date as certified by Consultant when the construction of the Project or a specified part thereof is sufficiently completed, in accordance with the Contract Documents, so that the Project or specified part can be utilized for the purposes for which it was intended, or if there be no such certification, the date when payment is due in accordance with paragraph 14.1.
Work - Any and all obligations, duties and responsibilities necessary to the successful completion of the project assigned to or undertaken by CONTRACTOR under the Contract Documents, including the furnishing of all labor, materials, equipment, and other incidentals.
ARTICLE 2 - PRELIMINARY MATTERS
Award:
2.1	The award of the Contract, if it is awarded, will be to the lowest responsible bidder whose qualifications indicate the award will be in the best interest of OWNER and whose proposal complies with all the prescribed requirements. No Notice of Award will be given until OWNER has concluded such investigations as he deems necessary to establish the responsibility, qualifications and financial ability of the Bidders to do the Work in accordance with the Contract Documents to the satisfaction of OWNER within the time prescribed. OWNER reserves the right to reject the Bid of any Bidder who does not pass such investigation to OWNER'S satisfaction.
In analyzing Bids, OWNER may take into consideration alternates and unit prices, if requested by the Bid Forms. If the Contract is awarded, OWNER will give the lowest responsible Bidder a Notice of Award within the time indicated in the Instructions to Bidders.
Execution of Agreement:
2.2	At least four (4) duplicate copies of the Agreement and such other Contract Documents as practicable shall be signed by CONTRACTOR within ten days of the Notice of Award, after which OWNER will sign. Consultant will identify those portions of the Contract Documents not so signed and such identification will be binding on all parties. OWNER, CONTRACTOR and CONSULTANT will each receive an executed duplicate original copy of the Contract Documents.
Delivery of Bonds and Certificates of Insurance:
2.3	The lowest responsible Bidder so designated shall furnish to OWNER (by delivery to CONSULTANT) within ten days after the date of Notice of Award, the required Payment and Performance Bonds and Certificates of Insurance. Failure of the lowest responsible Bidder to deliver the Bonds and Certificates of Insurance within the prescribed period shall be just cause for OWNER to annul the Notice of Award and declare the Bid and any Security therefore forfeited. OWNER may, in its sole discretion, award the Contract to said Bidder, following receipt of said properly executed Bonds and Certificates.
Forfeiture of Bid Security:
2.4	Failure of the lowest responsible Bidder to execute and deliver the Agreement within ten days of the Notice of Award shall be just cause for OWNER to annul the Notice of Award and declare the Bid and any Security therefore forfeited.
Copies of Documents:
2.5	OWNER will furnish to CONTRACTOR up to two (2) sets of the Specifications as are reasonably necessary for the execution of the Work. Additional copies will be furnished, upon request, at the cost of reproduction.
Before Starting Work:
2.6	Before starting the Work, a conference will be held to establish procedures for processing applications for payment, and to establish a working understanding between the parties as to the Project. Present at the conference will be CONSULTANT and other OWNER representatives, and CONTRACTOR'S Superintendent.
2.7	Before undertaking the Work, CONTRACTOR will carefully study and compare the Contract Documents and check and verify all figures shown thereon and all field measurements. He will at once report in writing to CONSULTANT any conflict, error or discrepancy which he may discover. CONTRACTOR assumes full responsibility for having familiarized himself with the nature and extent of the Contract Documents, Work, locality, and local conditions that may in any manner affect the Work to be done.
Commencement of Contract Time; Notice to Proceed:
2.8	The Contract Time, if any, will commence to run on the day indicated in the Notice to Proceed. A Notice to Proceed may be given any time after the Effective Date of the Agreement.
Qualifications of Subcontractors, Materialmen and Suppliers:
2.9	Within ten days after the opening of Bids, the lowest responsible Bidder will submit to CONSULTANT for acceptance a list of the names of Subcontractors and such other persons and organizations (including those who are to furnish principal items of materials or equipment) proposed for those portions of the Work as to which the identity of the Subcontractors and other persons and organizations must be submitted as specified in the Contract Documents. Prior to the Notice to Proceed, the lowest responsible Bidder will be notified in writing if, after due investigation, OWNER has reasonable objection to any Subcontractor, person or organization on such list. The failure of OWNER to make objection to any Subcontractor, person or organization on the list prior to the Notice to Proceed shall constitute an acceptance of such Subcontractor, person or organization. Acceptance of any such Subcontractor, person or organization shall not constitute a waiver of any right of OWNER or CONSULTANT to reject defective Work, material or equipment, or Work, material or equipment not in conformance with the requirements of the Contract Documents.
2.10	If, prior to the Notice to Proceed, OWNER or CONSULTANT has reasonable objection to and refuses to accept any Subcontractor, person or organization on such list, the lowest responsible Bidder may, prior to Notice to Proceed either: (a) submit an acceptable substitute without an increase in his Bid Price; or (b) withdraw his Bid and forfeit his Bid Security. If, after the Notice to Proceed OWNER or CONSULTANT refuses to accept any Subcontractor, person or organization on such list, CONTRACTOR will submit an acceptable substitute and the Contract Price shall be increased or decreased by the difference in cost occasioned by such substitution and an appropriate Change Order shall be issued.
Starting the Work:
2.11	CONTRACTOR will start the Work in accordance with the requirements of the Notice to Proceed.
ARTICLE 3 - CONTRACT DOCUMENTS
3.1	It is the intent of the Specifications and Drawings to describe a complete Project to be constructed in accordance with the Contract Documents. The Contract Documents comprise the entire Agreement between OWNER and CONTRACTOR. They may be altered only by a Modification.
3.2	The Contract Documents are complementary; what is called for by one is as binding as if called for by all. If CONTRACTOR finds a conflict, error or discrepancy in the Contract Documents, he shall report it to CONSULTANT in writing at once and before proceeding with the Work affected thereby. In resolving such conflicts, errors and discrepancies, the Documents shall be given precedence in the following order: the Agreement, Addenda, Supplementary Conditions, these General Conditions, the Specifications, and the Drawings. Figure dimensions in drawings shall govern over general drawings. Any Work that may reasonably be inferred from the Specifications or Drawings as being required to produce the intended result shall be supplied whether or not it is specifically called for. Work, materials or equipment described in words which so applied have a well-known technical or trade meaning shall be deemed to refer to such recognized standards. Reference to standard specifications, manuals or codes of any technical society, organization or association, or to the code of any governmental authority, whether such reference be specific or by implication, shall mean the latest standard specification, manual or code in effect at the time of opening Bids.
3.3	Each and every provision of law and clause required by law to be inserted in these Contract Documents shall be deemed to be inserted herein, and the Contract Documents shall be read and enforced as though it were included herein. If through mistake or otherwise, any such provision is not inserted, or is not correctly inserted, then, upon the application of either party, the Contract Documents shall forthwith be altered to make such insertion.
3.4	The Contract Documents shall be governed by the laws of the Emlenton, County of Venango, State of Pennsylvania and the United States of America.
ARTICLE 4 - AVAILABILITY OF LANDS, PHYSICAL CONDITIONS, REFERENCE POINTS
4.1	OWNER will provide, as indicated in the Contract Documents, the lands upon which the Work is to be performed, rights-of-way for access thereto, and such other lands which are designated for the use of CONTRACTOR. CONTRACTOR will provide all additional lands and access thereto that may be required for temporary construction facilities or storage of materials and equipment. CONTRACTOR shall not utilize any lands, other than those provided by OWNER, unless and until he shall place on file with OWNER a written agreement, executed by the property owner and CONTRACTOR, which shall clearly state the terms and conditions under which CONTRACTOR has obtained permission or right to such use. Filing of such agreement with OWNER shall not effect or imply enforcement of agreement terms and conditions by OWNER.
ARTICLE 5 - BONDS AND INSURANCE
Performance and Payment Bonds:
5.1	CONTRACTOR shall furnish Performance and Payment Bonds, each in an amount at least equal to the Contract Price as security for the faithful performance and payment of all CONTRACTOR'S obligations under the Contract Documents and any other bonds required. These Bonds shall remain in effect at least until one (1) year after the date of final payment, except as otherwise provided by law. All bonds shall be in the forms prescribed by the bidding documents and be executed by such sureties as (i) are licensed to conduct business in the Commonwealth of Pennsylvania, and (ii) are named in the current list of "Companies Holding Certificates of Authority as Acceptable Sureties on Federal Bonds and as Acceptable Reinsuring Companies" as published in Circular 570 (amended) by the Audit Staff Bureau of Accounts, United States Treasury Department. All bonds signed by an agent must be accompanied by a certified copy of the authority to act.
5.2	If the surety on any bond furnished by CONTRACTOR is declared bankrupt or becomes insolvent or its right to do business is terminated in the Commonwealth of Pennsylvania or it ceases to meet the requirements of clauses (i) and (ii) of Paragraph 5.1, CONTRACTOR shall within five (5) days thereafter substitute another bond and surety, both of which shall be acceptable to OWNER.
Comprehensive General Liability Insurance:
5.3	CONTRACTOR shall purchase and maintain during the life of this Contract such Comprehensive General Liability Insurance including product and completed operations liability insurance as will provide protection from CONTRACTOR'S performance of the Work and CONTRACTOR'S other obligations under the Contract Documents, whether such performance is by CONTRACTOR, by any Subcontractor, by anyone directly or indirectly employed by any of them, or by anyone for whose acts any of them may be liable. This coverage shall include:
5.3.1	Bodily Injury (including Personal Injury)
$  500,000 each person
$1,000,000 each occurrence
5.3.2	Property Damage (including loss of use)
$  300,000 each occurrence
5.3.3	Products and Completed Operations Coverage - same limits as General Liability for two (2) years after final acceptance
5.3.4	Contractual Liability Coverage - same limits as General Liability expressly extended to include indemnification of OWNER
5.3.5	Independent Contractor's Coverage - same limits as General Liability
5.3.6	Broad Form Property Damage Coverage (including Completed Operations) - same limits as Property Damage under General Liability
All such coverages shall provide for the elimination of the XCU exclusion on all contractor operations.
Comprehensive Automobile Liability Insurance:
5.4	CONTRACTOR shall purchase and maintain during the life of this Contract such Comprehensive Automobile Liability Insurance including Employer's Non-ownership Liability and Hired Car Liability Insurance to protect him and any Subcontractors performing Work covered by this Contract from claims for damages, whether such operations be by him or any Subcontractor or by anyone directly or indirectly employed by any of them, or by anyone for whose acts any of them may be liable. This coverage shall include:
5.4.1	Bodily Injury - $ 500,000 each person
$1,000,000 each occurrence
5.4.2	Property Damage - $ 300,000 each occurrence
Worker's Compensation Insurance:
5.5	CONTRACTOR shall purchase and maintain during the life of this Contract standard Worker's Compensation Insurance including employers liability coverage (Coverage B) with limits of at least $100,000 or as required by law, whichever is greater. A Broad Form All States Endorsement shall be attached.
Owner's Protective Liability Insurance:
5.6	CONTRACTOR shall purchase and furnish to OWNER and maintain during the life of this Contract, Owner's Protective Liability Insurance including Full XCU Coverage in amounts specified in Paragraphs 5.3.1 and 5.3.2 covering personal injury and property damage.
CONSULTANT shall be named as additional insured. 
Special Insurance:
5.7	CONTRACTOR shall purchase and furnish to OWNER, and maintain during the life of this Contract, "Umbrella" Excess Third Party Liability Insurance with limits of no less than $1,000,000 and providing excess insurance on the coverages specified in Paragraphs 5.3 through 5.6, and excess over $10,000 on any uninsured peril.
Insurance Certificates and Policies:
5.8	CONTRACTOR shall file with the OWNER as hereinbefore required, satisfactory proof of acceptable insurance coverage. Such proof shall, unless otherwise required by the OWNER, consist of the following:
5.8.1	Two copies, complete of all insurance policies. Which copies shall be clear, readable reproductions, but must be the entire policy including endorsements, exceptions, riders, qualifications and restrictions, exactly as maintained in the records of the insured.
5.8.2	Certificates of insurance on the insurance carrier's standard form indicating all policies required by law and the Contract Documents. Certificates of insurance shall be furnished in a number of copies equal to the number of counterparts of the Contract Documents executed. Each certificate shall carry the provision that the policy may not be canceled or materially changed except upon fifteen days notice to OWNER and CONSULTANT. All insurance shall be kept in force throughout the entire construction period and remain in effect for thirty (30) days after the date that the entire project is determined to be complete in accordance with paragraph 14.1.
ARTICLE 6 - CONTRACTOR'S RESPONSIBILITIES
Supervision and Superintendence:
6.1	CONTRACTOR shall supervise and direct the Work competently and efficiently, devoting such attention thereto and applying such skills and expertise as may be necessary to perform the Work in accordance with the Contract Documents. He shall be solely responsible for the means, methods, techniques, sequences and procedures of construction. CONTRACTOR shall be responsible to see that the finished Work complies accurately with the Contract Documents.
6.2	CONTRACTOR shall keep on the Work at all times during its progress a competent resident Superintendent, who shall not be replaced without written notice to OWNER and CONSULTANT except under extraordinary circumstances. The Superintendent will be CONTRACTOR'S representative at the site and shall have authority to act on behalf of CONTRACTOR. All communications given to the Superintendent shall be as binding as if given to CONTRACTOR.
Labor, Materials and Equipment:
6.3	CONTRACTOR shall provide competent, suitably qualified personnel to survey and lay out the Work and perform construction as required by the Contract Documents. He shall at all times maintain good discipline and order at the site.
6.4	CONTRACTOR shall furnish all materials, equipment, labor, transportation, construction equipment and machinery, tools, appliances, fuel, power, light, heat, telephone, water and sanitary facilities, and all other facilities and incidentals necessary for the execution, testing, initial operation, and completion of the Work.
6.5	All materials and equipment shall be of good quality and new, except as otherwise provided in the Contract Documents. If required by CONSULTANT, CONTRACTOR will furnish satisfactory evidence as to the kind and quality of materials and equipment. All materials and equipment shall be stored, stockpiled, applied, installed, connected, erected, used, cleaned and conditioned in accordance with the instructions of the applicable manufacturer, fabricator, supplier or distributor, except as otherwise provided in the Contract Documents.
6.6	CONTRACTOR shall, at his own cost and expense, erect and maintain all necessary signs, lights, and barricades as ordered by CONSULTANT; however, this does in no way impose on CONSULTANT any responsibility for project safety.
Substitute Materials and Equipment:
6.7	If it is indicated in the Contract Documents that CONTRACTOR may furnish or use a substitute that is equal to any material or equipment specified, and if CONTRACTOR wishes to furnish or use a proposed substitute, he will, promptly after the execution of the Contract, make written application to CONSULTANT for approval of such a substitute certifying in writing that the proposed substitute will perform adequately the duties imposed by the general design, be similar and of equal substance to that specified and be suited to the same use and capable of performing the same function as that specified. In his written application, CONTRACTOR shall call attention to any differences or nonconformities with the item specified. No substitute shall be ordered or installed without the written approval of CONSULTANT, who shall be the judge of equality.
Concerning Subcontractors:
6.8	CONTRACTOR shall not employ any Subcontractor, or other person or organization, whether initially or as a substitute, against whom OWNER or CONSULTANT may have reasonable objection, nor will CONTRACTOR be required to employ any Subcontractor against whom he has reasonable objection. CONTRACTOR will not make any substitution for any Subcontractor who has been accepted by OWNER and CONSULTANT, unless CONSULTANT determines that there is good cause for doing so.
6.9	CONTRACTOR shall be fully responsible for all acts and omissions of his Subcontractors and of persons directly or indirectly employed by them and of persons and organizations for whose acts any of them may be liable to the same extent that he is responsible for the acts and omissions of persons directly employed by him. Nothing in the Contract Documents shall create any contractual relationship between OWNER or CONSULTANT and any Subcontractor or other person or organization having a direct contract with CONTRACTOR, nor shall it create any obligation on the part of OWNER or CONSULTANT to pay or to see to the payment of any moneys due any Subcontractor, or other person or organization, except as may otherwise be required by law. OWNER or CONSULTANT may furnish to any Subcontractor, or other person or organization, to the extent practicable, evidence of amounts paid to CONTRACTOR on account of specific Work done.
6.10	The divisions and sections of the Specifications and the identifications of any Drawings shall not control CONTRACTOR in dividing the Work among Subcontractors or delineating the Work to be performed by any specific trade.
6.11	All Work performed for CONTRACTOR by a Subcontractor shall be pursuant to an appropriate agreement between CONTRACTOR and the Subcontractor.
6.12	CONTRACTOR agrees to bind specifically every Subcontractor to the applicable terms and conditions of the Contract Documents for the benefit of OWNER and CONSULTANT. Every Subcontractor by undertaking to perform any of the Work, will thereby be deemed to be bound by such terms and conditions.
Patent Fees and Royalties:
6.13	CONTRACTOR shall pay all license fees and royalties and assume all costs incident to the use of any invention, design, process, product or device which is the subject of patent rights or copyrights held by others. He will indemnify and hold harmless the OWNER and anyone directly or indirectly employed by the OWNER from and against all claims, damages, losses and expenses (including attorneys fees) arising out of any infringement of such rights during or after completion of the Work, and shall defend all such claims in connection with any alleged infringement of such rights.
Permits:
6.14	CONTRACTOR shall obtain and pay for all construction permits and licenses and shall pay all governmental charges and inspection fees necessary for the prosecution of the Work, which are applicable at the time of opening Bids. He shall also pay all public utility charges.
Laws and Regulations:
6.15	CONTRACTOR shall give all notices and comply with all laws, ordinances, rules and regulations applicable to the Work. If CONTRACTOR observes that the Specifications or Drawings are at variance therewith, he shall give CONSULTANT prompt written notice thereof, and any necessary changes shall be adjusted by an appropriate Modification. If CONTRACTOR performs any Work knowing or having reason to know that it is contrary to such laws, ordinances, rules and regulations, and without such notice to CONSULTANT, he shall bear all costs arising therefrom. However, it shall not be his primary responsibility to make certain that the Drawings and Specifications are in accordance with such laws, ordinances, rules and regulations.
Taxes:
6.16	CONTRACTOR shall pay all sales, consumer, use and other similar taxes required by the law of the place where the Work is to be performed.
Use of Premises:
6.17	CONTRACTOR shall confine his equipment, the storage of materials and equipment and the operations of his workmen to areas permitted by law, ordinances, permits, or the requirements of the Contract Documents; and shall not unreasonably encumber the premises with materials or equipment.  CONTRACTOR shall maintain reasonable access to properties affected by construction operations.
Cleaning Up:
6.18	CONTRACTOR shall continuously keep the Work, the site and adjacent properties free from accumulations of waste materials, rubbish and windblown debris caused by his operations. He shall remove waste materials, debris and rubbish from the site periodically and dispose of at legal disposal areas away from the site. Areas disturbed by construction shall be restored.
At the completion of the Work, or each major portion thereof, CONTRACTOR shall remove surplus materials, tools, construction equipment and machinery and leave the site clean.
6.19	CONTRACTOR shall not subject any part of the Work or adjacent property to stresses or pressures that will endanger it.
Record Documents:
6.20	CONTRACTOR shall keep one record copy of all Specifications, Drawings, Addenda, Modifications, Submittals, and samples at the site in good order and annotated to show all changes made during the construction process. These shall be available to CONSULTANT for examination and shall be delivered to her upon completion of the Project.
Safety and Protection:
6.21	CONTRACTOR shall be responsible for initiating, maintaining and supervising all safety precautions and programs in connection with the Work. He shall take all necessary precautions for the safety of, and shall provide the necessary protection to prevent damage, injury or loss to:
6.21.1	All employees on the Work and other persons who may be affected thereby.
6.21.2	All the Work and all materials or equipment to be incorporated therein, whether in storage on or off the site;
6.21.3	Other property at the site or adjacent thereto, including trees, shrubs, lawns, walks, pavements, roadways, structures, utilities and underground facilities not designated for removal, relocation or replacement in the course of construction.
6.22	CONTRACTOR shall have exclusive responsibility for the initiation and execution of measures necessary for the protection of persons and property and shall have exclusive responsibility for the means, methods, construction procedures, sequence of operations and every other aspect of the conduct of the Work. Nothing in the Contract Documents shall be construed as imposing upon OWNER or CONSULTANT any responsibility for project safety.
6.23	CONTRACTOR shall comply with all applicable laws, ordinances, rules, regulations and orders of any public body having jurisdiction for the safety of persons or property or to protect them from damage, injury or loss. He shall erect and maintain, as required by the conditions and progress of the Work, all necessary safeguards for safety and protection. CONTRACTOR shall notify owners of adjacent property and of underground facilities and utility owners when prosecution of the Work may affect them. All damage, injury or loss to any property referred to in Paragraph 6.21.2 or 6.21.3 caused, directly or indirectly, in whole or in part, by CONTRACTOR, any Subcontractor or anyone directly or indirectly employed by any of them or anyone for whose acts any of them may be liable, shall be remedied by CONTRACTOR. CONTRACTOR'S duties and responsibilities for the safety and protection of the Work shall continue until such time as all Work is completed and CONSULTANT has indicated to OWNER and CONTRACTOR that the Work is acceptable.
6.24	CONTRACTOR shall designate a responsible representative at the site whose duty shall be the prevention of accidents. This person shall be CONTRACTOR'S superintendent unless otherwise designated in writing by CONTRACTOR to OWNER.
Emergencies:
6.25	In emergencies affecting the safety or protection of persons or the Work or property at the site or adjacent thereto, CONTRACTOR, without special instruction or authorization from CONSULTANT or OWNER, is obligated to act, at his discretion, to prevent threatened damage, injury or loss. CONTRACTOR shall give CONSULTANT prompt written notice of any significant changes in the Work or deviations from the Contract Documents caused thereby, and a Change Order shall thereupon be issued covering the changes and deviations involved. If CONTRACTOR believes that additional Work done by him in an emergency which arose from causes beyond his control entitles him to an increase in the Contract Price or an extension of the Contract Time, he may make a claim therefore as provided in Articles 11 and 12.
Submittals:
6.26	CONTRACTOR shall make submittals as specified in the Technical Specifications and in Article 2 of these General Conditions.
6.27	CONSULTANT will review and approve with reasonable promptness all submittals, but her review and approval shall be only for conformance with the design concept of the Project and for compliance with the Contract Documents and shall not extend to means, methods, sequences, techniques or procedures of construction, or to safety precautions or programs incident thereto. CONTRACTOR shall make any corrections required by CONSULTANT and shall return the corrected submittal until approved. CONTRACTOR shall direct specific attention in writing or on resubmittals, revisions other than the corrections called for by CONSULTANT on previous submissions. CONTRACTOR'S stamp of approval on any submittal shall constitute a representation to OWNER and CONSULTANT that CONTRACTOR has either determined and verified all field construction criteria, materials, and similar data or he assumes full responsibility for doing so.
6.28	No Work shall be commenced until the required submittals have been approved by CONSULTANT.
Indemnification:
6.29	To the fullest extent permitted by law, CONTRACTOR shall indemnify and hold harmless OWNER, its agents and employees, including CONSULTANT, from and against all claims, damages, losses and expenses, including but not limited to attorney's fees, arising out of or resulting from the performance of the Work, provided that any such claim, damage, loss or expense (a) is attributable to bodily injury, sickness, disease or death, or to injury to or destruction of tangible property (other than the Work itself) including the loss of use resulting therefrom, and (b) is caused in whole or in part by any negligent act or omission of CONTRACTOR, any Subcontractor, anyone directly or indirectly employed by any of them or anyone for whose acts any of them may be liable, regardless of whether or not it is caused in part by a party indemnified hereunder.
6.30	In any and all claims against OWNER or any of its agents or employees, including CONSULTANT, by any employee of CONTRACTOR, any Subcontractor, anyone directly or indirectly employed by any of them or anyone for whose acts any of them may be liable, the indemnification obligation under paragraph 6.29 shall not be limited in any way by any limitation on the amount or type of damages, compensation or benefits payable by or for CONTRACTOR or any Subcontractor under worker's compensation acts, disability benefit acts or other employee benefit acts.
6.31	The obligations of CONTRACTOR under paragraph 6.29 shall not extend to the liability of OWNER or CONSULTANT arising out of (a) the preparation or approval of maps, drawings, opinions, reports, surveys, Change Orders, designs or specifications or (b) the giving of or the failure to give directions or instructions, provided such giving or failure to give is the primary cause of injury or damage.
ARTICLE 7 - WORK BY OTHERS
7.1	OWNER may perform additional work related to the project by himself, or have additional work performed by utility service companies, or let other direct contracts therefor which shall contain General Conditions similar to these. CONTRACTOR shall afford the utility service companies and the other contractors who are parties to such direct contracts (or OWNER, if OWNER is performing the additional work himself), reasonable opportunity for the introduction and storage of materials and equipment and the execution of work, and shall properly connect and coordinate his Work with theirs.
7.2	If any part of CONTRACTOR'S Work depends for proper execution or results upon the work of any such other Contractor or utility service company (or OWNER), CONTRACTOR shall inspect and promptly report to CONSULTANT in writing any defects or deficiencies in such work that render it unsuitable for such proper execution and results. His failure so to report shall constitute an acceptance of the other work as fit and proper for integration with his Work except as to defects and deficiencies which may appear in the other work after the execution of his Work.
7.3	CONTRACTOR shall do all cutting, fitting and patching of his Work that may be required to make its several parts come together properly and integrate with such other work. CONTRACTOR shall not endanger any work of others by cutting, excavating or otherwise altering their work and will only cut or alter their work with the written consent of CONSULTANT and the others whose work will be affected.
7.4	If the performance of additional work by other contractors or utility service companies or OWNER is not noted in the Contract Documents prior to the execution of the Contract, written notice thereof shall be given to CONTRACTOR prior to starting any such additional Work. If CONTRACTOR believes that the performance of such additional work by OWNER or others involves him in additional expense or entitles him to an extension of the Contract Time, he may make a claim therefor as provided in Articles 11 and 12.
ARTICLE 8 - OWNER'S RESPONSIBILITIES
8.1	OWNER will issue all communications to CONTRACTOR through CONSULTANT.
8.2	OWNER will furnish the data required of OWNER under the Contract Documents promptly and shall make payments to CONTRACTOR promptly after they are due as provided in Paragraph 14.2.
8.3	OWNER'S duties in respect of providing lands and easements are set forth in Paragraph 4.1.
8.4	In addition to his rights to request changes in the Work in accordance with Article 10, OWNER will be obligated to execute Change Orders.
8.5	In connection with OWNER'S right to stop Work or suspend Work, see Paragraphs 13.5 and 15.1. Paragraph 15.2 deals with OWNER'S right to terminate services of CONTRACTOR under certain circumstances.
ARTICLE 9 - CONSULTANT'S STATUS DURING CONSTRUCTION
Owner's Representative:
9.1	The CONSULTANT, as an employee of OWNER, shall be OWNER'S representative during the construction period. The duties and responsibilities of CONSULTANT as OWNER'S representative during construction are set forth in Articles 1 through 19 of these General Conditions.
Visits to Site:
9.2	CONSULTANT will make periodic visits to the site to observe the progress and quality of the executed Work and to determine, in general, if the Work is proceeding in accordance with the Contract Documents. CONSULTANT will not be required to make exhaustive or continuous on-site inspections to check the quality or quantity of the Work. Her efforts will be directed toward providing assurance for OWNER that the completed Project will conform to the requirements of the Contract Documents. On the basis of such on-site observations, she will keep OWNER informed of the progress of the Work and will endeavor to guard OWNER against defects and deficiencies in the Work.
Clarifications and Interpretations:
9.3	CONSULTANT will issue with reasonable promptness such written clarifications or interpretations of the Contract Documents (in the form of drawings or otherwise) as she may determine necessary, which shall be consistent with or reasonably inferable from the overall intent of the Contract Documents. If CONTRACTOR believes that a written clarification or interpretation entitles him to an increase in the Contract Price, or the Contract Time, he may make a claim therefore as provided in Article 11 or 12.
Rejecting Defective Work:
9.4	CONSULTANT will have authority to disapprove or reject Work which is defective, and will also have authority to require special inspection or testing of the Work as provided in Article 13, whether or not the Work is fabricated, installed or completed.
Submittals and Payments:
9.5	In connection with CONSULTANT'S responsibility for Submittals, see paragraphs 6.27 and 6.28.
9.6	In connection with CONSULTANT'S responsibility for Change Orders, see Articles 10, 11, and 12.
9.7	In connection with CONSULTANT'S responsibilities in respect of applications for payment, etc., see Article 14.
Project Representation:
9.8	A full-time Resident Project Representative of CONSULTANT may be furnished on this Project. The duties, responsibilities, and limitations of authority of a Resident Project Representative of CONSULTANT will be the same as for CONSULTANT.
Decisions on Disagreements:
9.9	CONSULTANT will be the initial interpreter of the terms and conditions of the Contract Documents and judge of the acceptability of the Work thereunder. Claims, disputes and other matters relating to the execution and progress of the Work or the interpretation of or performance under the Contract Documents shall be referred initially to CONSULTANT for decision, which she shall render in writing within a reasonable time. CONSULTANT will not be liable in connection with any interpretation or decision rendered in good faith.
Limitations on Engineer's Responsibilities:
9.10	Neither CONSULTANT’S authority to act under this Article 9 or elsewhere in the Contract Documents nor any decision made by CONSULTANT in good faith either to exercise or not exercise such authority shall give rise to any duty or responsibility of CONSULTANT to CONTRACTOR, any Subcontractor, any manufacturer, fabricator, supplier or distributor, any of their agents or employees or any other person performing any of the Work.
9.11	Whenever in the Contract Documents the terms "as ordered", "as directed", "as required", "as allowed" or terms of like effect or import are used, or the adjectives "reasonable", "suitable", "acceptable", "proper" or "satisfactory" or adjectives of like effect or import are used, to describe requirement, direction, review or judgment of CONSULTANT as to the Work, it is intended that such requirement, direction, review or judgment will be solely to evaluate the Work for compliance with the Contract Documents (unless there is a specific statement indicating otherwise). The use of any such term or adjective never indicates that CONSULTANT shall have authority to supervise or direct performance of the Work or authority to undertake responsibility contrary to the provisions of Paragraphs 9.12 or 9.13.
9.12	CONSULTANT will not be responsible for the construction means, methods, techniques, sequences or procedures, or the safety precautions and programs incident thereto, and will not be responsible for CONTRACTOR'S failure to perform the Work in accordance with the Contract Documents.
9.13	CONSULTANT will not be responsible for the acts or omissions of CONTRACTOR, or any Subcontractors, or any of his or their agents or employees, or any other persons performing any of the Work.
ARTICLE 10 - CHANGES IN THE WORK
10.1	Without invalidating the Agreement, OWNER may, at any time or from time to time, order additions, deletions, or revisions in the Work; these will be authorized by Change Orders. Upon receipt of a Change Order, CONTRACTOR shall proceed with the Work involved. All such Work shall be executed under the applicable conditions of the Contract Documents. If any Change Order causes an increase or decrease in the Contract Price or an extension or shortening of the Contract Time, an equitable adjustment will be made as provided in Article 11 or 12.
10.2	CONSULTANT may authorize minor changes or alterations in the Work not involving an adjustment in the Contract Price or the Contract Time, which are consistent with the overall intent of the Contract Documents. These may be accomplished by a Field Order. If CONTRACTOR believes that a Field Order justifies an increase in the Contract Price or Contract Time, he may make a claim therefor as provided in Article 11 or 12.
10.3	Additional Work performed by CONTRACTOR without authorization of a Change Order will not entitle him to an increase in the Contract Price or an extension of the Contract Time, except in the case of an emergency as provided in Paragraph 6.25 and except as provided in Paragraph 10.2.
10.4	OWNER shall execute appropriate Change Orders prepared by CONSULTANT covering changes in the Work which are required by OWNER, or required because of unforeseen physical conditions or emergencies, or because of uncovering Work found not to be defective, or because of any other claim of CONTRACTOR for a change in the Contract Time or the Contract Price which is approved by CONSULTANT.
10.5	It is CONTRACTOR'S responsibility to notify his Surety of any changes affecting the general scope of the Work or change in the Contract Price or Contract Time, and the amount of the applicable Bonds shall be adjusted accordingly. CONTRACTOR will furnish proof of such adjustment to OWNER.
ARTICLE 11 - CHANGE OF CONTRACT PRICE
11.1	The Contract Price constitutes the total compensation payable to CONTRACTOR for performing the Work. All duties, responsibilities and obligations assigned to or undertaken by CONTRACTOR shall be at his expense without change in the Contract Price.
11.2	The Contract Price may only be changed by a Change Order. Any claim for an increase in the Contract Price, shall be in writing delivered to OWNER and to CONSULTANT within fifteen days of the occurrence of the event giving rise to the claim. All claims for adjustments in the Contract Price shall be determined by CONSULTANT if OWNER and CONTRACTOR cannot otherwise agree on the amount involved. Any change in the Contract Price resulting from any such claim shall be incorporated in a Change Order.
11.3	The value of any Work covered by a Change Order or of any claim for an increase or decrease in the Contract Price shall be determined in one of the following ways:
11.3.1	Where the Work involved is covered by unit prices contained in the Contract Documents, by application of unit prices to the quantities of the items involved.
11.3.2	By mutual acceptance of a lump sum.
11.3.3	By cost and a mutually acceptable fixed amount for overhead and profit.
11.3.4	If none of the above methods is agreed upon, the value shall be determined by CONSULTANT on the basis of costs and a percentage for overhead and profit. Costs shall only include labor (payroll, payroll taxes, fringe benefits, workmen's compensation, etc.), materials, equipment, and other incidentals directly related to the Work involved. The maximum percentage which shall be allowed for CONTRACTOR'S combined overhead and profit shall be as follows:
11.3.4.1	For all such Work done by his own organization, CONTRACTOR may add up to ten percent (10%) of his actual net increase in cost, and
11.3.4.2	For all such Work done by Subcontractors, each Subcontractor may add up to ten percent (10%) of his actual net increase in costs for combined overhead and profit and CONTRACTOR may add up to five percent (5%) of the Subcontractor's total for his combined overhead and profit, provided that no overhead or profit shall be allowed on costs incurred in connection with premiums for public liability insurance or other special insurance directly related to such Work.
In such case and also under Paragraph 11.3.3, CONTRACTOR shall submit to CONSULTANT an itemized cost breakdown together with supporting data.
11.4	The amount of credit to be allowed by CONTRACTOR to OWNER for any such change which results in a net decrease in cost, will be the amount of the actual net decrease as determined by CONSULTANT. When both additions and credits are involved in any one change, the combined overhead and profit shall be figured on the basis of the net increase, if any.
Cash Allowances:
11.5	It is understood that CONTRACTOR has included in the Contract Price all allowances so named in the Contract Documents and shall cause the Work so covered to be done by such Subcontractors, manufacturers, fabricators, suppliers or distributors and for such sums within the limit of the allowances as Consultant may approve. Upon final payment, the Contract Price shall be adjusted as required and an appropriate Change Order issued. CONTRACTOR agrees that the original Contract Price includes such sums as he deems proper for costs and profit on account of cash allowances. No demand for additional cost or profit in connection therewith will be valid.
ARTICLE 12 - CHANGE OF CONTRACT TIME
12.1	The Contract Time may only be changed by a Change Order. Any claim for an extension in the Contract Time shall be in writing delivered to OWNER and CONSULTANT within fifteen days of the occurrence of the event giving rise to the claim. All claims for adjustment in the Contract Time shall be determined by CONSULTANT if OWNER and CONTRACTOR cannot otherwise agree. Any change in the Contract Time resulting from any such claim shall be incorporated in a Change Order.
12.2	The Contract Time will be extended in an amount equal to time lost due to delays beyond the control of CONTRACTOR if he makes a claim therefor as provided in paragraph 12.1.
Such delays shall include, but not be limited to, acts or neglect by OWNER or others performing additional Work as contemplated by Article 7, or to fires, floods, labor disputes, epidemics, abnormal weather conditions, or acts of God.
12.3	All time limits stated in the Contract Documents are of the essence of the Agreement. The provisions of this Article 12 shall not exclude recovery for damages (including compensation for additional professional services) for delay by either party.
ARTICLE 13 - WARRANTY AND GUARANTEE; TESTS AND INSPECTIONS; CORRECTION, REMOVAL OR ACCEPTANCE OF DEFECTIVE WORK
Warranty and Guarantee:
13.1	CONTRACTOR warrants and guarantees to OWNER and CONSULTANT that all materials and Work will be of good quality and free from faults or defects and in accordance with the requirements of the Contract Documents for a period of three years from the date of Substantial Completion. Prompt notice of all defects shall be given to CONTRACTOR. All defective Work, whether or not in place, may be rejected, corrected or accepted as provided in this Article 13.
Tests and Inspections:
13.2	If the Contract Documents, or any law, ordinance, rule, regulation, code, or order of any public authority having jurisdiction require any Work (or part thereof) to specifically be inspected, tested, or approved by someone other than CONTRACTOR, CONTRACTOR shall give CONSULTANT timely notice of readiness therefor and shall assume full responsibility therefor, pay all costs in connection therewith and furnish CONSULTANT the required certificates of inspection, testing or approval. All such tests will be in accordance with the methods prescribed by the American Society for Testing and Materials or such other applicable organization as may be required by law or the Contract Documents.
13.3	Neither observations by CONSULTANT nor inspections, tests or approvals by persons other than CONTRACTOR shall relieve CONTRACTOR from his obligations to perform the Work in accordance with the requirements of the Contract Documents.
Access to the Work:
13.4	CONSULTANT or CONSULTANT’S representatives, other representatives of OWNER, testing agencies and governmental agencies with jurisdictional interests, will at all times have access to the Work. CONTRACTOR shall provide proper facilities for such access and observation of the Work and also for any inspection, or testing thereof by others.
Owner May Stop the Work:
13.5	If the Work is defective or CONTRACTOR fails to supply sufficient skilled workmen or suitable materials or equipment, or if CONTRACTOR fails to make prompt payments to Subcontractors or for labor, materials or equipment, OWNER may order CONTRACTOR to stop the Work, or any portion thereof, until the cause for such order has been eliminated. However, this right of OWNER to stop the Work shall not give rise to any duty on the part of OWNER to exercise this right for the benefit of CONTRACTOR or any other party.
Correction or Removal of Defective Work:
13.6	If required by CONSULTANT prior to approval of payment, CONTRACTOR shall promptly, without cost to OWNER and as specified by CONSULTANT, if the work has been rejected by CONSULTANT, remove it from the site and replace it with nondefective work. If CONTRACTOR does not remove and replace such rejected work within a reasonable time, all as specified in a written notice from CONSULTANT, OWNER may have the rejected work removed and replaced. All direct or indirect costs of such removal and replacement, including compensation for additional professional services, shall be paid by CONTRACTOR, and an appropriate deductive Change Order shall be issued. CONTRACTOR shall also bear the expenses of making good all work of others destroyed or damaged by his removal or replacement of his defective work.
Guaranty Period:
13.7	If, after the approval of payment and prior to the expiration of three years after the date of Substantial Completion or such longer period of time as may be prescribed by law or by the terms of any applicable special guarantee required by the Contract Documents, any work is found to be defective, CONTRACTOR shall, promptly, without cost to OWNER, and in accordance with OWNER'S written instructions, if it has been rejected by OWNER, remove it from the site and replace it with nondefective work. If CONTRACTOR does not promptly comply with the terms of such instructions, or in an emergency where delay would cause serious risk of loss or damage, OWNER may have the rejected work removed and replaced, and all direct and indirect costs of such removal and replacement, including compensation for additional professional services, shall be paid by CONTRACTOR.
Acceptance of Defective Work:
13.8	if, instead of requiring removal and replacement of defective work, OWNER (and, prior to approval of payment, also CONSULTANT) prefers to accept it, OWNER may do so. In such case, if acceptance occurs prior to approval of payment, a Change Order shall be issued incorporating the necessary revisions in the Contract Documents, including appropriate reduction in the Contract Price, or, if the acceptance occurs after approval of payment, an appropriate amount shall be paid by CONTRACTOR to OWNER.
Neglected Work by Contractor:
13.9	If CONTRACTOR should neglect to prosecute the Work in accordance with the Contract Documents, including any requirements of the progress schedule, OWNER, after three days written notice to CONTRACTOR may, without prejudice to any other remedy he may have, make good such deficiencies and the cost thereof (including compensation for additional professional services) shall be charged against CONTRACTOR if CONSULTANT approves such action, in which case a Change Order shall be issued incorporating the necessary revisions in the Contract Documents including an appropriate reduction in the Contract Price. If the payments then or thereafter due CONTRACTOR are not sufficient to cover such amount, CONTRACTOR shall pay the difference to OWNER.
ARTICLE 14 - PAYMENTS AND COMPLETION
Application for Payment:
14.1	After the Work has been completed, and after CONTRACTOR has completed any such corrections to the satisfaction of CONSULTANT and delivered all guarantees, bonds, certificates of inspection and other documents, all as required by the Contract Documents, and after CONSULTANT has indicated that the Work is acceptable (subject to the provisions of Paragraph 14.6), CONTRACTOR may make his application for payment. CONSULTANT will advise CONTRACTOR of the breakdown of accounts to be charged on his invoice.  The application for payment shall be accompanied by such supporting data as CONSULTANT may require, together with complete and legally effective releases or waivers (satisfactory to OWNER) of all liens arising out of the Contract Documents and the labor and services performed and the material furnished thereunder. In lieu thereof and as approved by OWNER, CONTRACTOR may furnish receipts or releases in full, an affidavit of CONTRACTOR that the releases and receipts include all labor, services, and material for which a lien could be filed, and that all payrolls, material and equipment bills, and other indebtedness connected with the Work for which OWNER or his property might in any way be responsible, have been paid or otherwise satisfied, and consent of the Surety, if any, to payment. If any Subcontractor, manufacturer, fabricator, supplier, or distributor fails to furnish a release or receipt in full, CONTRACTOR may furnish a bond satisfactory to OWNER to indemnify OWNER against any lien. Payment will be based on the lump-sum Contract Price stated in the Agreement.
Approval of Payment Application:
14.2	If, on the basis of CONSULTANT’S observation and review of the Work during construction and final inspection, and her review of the application for payment, all as required by the Contract Documents, CONSULTANT is satisfied that the Work has been completed and CONTRACTOR has fulfilled all of his obligations under the Contract Documents, she will, within ten days after receipt of the application for payment, indicate in writing her approval of payment and present the application to the OWNER for payment. Otherwise, she will return the application to CONTRACTOR, indicating in writing her reasons for refusing to approve payment, in which case CONTRACTOR shall make the necessary corrections and resubmit the application. OWNER will, within six weeks of presentation to him of an approved application for payment, pay CONTRACTOR the amount approved by CONSULTANT.
Contractor's Warranty of Title:
14.3	CONTRACTOR warrants and guarantees that title to all Work and materials covered by his application for payment, will have passed to OWNER prior to the making of the application for payment, free and clear of all liens, claims, security interests and encumbrances (hereafter in these General Conditions referred to as liens), and that no Work or materials covered by his application for payment will have been acquired by CONTRACTOR or by any other person performing the Work at the site or furnishing materials and equipment for the Project, subject to an agreement under which an interest therein or encumbrance thereon is retained by the seller or otherwise imposed by CONTRACTOR or such other person.
14.4	CONSULTANT’S approval of payment shall constitute an additional representation by CONSULTANT to OWNER that the conditions precedent to CONTRACTOR'S being entitled to payment as set forth in paragraph 14.2 have been fulfilled.
14.5	CONSULTANT may refuse to approve the whole or any part of any payment if, in her opinion, it would be incorrect to make such representations to OWNER. CONSULTANT may also refuse to approve any such payment to such extent as may be necessary in her opinion to protect OWNER from loss because:
14.5.1	The Work is defective, or completed Work has been damaged, requiring correction or replacement,
14.5.2	Claims have been filed or there is reasonable evidence indicating the probable filing thereof,
14.5.3	The Contract Price has been reduced because of Modifications,
14.5.4	OWNER has been required to correct defective Work or complete the Work in accordance with paragraph 13.9,
14.5.5	Of CONTRACTOR'S unsatisfactory prosecution of Work, in accordance with the Contract Documents, including failure to clean up as required by paragraph 6.18, or
14.5.6	CONTRACTOR'S failure to make payment to Subcontractors, or for labor, materials or equipment.
14.6	The making and acceptance of payment shall constitute:
14.6.1	A waiver of all claims by OWNER against CONTRACTOR, except claims arising from unsettled liens, from defective Work appearing after final inspection or from failure to comply with the requirements of the Contract Documents or the terms of any special guarantees specified therein; however, it shall not constitute a waiver by OWNER of any rights in respect of CONTRACTOR'S continuing obligations under the Contract Documents; and
14.6.2	A waiver of all claims by CONTRACTOR against OWNER other than those previously made in writing and still unsettled.
ARTICLE 15 - SUSPENSION OF WORK AND TERMINATION
Owner May Suspend Work:
15.1	OWNER may, at any time and without cause, suspend the Work or any portion thereof for a period of not more than ninety days by notice in writing to CONTRACTOR and to CONSULTANT which shall fix the date on which work shall be resumed. CONTRACTOR shall resume the Work on the date so fixed. CONTRACTOR will be allowed an increase in the Contract Price or an extension of the Contract Time, or both, directly attributable to any suspension if he makes a claim therefor as provided in Articles 11 and 12.
Owner May Terminate:
15.2	If CONTRACTOR is adjudged as bankrupt or insolvent, or if he makes a general assignment for the benefit of his creditors, or if a trustee or receiver is appointed for CONTRACTOR or for any of his property, or if he files a petition to take advantage of any debtor's act, or to reorganize under the bankruptcy or similar laws, or if he repeatedly fails to supply sufficient skilled workmen or suitable materials or equipment, or if he repeatedly fails to make prompt payments to Subcontractors or for labor, materials or equipment, or if he disregards laws, ordinances, rules, regulations or order of any public body having jurisdiction, or if he disregards the Authority of CONSULTANT, or if he otherwise violates any provision of the Contract Documents, then OWNER may, without prejudice to any other right or remedy and after giving CONTRACTOR and his Surety seven days written notice, terminate the services of CONTRACTOR and take possession of the Project and of all materials, equipment, tools, construction equipment and machinery thereon owned by CONTRACTOR or for which OWNER has paid CONTRACTOR but which are stored elsewhere, and finish the Work as OWNER may deem expedient. In such case, CONTRACTOR shall not be entitled to receive any further payment until the Work is finished. If the unpaid balance of the Contract Price exceeds the direct and indirect costs of completing the Project, including compensation for additional professional services, such excess shall be paid to CONTRACTOR. If such costs exceed such unpaid balance, CONTRACTOR shall pay the difference to OWNER. Such costs incurred by OWNER will be determined by CONSULTANT and incorporated in a Change Order, but in finishing the Work, OWNER will not be required to obtain the lowest figure for the Work performed.
15.3	Where CONTRACTOR'S services have been so terminated by OWNER, the termination shall not affect any rights of OWNER against CONTRACTOR then existing or which may thereafter accrue. Any retention or payment of moneys by OWNER due CONTRACTOR will not release CONTRACTOR from liability.
15.4	Upon seven days' written notice to CONTRACTOR and CONSULTANT, OWNER may, without cause and without prejudice to any other right or remedy, elect to abandon the Project and terminate the Agreement. In such case, CONTRACTOR shall be paid for all work executed and any expense sustained plus reasonable termination expenses.
Contractor May Stop Work or Terminate:
15.5	If, through no act or fault of CONTRACTOR, the Work is suspended for a period of more than ninety days by OWNER or under an order of court or other public authority, or CONSULTANT fails to act on any application for payment within thirty days after it is submitted, or OWNER fails to pay CONTRACTOR any sum approved by CONSULTANT or awarded by arbitrators within thirty days of its approval and presentation, then CONTRACTOR may, upon seven days' written notice to OWNER and CONSULTANT, terminate the Agreement and recover from OWNER payment for all work executed and any expense sustained plus reasonable termination expenses. In addition and in lieu of terminating the Agreement, if CONSULTANT has failed to act on an application for payment or OWNER has failed to make any payment as aforesaid, CONTRACTOR may upon seven days' notice to OWNER and CONSULTANT stop the Work until he has been paid all amounts then due.
ARTICLE 16 - NOT APPLICABLE
ARTICLE 17 - ASSIGNMENT OF CONTRACT
17.1	CONTRACTOR shall not assign the Contract or sublet it as a whole without the written permission of OWNER, nor shall CONTRACTOR assign any moneys due to him under the Contract, except to a bank or financial institution.
ARTICLE 18 - REMOVAL OF EQUIPMENT
18.1	In the case of termination of this Contract, before completion, from any cause whatever, CONTRACTOR, if notified to do so by OWNER, shall promptly remove any part or all of his equipment and supplies from the property of OWNER, failing which OWNER shall have the right to remove such equipment and supplies at the expense of CONTRACTOR.
ARTICLE 19 - MISCELLANEOUS
19.1	Whenever any provision of the Contract Documents requires the giving of written notice, it shall be deemed to have been validly given if delivered in person to the individual or to a member of the firm or to an officer of the corporation for whom it is intended, or if delivered at or sent by registered or certified mail, postage prepaid, to the last business address known to him who gives the notice.
19.2	NOT APPLICABLE
19.3	All Specifications, Drawings and copies thereof furnished by CONSULTANT shall remain her property. They shall not be used on another project, and with the exception of those sets which have been signed in connection with the execution of the Agreement, shall be returned to her on request upon completion of the Project.
19.4	The duties and obligations imposed by these General Conditions and the rights and remedies available hereunder, and, in particular but without limitation, the warranties, guarantees and obligations imposed upon CONTRACTOR by paragraphs 6.3, 13.1, 13.6, 14.3, and 15.2, and the rights and remedies available to OWNER and CONSULTANT thereunder, shall be in addition to and not a limitation of any otherwise imposed or available by law, by special guarantee or other provisions of the Contract Documents.
19.5	Should OWNER or CONTRACTOR suffer injury or damage to its person or property because of any error, omission or act of the other or of any of his employees or agents or others for whose acts he is legally liable, claim shall be made in writing to the other party within a reasonable time of the first observance of such injury or damage.
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2.4.2  PREVAILING WAGES

Contractors shall pay not less than the prevailing wages and fringe benefits contained in the PENNSYLVANIA PREVAILING WAGE RATES which are made part of this Specification and contained in the following pages.

BUREAU OF LABOR LAW COMPLIANCE — PREVAILING WAGES PROJECT RATES

Commonwealth of Pennsylvania, Department of Labor & Industry — Report Date: 10/13/26
[image: ]
Building

	Contractor Craft
	Hourly Rate
	Fringe Benefits
	Total
	Effective Date
	Expiration Date

	Asbestos & Insulation Workers
	$43.06
	$30.31
	$73.37
	08/01/2025
	

	Boilermakers
	$40.90
	$27.61
	$68.51
	06/01/2016
	

	Bricklayer
	$39.15
	$24.66
	$63.81
	12/01/2025
	

	Bricklayer
	$39.75
	$25.06
	$64.81
	06/01/2026
	

	Carpenters - Piledriver/Welder
	$44.63
	$23.47
	$68.10
	01/01/2026
	

	Carpenters, Drywall Hangers, Framers, Instrument Men, Lathers, Soft Floor Layers
	$33.01
	$19.09
	$52.10
	06/01/2025
	

	Cement Finishers
	$28.71
	$17.85
	$46.56
	06/01/2016
	

	Cement Masons
	$34.57
	$25.09
	$59.66
	07/01/2024
	

	Drywall Finisher
	$34.66
	$25.15
	$59.81
	06/01/2025
	

	Drywall Finisher
	$36.09
	$26.47
	$62.56
	06/01/2026
	

	Electricians & Telecommunications Installation Technician
	$53.11
	$33.72
	$86.83
	12/26/2025
	

	Elevator Constructor
	$61.07
	$40.05
	$101.12
	01/01/2025
	

	Elevator Constructor
	$63.71
	$40.89
	$104.60
	01/01/2026
	



	Glazier
	$22.00
	$24.35
	$46.35
	06/01/2025
	

	Glazier
	$23.52
	$24.33
	$47.85
	06/01/2026
	

	Iron Workers
	$36.26
	$28.64
	$64.90
	06/01/2025
	

	Iron Workers
	$37.76
	$29.35
	$67.11
	06/01/2026
	

	Laborers (Class 01 - See notes)
	$27.32
	$19.87
	$47.19
	01/01/2025
	

	Laborers (Class 01 - See notes)
	$27.82
	$20.37
	$48.19
	01/01/2026
	

	Laborers (Class 02 - See notes)
	$27.47
	$19.87
	$47.34
	01/01/2025
	

	



Heavy/Highway

Contractor Craft
Hourly Rate
Fringe Benefits
Total
Effective Date
Expiration Date
Carpenter
$42.35
$22.84
$65.19
01/01/2026

Carpenter Welder
$43.85
$22.84
$66.69
01/01/2026

Carpenters - Piledriver/Welder
$44.63
$23.47
$68.10
01/01/2026

Cement Finishers
$35.94
$27.50
$63.44
01/01/2025

Cement Masons
$32.84
$21.10
$53.94
01/01/2020

Electric Lineman
$68.06
$32.29
$100.35
09/01/2025

Electric Lineman
$69.90
$34.20
$104.10
08/30/2026

Iron Workers
$36.26
$28.64
$64.90
06/01/2025

Laborers (Class 01 - See notes)
$33.70
$26.00
$59.70
01/01/2025

Laborers (Class 01 - See notes)
$34.70
$27.00
$61.70
01/01/2026

Laborers (Class 02 - See notes)
$33.86
$26.00
$59.86
01/01/2025

Laborers (Class 02 - See notes)
$34.86
$27.00
$61.86
01/01/2026

Laborers (Class 03 - See notes)
$34.25
$26.00
$60.25
01/01/2025

Laborers (Class 03 - See notes)
$35.25
$27.00
$62.25
01/01/2026

Laborers (Class 04 - See notes)
$34.70
$26.00
$60.70
01/01/2025

Laborers (Class 04 - See notes)
$35.70
$27.00
$62.70
01/01/2026

Laborers (Class 05 - See notes)
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$26.00
$61.11
01/01/2025

Laborers (Class 05 - See notes)
$36.11
$27.00
$63.11
01/01/2026

Laborers (Class 06 - See notes)
$31.95
$26.00
$57.95
01/01/2025

Laborers (Class 06 - See notes)
$32.95
$27.00
$59.95
01/01/2026
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2.5  SCHEDULE OF DRAWINGS

1.	The following numbered and titled drawings, entitled "Fuchs Lubricants Co. Site Demolition/E&S Plans," 105 8th Street, Emlenton, Pennsylvania, prepared by Moody and Associates, Inc., and dated October 2026, are to be included as part of the Contract Documents as fully as if here set forth. The Drawings are bound in Appendix A of this Project Manual.

	NUMBER
	TITLE

	C000
	Cover Sheet

	C110
	Demolition–E&S Plan

	C141
	Erosion & Sediment Control Details

	C142
	Erosion & Sediment Control Details

	C143
	Erosion & Sediment Control Details




2.	The following report is included as part of the Contract Documents as fully as if here set forth. It is bound in Appendix B of this Project Manual and is referred to in the Specifications as the "Hazardous Building Materials Survey" or "HBMS."

	REFERENCE
	TITLE

	HBMS
	Pre-Demolition Hazardous Building Materials Survey, Fuchs Lubricants Co. Site, 105 Eighth Street, Emlenton, Pennsylvania, prepared by Moody and Associates, Inc. (Moody Project No. 24-046-MM), dated June 24, 2025
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2.6  SPECIFICATIONS
GENERAL TECHNICAL SPECIFICATIONS
1.  QUANTITIES, MATERIALS, AND WORK
The CONTRACTOR shall be responsible to satisfy himself of the accuracy of any estimated quantities in the Drawings, the Hazardous Building Materials Survey (HBMS) or the Specifications by examination of the site and a review of the Drawings, the HBMS and Specifications including any issued Addenda and Change Orders. After the Contract has been awarded, the CONTRACTOR shall not assert that there was a misunderstanding concerning the quantities of work or of the nature or scope of the work to be done.
2.  MANUFACTURER OR BRAND NAMES
Where a manufacturer or brand name is used it is understood that the equipment or product so described shall be similar and equal to the brand and designation given but such reference is for descriptive purposes only. All necessary submittals, tests, certificates, etc., will be required whether a brand name or manufacturer designated product is used as referred to in these Specifications or whether an equal product is selected. Prior to the use of similar and equal products, the CONTRACTOR must obtain written approval from the CONSULTANT.
3.  SHOP SUBMITTALS
The CONTRACTOR shall submit to the CONSULTANT one electronic copy and one hardcopy of descriptive details and shop and setting drawings for all materials and equipment installed or provided as part of the Contract Work. Submissions shall be made even though the items proposed to be furnished conform to the exact description stated in the Specifications.
4.  COMPLIANCE WITH FEDERAL, STATE, AND LOCAL LAWS, RULES, AND REGULATIONS
It is a requirement of these Specifications that all work performed under this Contract shall comply with all Federal, State, and Local laws and rules and regulations. Particular attention is directed to the safety requirements of the Pennsylvania Department of Labor and Industry with regard to sheeting and shoring, the Occupational Safety and Health Administration with regard to job-site safety, and the erosion control and pollution control requirements of the Pennsylvania Department of Environmental Protection with regard to water and air pollution. The CONTRACTOR shall be responsible for performing all Contract Work in accordance with all applicable permit and/or approval requirements, and all inspections, observations, etc. necessary to ensure conformance with said requirements shall be the responsibility of the CONTRACTOR.
5.  SAFETY
The CONTRACTOR will be solely and completely responsible for conditions of the job site, including safety of all persons and property during performance of the work. This requirement will apply continuously and will not be limited to normal working hours. The CONTRACTOR shall be responsible to ensure all employees adhere to safe work practices. The duty of the OWNER or the CONSULTANT to conduct construction review of the CONTRACTOR's performance is in no way intended to include review of the adequacy of the CONTRACTOR's safety measures, in, on, or near the construction site.
The HBMS reports accumulations of graphite dust on most surfaces within the building. Graphite dust presents a respiratory hazard and, in dust form, an explosion hazard if ignited. The CONTRACTOR shall address graphite dust in its site safety procedures, control ignition sources in areas where graphite dust is present, and comply with Section 026610 and all applicable OSHA standards.
6.  EROSION AND SEDIMENTATION CONTROL
The CONTRACTOR shall plan and manage his construction operations and activities to control and minimize project related erosion and sedimentation. The CONTRACTOR shall implement control measures in accordance with acceptable best management practices (BMPs) for the control of erosion and sedimentation. These control measures shall include, but not be limited to, the 18-inch compost filter socks, inlet filter bag protection at the existing inlet, and rock construction entrance shown on the Drawings, the diversion of stormwater around areas of disturbed soil, and the prompt establishment of finished surface grade conditions. The CONTRACTOR shall perform all site work in accordance with the Erosion and Sedimentation Control Plan, notes and details shown on Drawings C110 and C141 through C143, and with the requirements of 25 Pa. Code Chapter 102. The limit of disturbance is less than one (1) acre; an NPDES permit for stormwater discharges associated with construction activities is not required. A copy of the approved E&S Plan shall be kept at the project site at all times. Construction vehicles shall not enter areas outside the limit of disturbance shown on the Drawings.
7.  REMOVAL AND DISPOSAL OF MATERIAL
The CONTRACTOR shall undertake, to their fullest ability, all practicable actions and efforts to minimize project related debris and waste, recycle and re-use project materials, and minimize the project work activities upon the environment. All construction related debris, including vegetation resulting from project related activities, remaining in the work area shall be removed from the site and disposed of by the CONTRACTOR at a Pennsylvania Department of Environmental Protection approved disposal facility. No soils shall be moved off site (Drawing C110, Demolition Note 22). All concrete and debris resulting from demolition activities shall be cleaned of soils before being disposed of off-site in accordance with the PADEP Management of Fill Policy (Document No. 258-2182-773). Demolished materials shall not be allowed to accumulate on-site and shall not be burned on-site. Regulated waste, graphite dust and asbestos-containing material shall be handled and disposed of in accordance with Sections 026610 and 028213. The CONTRACTOR shall be responsible for cleanup of the site upon project completion and shall be responsible for the removal of all work-related debris from the property of the OWNER.
8.  MATERIAL STORAGE
The CONTRACTOR may store materials necessary for project related activities on the property identified by the CONSULTANT, within the limit of disturbance shown on the Drawings. The CONSULTANT and the OWNER however assume no responsibility or liability for injury or damages associated with said storage. Furthermore, the CONSULTANT and the OWNER assume no responsibility or liability for theft of materials occurring while said materials are in storage.
9.  LIGHT, HEAT, POWER, AND WATER
Unless expressly otherwise stated, the CONTRACTOR shall arrange for, supply and maintain, at his own cost, all light, heat, power and ample water supply required for the proper prosecution and completion of the Contract.
10.  WARNING SIGNS AND BARRICADES
The CONTRACTOR shall provide adequate signs, barricades, warning/signal lights, etc. and take all necessary precautions for the protection of the work and the safety of the public, including users of the Allegheny River Trail. All barricades and obstructions shall be protected at night by suitable signal lights which shall be kept operating from sunset to sunrise. Barricades shall be of substantial construction and shall be painted such as to increase their visibility at night. Suitable warning signs shall be so placed and illuminated at night as to show in advance where construction, barricades or detours exist.
11.  PUBLIC CONVENIENCE
The CONTRACTOR shall at all times so conduct his work as to ensure the least possible obstruction to traffic and inconvenience to the general public and the residents in the vicinity of the work, and to ensure the protection of all persons and property. No road, street or trail shall be closed to the public except with the permission of the proper authorities. Fire hydrants on or adjacent to the work shall be kept accessible to fire-fighting equipment at all times. Temporary provisions shall be made by the CONTRACTOR to ensure the continuous and unobstructed use of all sidewalks and walkways and the proper functioning of all gutters, sewer inlets, drainage ditches, etc. throughout the duration of the project work.
12.  EXCAVATION, BACKFILL, GRADING AND COMPACTION
12.1	General Scope of Work
12.1.1	All labor, materials, equipment, tools and services required for the making of all excavations for removal of foundations and slabs, the placing of backfill and general site grading required on this Contract shall be furnished and performed in compliance with the following General Specification, the Specifications and the Drawings.
12.1.2	This General Specification covers the description of methods usually employed in excavation and backfill for structures and general grading operations. The Detailed Specifications and the Drawings designate the specific work, the lines, grades and details of the work to be performed under this Contract.
12.1.3	Excavation and Backfill specifications for facilities other than structures are included in other Sections of the Specifications.
12.2	General Construction Methods
12.2.1	The CONTRACTOR shall accept conditions at the site of the work as found and shall assume the risk of any variation of the condition of site or buildings thereon which may occur subsequent to signing of the Contract. The CONTRACTOR must assume the risk of meeting, and the Contract Price shall include, the cost of removal of quicksand, hardpan, boulders, clay, rubbish, unforeseen obstacles, underground conduits, gas pipe, drain tile, trees, roots, timber or masonry structures, railroad tracks, pavements and sidewalks and the delay or damage occasioned by same, whether or not these obstacles are shown on the Drawings. No claim for an amount of money beyond the Contract Price of the work will be entertained or allowed on account of the character of the ground in which the excavation is made unless rock as defined hereinafter is encountered and removed.
12.2.2	The OWNER reserves the right to make minor variations in the location of proposed work during the construction. No extra payment will be allowed the CONTRACTOR for such shifts in alignment or location.
12.2.3	Soils investigation data, if any, shown on the Drawings is presented only for the general information of the CONTRACTOR. If, after excavation is made, conditions are disclosed which are unsuitable, the CONTRACTOR shall take such measures as directed by the CONSULTANT. Any such work ordered will be paid for in accordance with the provisions for changes in the Work and changes in the Contract Price in Articles 10 and 11 of the General Conditions or at Contract unit prices, if any.
12.3	Protection of Property
12.3.1	Necessary arrangements shall be made by the CONTRACTOR with all persons, firms, corporations owning or using any poles, pipes, tracks, or conduits, etc., affected by the construction included under this Section to maintain and protect such facilities during construction. The cost of any protection shall be paid by the CONTRACTOR and included in the Contract Price.
12.3.2	In the event that any existing gas pipes, water pipes, conduits, sewers, tile drains, poles or other utilities not designated for disconnection are blocked or interfered with by construction operations, the CONTRACTOR shall maintain them in continuous operation, and restore them to the same condition as they were prior to the start of construction on this project, all at no additional compensation.
12.3.3	Excavated materials shall be deposited in areas designated by the CONSULTANT within the limit of disturbance. The CONTRACTOR shall avoid depositing excavated materials on pavements, sidewalks or grass plots, except on authorization of the CONSULTANT, and then only when adequate temporary provisions have been made for passage and protection of pedestrians and vehicles. Adequate bridging and planked crossings must be provided and maintained across all open excavations for pedestrians and vehicles.
12.3.4	The CONTRACTOR shall shore up or otherwise protect all fences, buildings, walls, walks, curbs, or other property adjacent to any excavation which might be disturbed during the progress of the work, including the existing walls and buildings to remain shown on the Drawings. The CONTRACTOR will be held liable for any damage which may result to neighboring property from excavation, backfill or grading operations performed.
12.3.5	Where excavation or demolition is to be carried on adjacent to property or construction owned by others, the CONTRACTOR shall give due and legal notice to such owner and shall take all steps necessary to protect adjacent construction from damage arising out of his operations; and he shall protect the OWNER named in this Contract and his agents from any and all claims arising from excavation or demolition operations. Operations shall cease immediately if adjacent structures appear to be in danger, and the authority having jurisdiction shall be notified.
12.4	Protection Against Water
12.4.1	The CONTRACTOR shall take all steps necessary such as ditching, diking, pumping, well pointing, and bailing, construct necessary drains and channels to keep the excavation clear of ground water, sewage or stormwater, during the progress of the work and until the finished work is safe from injury. All pumped water shall be discharged through a pumped water filter bag as detailed on the Drawings.
12.4.2	Adequate measures and protection shall be provided for vaults, tanks, basements, etc., from effect of possible uplift due to storm or ground water where buoyancy might lift structures or floor failures may occur during construction.
12.5	Site Clearing
12.5.1	All foundations, concrete slabs and other existing construction of Building 1, and other existing pavements, structures and similar work designated on the Drawings for removal, or encountered which will interfere with site grading and restoration operations, shall be demolished and removed, and the building footprint shall be returned to existing grade, as shown on Drawing C110. All pipe and sewer services shall be sealed during demolition.
12.5.2	Existing wells, cisterns, catch basins, pits or cesspools encountered within the building footprint shall be cleaned out and backfilled in accordance with Paragraph 12.11. Existing basement floors, cisterns or cess pools outside of building areas, if of masonry or concrete and to remain in place, shall be cleared of all debris and bottoms broken up to provide drainage before any fill is placed over them.
12.5.3	All areas within which site grading or related construction is to be accomplished shall be cleared of brush, vegetation, rubbish, spoils, and other objectionable materials. Stumps encountered shall be entirely grubbed out. All trees and shrubbery designated to remain shall be adequately protected until finished grading is completed.
12.6	General Excavation
12.6.1	Excavation shall include the loosening, loading, removing, transporting, and disposing of all materials, wet or dry, necessary to be removed to complete the work included in this Section to the lines, grades and locations shown on the Drawings. Excavated materials shall be piled in locations that will not interfere with construction operations.
12.6.2	Unless specifically directed by the CONSULTANT, excavation shall not be carried below the depth necessary to remove existing foundations and slabs. Where any excavation is made below that depth, the excavation shall be restored to the proper elevation with compacted backfill in accordance with Paragraph 12.11, at no additional expense to the OWNER.
12.6.3	The CONTRACTOR shall furnish and install all temporary sheeting, shoring, timbering, bracing and steel sheet piling required to maintain the excavation in a safe condition and to prevent movement or settlement of adjacent structures. Upon completion, all temporary shores and bracing shall be removed. While being withdrawn, all vacancies left by the sheeting and bracing shall be carefully filled and compacted as directed by the CONSULTANT.
12.6.4	Under certain conditions sheeting and bracing may be ordered by the CONSULTANT to be left in place. Any sheeting so ordered left in place will be paid for on the basis of the Contract unit price for such work. If no Contract unit price is established for this work, payment will be established in accordance with Articles 10 and 11 of the General Conditions.
12.6.5	DELETED.
12.6.6	When soils materials encountered in any excavation are not suitable, the CONTRACTOR shall furnish and place well-graded crushed stone or gravel backfill as directed by the CONSULTANT. The crushed stone or gravel shall have a minimum size of 1 inch and a maximum of 2½ inches and shall be installed in 8 inch layers. If no Contract unit price is established for this work, payment will be made in accordance with Articles 10 and 11 of the General Conditions. If layer of backfill is greater than 8 inches, fine granular material shall be placed and mixed into the stone or gravel to fill voids.
12.6.7	Where existing topsoil is present in areas to be excavated or regraded, topsoil shall be stripped and deposited in stockpiles convenient to the areas which are subsequently to receive application of topsoil. Stockpiles shall be located in dry, stable areas, with side slopes no steeper than 2:1, and protected as detailed on the Drawings. Topsoil shall be used exclusively for finished grading.
12.6.8	Unsuitable and surplus excavated soil shall be managed on site as directed by the CONSULTANT; no soils shall be moved off site. Debris not incorporated in the project shall be disposed of by the CONTRACTOR at his own expense outside the limits of the Project site in accordance with Article 7.
12.6.9	DELETED.
12.7	Rock Excavation
12.7.1	Wherever the word "Rock" appears in this Section, it shall be interpreted to mean any material geologically in place and of a hardness when first exposed of three (3) or greater in the scale of mineral hardness, which corresponds to the hardness of the transparent variety of calcite. Any material encountered not of a uniform hardness of three (3) in the scale of mineral hardness which cannot be removed from its original position with a modern three-quarter cubic yard backhoe power excavator in good condition without continuous drilling and blasting will be considered rock, provided that the CONTRACTOR proves by demonstration and photographic evidence that slate, shale, sandstone or other hard material encountered cannot be removed with heavy equipment without continuous drilling and blasting. Other materials shall not be classified as rock, although it may be more economical to remove same by blasting. Boulders will not be classified as rock unless larger than 1 cubic yard, and boulder removal will only be considered extra work in the event they require all removal efforts herein described for rock.
12.7.2	Should rock be encountered in the excavation, it shall be removed by blasting or other approved methods. Where blasts are made the excavation shall be carefully covered with suitable brush, timber, or matting to prevent danger to life and property. The CONTRACTOR shall secure all permits required by Law for blasting operations and any additional hazard insurance required, the cost of such permits and insurance to be borne by the CONTRACTOR. No blasting shall be done by the CONTRACTOR until he has notified the CONSULTANT and until the necessary cross-sections of the top of the rock have been taken.
12.7.3	DELETED.
12.8	Trench Excavation
12.8.1	Trench excavation required for utility disconnection and capping shall be of sufficient width and depth to provide ample room within the limits of the excavation, or lines of sheeting and bracing, for the proper performance of the work. Trenches shall be backfilled in accordance with Paragraph 12.11. Where trench excavation is required for pipelines or appurtenances, the minimum cover to the established grade shall be 3 feet unless otherwise shown on the Drawings, and pipe shall be bedded in a minimum of six (6) inches of AASHTO No. 67 coarse aggregate.
12.9	Excavation for Structures, Footings, and Appurtenances (DELETED)
12.10	Foundation Strengthening (DELETED)
12.11	Backfill, Embankment, and Fills
12.11.1	All backfilling shall be made to lines and grades shown on the Drawings. The building footprint and other excavations resulting from removal of foundations and slabs shall be backfilled with clean fill compacted to ninety-five percent (95%) of maximum dry density, as shown on Drawing C110. Backfill shall be placed in horizontal layers not in excess of six (6) inches in thickness after compaction, with optimum moisture content required for maximum compaction. Fill immediately adjacent to walls to remain shall be hand tamped, and special care shall be taken to prevent any wedging action or eccentric loading against the walls. No frozen material shall be used for backfilling and embankment, and fill shall not be placed on saturated or frozen surfaces.
12.11.2	If backfills, embankments, and fills are constructed in winter, all snow and ice shall be removed from the area. The area shall be thoroughly scarified before any fill is placed to insure bonding of the materials. So far as practicable, each layer shall extend the entire length of the embankment or fill. When completed, embankments and fills shall conform to lines, grades and slopes indicated on the Drawings.
12.11.3	All materials required for backfill, embankment, or fill shall be clean fill provided by the CONTRACTOR from sources approved by the CONSULTANT. The CONTRACTOR is responsible for ensuring that any material brought onto the site is clean fill as defined in the PADEP Management of Fill Policy. Documentation of clean fill determination (PADEP Form FP-001) shall be retained by the CONTRACTOR and submitted to the CONSULTANT prior to placement.
12.12	Compaction
12.12.1	All backfill and other areas of soil fill shall be compacted to a minimum of ninety-five percent (95%) of the maximum dry weight density, unless otherwise shown on the Drawings. The CONTRACTOR shall determine the maximum dry weight density by testing a minimum of 2 samples of each fill material. The maximum dry weight density shall be determined using modified moisture density tests, AASHTO T180, Method D (ASTM D 1557, Method D). The CONTRACTOR shall check the compaction achieved utilizing field density tests of the soil in-place. A minimum of one (1) field density test shall be performed for each 5,000 square feet of each lift of backfill placed in the building footprint. The CONSULTANT will designate the sampling locations. Copies of all test results shall be submitted to the CONSULTANT within 10 days of the performance of the testing.
12.12.2	The moisture content of the soil at the time of placement and compaction shall not be more than 2 percent above the optimum moisture content. Any soil displaying pronounced elasticity or deformation under construction equipment, or where the specified density cannot be obtained, shall be removed, replaced, and re-compacted to the required density by the CONTRACTOR at no additional cost to the OWNER.
12.12.3	The CONTRACTOR may submit to the CONSULTANT for review, alternative compaction testing procedures. Any such submittals shall be detailed and clearly written. No changes or deviations shall be made from the testing specified herein without written authorization from the CONSULTANT.
12.13	Site Grading and Restoration
12.13.1	Upon completion of the demolition operations the entire site within the limit of disturbance shown on the Drawings shall be rough graded and compacted to maintain site grades and contours and to provide proper drainage. The building footprint shall be returned to existing grade.
12.13.2	Areas to be topsoiled shall be scarified to a depth of 3 to 5 inches (6 to 12 inches on compacted soils) prior to placement of topsoil. A minimum of four (4) inches of topsoil shall be placed over the backfilled building footprint and other disturbed areas, and shall be limed, fertilized, seeded and mulched in accordance with the seeding and mulching tables and notes on the Drawings.
12.13.3	Permanent stabilization is defined as a minimum uniform, perennial 70% vegetative cover. Temporary E&S BMPs shall remain in place until permanent stabilization is achieved, and shall then be removed. Areas disturbed during removal of the BMPs shall be stabilized immediately.
13.  PROTECTION OF PROPERTY
13.1	Necessary arrangements shall be made by the CONTRACTOR with all persons, firms, corporations, etc., including the OWNER, whose property or possessions may be affected by the work performed under this Contract to maintain and protect said property or possessions during construction. The cost of any protection shall be the responsibility of CONTRACTOR and shall be included in the Contract Price.
13.2	CONTRACTOR shall be responsible for any and all damage caused by or as a result of his work or through neglect of his workmen or subcontractor. Repairing of damaged property or work shall be done by the CONTRACTOR to the complete satisfaction of the OWNER and the CONSULTANT. The cost of all repairs shall be the full responsibility of the CONTRACTOR.
13.3	The CONTRACTOR shall be responsible for damages caused by or as a result of the Contract work to the grounds, walks, roads, trails, buildings to remain, walls, piping systems, electrical systems, telephone systems, cable systems, computer network systems, etc. The CONTRACTOR shall, at his own expense, have all repairs undertaken to restore any damages to the state of repair prior to said damage. All repair work shall be completed to the satisfaction of OWNER and the CONSULTANT.
13.4	The CONTRACTOR shall, at his own expense, construct, repair, replace, and maintain in service any utilities, facilities, or services (underground, overground, exterior, or interior) not designated for disconnection that are damaged, broken, or otherwise rendered inoperative during the course of the Contract work. The materials utilized by the CONTRACTOR in repairing, replacing, or maintaining said services shall be approved in writing by the CONSULTANT prior to use.
13.5	It shall be the responsibility of the CONTRACTOR to protect all property and possessions of the OWNER as well as the property and possessions of property owners adjacent to the project site from dirt, grime, dust, water, etc. during all phases of the Contract work. Water mist, temporary enclosures and other suitable methods shall be used to limit the spread of dust and dirt; water shall not be used where it may cause icing, flooding or transport of pollutants. The CONTRACTOR shall replace all property or possessions damaged during the Contract work.
13.6	The OWNER reserves the right to make or order emergency repairs as necessary to keep systems and/or equipment in operation and to ensure continuous use of and access to the OWNER's property and facilities. Said emergency repairs shall not void or limit the CONTRACTOR's guarantee nor relieve the CONTRACTOR of his responsibility during the guarantee or bonding period.
14.  UNDERGROUND UTILITY NOTIFICATION AND UTILITY DISCONNECTION
The Pennsylvania Underground Utility Line Protection Law (Act 287 of 1974, as amended); OSHA Standard 1926.651; the Federal Pipeline Safety Act of 1968; and the National Electrical Safety Code (ANSI C-2) require anyone who engages in any type of excavation or demolition to provide advance notice. In Pennsylvania, the Act requires notice to the Pennsylvania One Call System (dial 811 or 1-800-242-1776) not less than three (3) business days and not more than ten (10) business days prior to excavation or demolition, or as otherwise required by current law.
All CONTRACTORS, including SUBCONTRACTORS, shall make their own notifications. The Act states that the person doing the work shall make the notification. The CONTRACTOR shall be responsible for making all appropriate utility notifications prior to beginning any project excavations or demolition. The CONTRACTOR shall locate and identify all existing utilities within the construction area; notify affected utility companies at least 48 hours before starting work and comply with their requirements; disconnect and seal or cap off utility services affected by the work, including the capping of sanitary sewer laterals; and verify that utilities have been disconnected and capped before demolition begins. Existing utilities to remain shall be maintained in service and protected against damage.
15.  SITE SECURITY
The CONTRACTOR shall be responsible to secure the site from unwanted or accidental access as appropriate and/or necessary to prevent property damage, vandalism, theft, etc. In addition to the temporary construction fencing required by Section 015626 and any local municipal requirements for site fencing, the CONTRACTOR, with written authorization from the OWNER, may install additional fencing, surveillance cameras, etc. to protect his property and interest; and authorization from the OWNER for said security measure shall not be unreasonably withheld. The OWNER maintains no responsibility for CONTRACTOR'S property or interest, and shall allow the CONTRACTOR to undertake reasonable measures to secure and protect said interests. The OWNER shall have complete access to the property at all times, and the CONTRACTOR shall be responsible to provide the OWNER with any keys, codes, passwords, etc. as necessary to maintain access to their property. In all events, the CONTRACTOR shall be responsible for protection of property in accordance with all other provisions of the document including General Technical Specifications, Article 13, Protection of Property.
16.  GUARANTEE
In addition to any other herein stated warranties and/or guarantees, the CONTRACTOR shall guarantee and warrant for a period of three years from the date of Substantial Completion that all work performed under this Contract is free from defects in material and workmanship, and shall further guarantee and warrant for a period of three years from the date of Substantial Completion against failures and damage. This guarantee/warranty shall apply to the work performed under this Contract, including backfill settlement and site stabilization, and the CONTRACTOR shall not be held responsible for defects, failures, and damage caused by further deterioration of adjacent areas. Upon written notice from the OWNER, the CONTRACTOR shall respond and repair, and/or correct said conditions to full and proper working order in accordance with the Contract Documents. In the event that any portion of the Contract work fails to perform as intended during the guarantee period, the CONTRACTOR shall repair, replace, and/or correct the subject area without cost to the OWNER. The CONTRACTOR shall further provide, without cost to the OWNER, all labor, equipment, tools, and materials as required to replace, repair, and/or correct the defective area. All repairs, replacements, and corrections shall be made to the satisfaction of the OWNER.
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SECTION 011000 - SUMMARY
PART 1 - GENERAL
1.1	SUMMARY
A.	This Section includes the following:
1.	Work covered by the Contract Documents.
2.	Use of premises.
3.	Owner's access requirements.
4.	Specification formats and conventions.
1.2	WORK COVERED BY CONTRACT DOCUMENTS
A.	Project Identification: Demolition of the Fuchs Industrial Site – Project No. ISRP26.
1.	Project Location: 105 8th Street, Emlenton, PA 16373 (Fuchs Lubricants Co. Site).
B.	Owner: Oil Region Alliance of Business, Industry and Tourism, 217 Elm Street, Oil City, PA 16301.
1.	Owner's Representative: Debbie Sobina, Project Manager.
C.	Consultant: Moody and Associates, Inc., 180 Mercer Street, Suite A, Meadville, PA 16335; telephone 814-724-4970.
D.	The Work consists of the following, as shown on the Drawings (Sheets C000, C110 and C141 through C143) and as identified in the Pre-Demolition Hazardous Building Materials Survey (HBMS):
1.	Removal and disposal, prior to demolition, of the asbestos-containing materials, PCB light ballasts, universal wastes and other hazardous materials identified in the HBMS, in accordance with Sections 026610 and 028213.
2.	Cleanup of graphite dust throughout the building, using wet methods and/or vacuum systems, prior to demolition, in accordance with Section 026610.
3.	Disconnection, sealing and capping of all utility services, including sanitary sewer laterals.
4.	Demolition of the steel and block building designated as Building 1 on Drawing C110 (approximately 34,000 square feet of building footprint per the HBMS), including its contents, all foundations and concrete slabs, and offsite disposal of all debris.
5.	Backfilling of the building footprint with clean fill compacted to 95 percent, followed by 4 inches of topsoil, seed and mulch, and rough grading of all areas affected by demolition, as shown on Drawing C110.
6.	Installation, maintenance and removal of erosion and sedimentation controls, including compost filter socks, inlet filter bag protection and rock construction entrance, as shown on Drawings C110 and C141 through C143.
E.	The buildings designated "Buildings to Remain" on Drawing C110, existing walls, existing asphalt, and existing gravel areas are not part of the demolition Work and shall be protected.
F.	Project will be constructed under a single prime contract.
1.3	USE OF PREMISES
A.	General: Contractor shall have limited use of premises for construction operations as indicated on the Drawings by the limit of disturbance (LOD).
B.	Use of Site: Limit use of premises to areas within the limit of disturbance shown on Drawing C110. Do not disturb portions of the Project site beyond areas in which the Work is indicated.
1.	Owner Access: Allow for Owner access to the site when requested and coordinated in advance.
2.	Driveways and Entrances: Keep driveways and entrances serving premises clear and available to Owner, Owner's employees, and emergency vehicles at all times. Do not use these areas for parking or storage of materials.
a.	Schedule deliveries to minimize use of driveways and entrances.
b.	Schedule deliveries to minimize space and time requirements for storage of materials and equipment on-site.
3.	Allegheny River Trail: The Allegheny River Trail adjoins the north side of the Work. Conduct operations to ensure safe passage of people around the demolition area, as required by Drawing C110, Demolition Note 16.
C.	Protection of Structures to Remain: Protect the buildings to remain, existing walls, adjacent structures, and adjacent property from damage during demolition operations. Repair damage caused by construction operations. Notify adjacent owners of work that may affect their property, as required by Drawing C110, Demolition Note 5.
1.4	OWNER'S ACCESS REQUIREMENTS
A.	The Owner will not occupy the site during the Work. The Owner, the Consultant, and representatives of agencies having jurisdiction shall have access to the site at all times.
1.5	WORK RESTRICTIONS (DELETED)
1.6	SPECIFICATION FORMATS AND CONVENTIONS
A.	Specification Format: The Specifications are organized into Divisions and Sections using CSI/CSC's "MasterFormat" numbering system.
1.	Division 01: Sections in Division 01 govern the execution of the Work of all Sections in the Specifications.
B.	Specification Content: The Specifications use certain conventions for the style of language and the intended meaning of certain terms, words, and phrases when used in particular situations. These conventions are as follows:
1.	Abbreviated Language: Language used in the Specifications and other Contract Documents is abbreviated. Words and meanings shall be interpreted as appropriate. Words implied, but not stated, shall be inferred as the sense requires. Singular words shall be interpreted as plural, and plural words shall be interpreted as singular where applicable as the context of the Contract Documents indicates.
2.	Imperative mood and streamlined language are generally used in the Specifications. Requirements expressed in the imperative mood are to be performed by Contractor. Occasionally, the indicative or subjunctive mood may be used in the Section Text for clarity to describe responsibilities that must be fulfilled indirectly by Contractor or by others when so noted.
a.	The words "shall," "shall be," or "shall comply with," depending on the context, are implied where a colon (:) is used within a sentence or phrase.
PART 2 - PRODUCTS (Not Used)
PART 3 - EXECUTION (Not Used)
END OF SECTION 011000
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SUMMARY	011000 - 1
SECTION 012600 - CONTRACT MODIFICATION PROCEDURES
PART 1 - GENERAL
1.1	SUMMARY
A.	This Section specifies administrative and procedural requirements for handling and processing Contract modifications.
1.2	MINOR CHANGES IN THE WORK
A.	Consultant will issue supplemental instructions authorizing Minor Changes in the Work, not involving adjustment to the Contract Sum or the Contract Time, on AIA Document G710, "Architect's Supplemental Instructions."
1.3	PROPOSAL REQUESTS
A.	Owner-Initiated Proposal Requests: Consultant will issue a detailed description of proposed changes in the Work that may require adjustment to the Contract Sum or the Contract Time. If necessary, the description will include supplemental or revised Drawings and Specifications.
1.	Proposal Requests issued by Consultant are for information only. Do not consider them instructions either to stop work in progress or to execute the proposed change.
2.	Within time specified in Proposal Request after receipt of Proposal Request, submit a quotation estimating cost adjustments to the Contract Sum and the Contract Time necessary to execute the change.
a.	Include a list of quantities of products required or eliminated and unit costs, with total amount of purchases and credits to be made. If requested, furnish survey data to substantiate quantities.
b.	Indicate applicable taxes, delivery charges, equipment rental, and amounts of trade discounts.
c.	Include costs of labor and supervision directly attributable to the change.
d.	Include an updated Contractor's Construction Schedule that indicates the effect of the change, including, but not limited to, changes in activity duration, start and finish times, and activity relationship. Use available total float before requesting an extension of the Contract Time.
B.	Contractor-Initiated Proposals: If latent or unforeseen conditions require modifications to the Contract, Contractor may propose changes by submitting a request for a change to Consultant.
1.	Include a statement outlining reasons for the change and the effect of the change on the Work. Provide a complete description of the proposed change. Indicate the effect of the proposed change on the Contract Sum and the Contract Time.
2.	Include a list of quantities of products required or eliminated and unit costs, with total amount of purchases and credits to be made. If requested, furnish survey data to substantiate quantities.
3.	Indicate applicable taxes, delivery charges, equipment rental, and amounts of trade discounts.
4.	Include costs of labor and supervision directly attributable to the change.
5.	Include an updated Contractor's Construction Schedule that indicates the effect of the change, including, but not limited to, changes in activity duration, start and finish times, and activity relationship. Use available total float before requesting an extension of the Contract Time.
6.	Comply with requirements in Division 01 Section "Product Requirements" if the proposed change requires substitution of one product or system for product or system specified.
C.	Proposal Request Form: Use AIA Document G709 for Proposal Requests or Contractor's company form.
1.4	ALLOWANCES
A.	Allowance Adjustment: To adjust allowance amounts, base each Change Order proposal on the difference between purchase amount and the allowance, multiplied by final measurement of work-in-place. If applicable, include reasonable allowances for cutting losses, tolerances, mixing wastes, normal product imperfections, and similar margins.
1.	Include installation costs in purchase amount only where indicated as part of the allowance.
2.	If requested, prepare explanation and documentation to substantiate distribution of overhead costs and other margins claimed.
3.	Submit substantiation of a change in scope of work, if any, claimed in Change Orders related to unit-cost allowances.
4.	Owner reserves the right to establish the quantity of work-in-place by independent quantity survey, measure, or count.
B.	Submit claims for increased costs because of a change in scope or nature of the allowance described in the Contract Documents, whether for the Purchase Order amount or Contractor's handling, labor, installation, overhead, and profit. Submit claims within 21 days of receipt of the Change Order or Construction Change Directive authorizing work to proceed. Owner will reject claims submitted later than 21 days after such authorization.
1.	Do not include Contractor's or subcontractor's indirect expense in the Change Order cost amount unless it is clearly shown that the nature or extent of work has changed from what could have been foreseen from information in the Contract Documents.
2.	No change to Contractor's indirect expense is permitted for selection of higher- or lower-priced materials or systems of the same scope and nature as originally indicated.
1.5	CHANGE ORDER PROCEDURES
A.	On Owner's approval of a Proposal Request, Consultant will issue a Change Order for signatures of Owner and Contractor on AIA Document G701.
1.6	CONSTRUCTION CHANGE DIRECTIVE
A.	Construction Change Directive: Consultant may issue a Construction Change Directive on AIA Document G714. Construction Change Directive instructs Contractor to proceed with a change in the Work, for subsequent inclusion in a Change Order.
1.	Construction Change Directive contains a complete description of change in the Work. It also designates method to be followed to determine change in the Contract Sum or the Contract Time.
B.	Documentation: Maintain detailed records on a time and material basis of work required by the Construction Change Directive.
1.	After completion of change, submit an itemized account and supporting data necessary to substantiate cost and time adjustments to the Contract.
PART 2 - PRODUCTS (Not Used)
PART 3 - EXECUTION (Not Used)
END OF SECTION 012600
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CONTRACT MODIFICATION PROCEDURES	012600 - 1
SECTION 012900 - PAYMENT PROCEDURES
PART 1 - GENERAL
1.1	SUMMARY
A.	This Section specifies administrative and procedural requirements necessary to prepare and process Applications for Payment.
1.2	SCHEDULE OF VALUES
A.	Coordination: Coordinate preparation of the Schedule of Values with preparation of Contractor's Construction Schedule. Cost-loaded CPM Schedule may serve to satisfy requirements for the Schedule of Values.
1.	Correlate line items in the Schedule of Values with other required administrative forms and schedules, including Application for Payment forms with Continuation Sheets, Submittals Schedule and Contractor's Construction Schedule.
2.	Submit the Schedule of Values to Consultant at earliest possible date but no later than seven days before the date scheduled for submittal of initial Applications for Payment.
3.	Subschedules: Where the Work is separated into phases requiring separately phased payments, provide subschedules showing values correlated with each phase of payment.
B.	Format and Content: Use the Project Manual table of contents as a guide to establish line items for the Schedule of Values. Provide at least one line item for each Specification Section. Provide separate line items for asbestos abatement, regulated waste removal and disposal, graphite dust cleanup, building demolition, backfill and site restoration, and erosion and sedimentation controls.
1.	Identification: Include the following Project identification on the Schedule of Values:
a.	Project name and location.
b.	Name of Consultant.
c.	Consultant's project number.
d.	Contractor's name and address.
e.	Date of submittal.
2.	Submit draft of AIA Document G703 Continuation Sheets.
3.	Provide a breakdown of the Contract Sum in enough detail to facilitate continued evaluation of Applications for Payment and progress reports. Coordinate with the Project Manual table of contents. Provide several line items for principal subcontract amounts, where appropriate.
4.	Round amounts to nearest whole dollar; total shall equal the Contract Sum.
5.	Provide a separate line item in the Schedule of Values for each part of the Work where Applications for Payment may include materials or equipment purchased or fabricated and stored, but not yet installed.
6.	Provide separate line items in the Schedule of Values for initial cost of materials, for each subsequent stage of completion, and for total installed value of that part of the Work.
7.	Allowances: Provide a separate line item in the Schedule of Values for each allowance. Show line-item value of unit-cost allowances, as a product of the unit cost, multiplied by measured quantity. Use information indicated in the Contract Documents to determine quantities.
8.	Each item in the Schedule of Values and Applications for Payment shall be complete. Include total cost and proportionate share of general overhead and profit for each item.
9.	Temporary facilities and other major cost items that are not direct cost of actual work-in-place may be shown either as separate line items in the Schedule of Values or distributed as general overhead expense, at Contractor's option.
10.	Schedule Updating: Update and resubmit the Schedule of Values before the next Applications for Payment when Change Orders or Construction Change Directives result in a change in the Contract Sum.
1.3	APPLICATIONS FOR PAYMENT
A.	Each Application for Payment shall be consistent with previous applications and payments as certified by Consultant and paid for by Owner.
1.	Initial Application for Payment, Application for Payment at time of Substantial Completion, and final Application for Payment involve additional requirements.
B.	Payment Application Times: The date for each progress payment is indicated in the Agreement between Owner and Contractor. The period of construction Work covered by each Application for Payment is the period indicated in the Agreement.
C.	Payment Application Times: Progress payments shall be submitted to Consultant by the 16th day of the month for work completed from the 1st through the 15th day of the month and on the 1st day of the month for work completed from the 16th through the last day of the month.
D.	Payment Application Forms: Use AIA Document G702 and AIA Document G703 Continuation Sheets as form for Applications for Payment. Provide detailed Pennsylvania Prevailing Wage forms for all personnel who worked on the project during the invoice period.
E.	Application Preparation: Complete every entry on form. Notarize and execute by a person authorized to sign legal documents on behalf of Contractor. Consultant will return incomplete applications without action.
1.	Entries shall match data on the Schedule of Values and Contractor's Construction Schedule. Use updated schedules if revisions were made.
2.	Include amounts of Change Orders and Construction Change Directives issued before last day of construction period covered by application.
F.	Transmittal: Submit 3 signed and notarized original copies of each Application for Payment to Consultant by a method ensuring receipt. One copy shall include waivers of lien and similar attachments if required.
1.	Transmit each copy with a transmittal form listing attachments and recording appropriate information about application.
G.	Initial Application for Payment: Administrative actions and submittals that must precede or coincide with submittal of first Application for Payment include the following:
1.	List of subcontractors.
2.	Schedule of Values.
3.	Contractor's Construction Schedule (preliminary if not final).
4.	Schedule of unit prices.
5.	Submittals Schedule (preliminary if not final).
6.	List of Contractor's staff assignments.
7.	List of Contractor's principal consultants.
8.	Copies of demolition permits.
9.	Copies of authorizations and licenses from authorities having jurisdiction for performance of the Work, including the PADEP Asbestos Abatement and Demolition/Renovation Notification.
10.	Initial progress report.
11.	Report of preconstruction conference.
12.	Certificates of insurance and insurance policies.
H.	Application for Payment at Substantial Completion: After issuing the Certificate of Substantial Completion, submit an Application for Payment showing 100 percent completion for portion of the Work claimed as substantially complete.
1.	Include documentation supporting claim that the Work is substantially complete and a statement showing an accounting of changes to the Contract Sum.
2.	This application shall reflect Certificates of Partial Substantial Completion issued previously for designated portions of the Work.
I.	Final Payment Application: Submit final Application for Payment with releases and supporting documentation not previously submitted and accepted, including, but not limited, to the following:
1.	Evidence of completion of Project closeout requirements.
2.	Insurance certificates for products and completed operations where required and proof that taxes, fees, and similar obligations were paid.
3.	Updated final statement, accounting for final changes to the Contract Sum.
4.	AIA Document G706, "Contractor's Affidavit of Payment of Debts and Claims."
5.	AIA Document G706A, "Contractor's Affidavit of Release of Liens."
6.	AIA Document G707, "Consent of Surety to Final Payment."
7.	Evidence that claims have been settled.
8.	Waste manifests, waste shipment records and disposal facility receipts required by Sections 026610 and 028213.
PART 2 - PRODUCTS (Not Used)
PART 3 - EXECUTION (Not Used)
END OF SECTION 012900
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PAYMENT PROCEDURES	012900 - 1
SECTION 013523.10 - LEAD EXPOSURE SAFETY PRECAUTIONS & PROTECTIONS
PART 1 - GENERAL
1.1	SUMMARY
A.	Painted surfaces and other building components at the Project site may contain lead. The Hazardous Building Materials Survey (HBMS) did not include a lead-based paint inspection, and no lead sampling results are provided by the OWNER. Unless adequate and appropriate sampling and testing is undertaken by the CONTRACTOR to verify painted surfaces are not lead containing, all work activities involving cutting, torching, grinding, and other processes that could result in dispersing lead particulate into the air shall be considered as an occupational exposure to lead. The CONTRACTOR shall be responsible to undertake the work in accordance with all applicable laws, rules, regulations, etc., including OSHA 29 CFR 1926.62; and prior to commencement of the Work, the CONTRACTOR shall provide to the CONSULTANT a written work plan outlining the procedures and processes that will be implemented to ensure worker safety, environmental protection, and regulatory compliance.
B.	This section applies to all construction work where an employee/worker may be occupationally exposed to lead. This includes but is not limited to the following: Demolition or salvage of structures where lead or material containing lead are present, transportation, disposal, storage, or containment of lead or materials containing lead on the site or location at which construction activities are performed.
C.	The CONTRACTOR shall perform work tasks using appropriate precautions and protections in accordance with all applicable safety standards, laws, rules, regulations, etc.; and the precautions and protections may include but not be limited to respiratory protection, personal protective clothing, change area, hand washing facilities, blood sampling, and training regarding: hazard communication, use of respirators, safety training and education, and mechanical ventilation.
PART 2 - PRODUCTS
2.1	GENERAL
A.	Provide material, equipment, tools, and devices required to complete the lead work safely.
PART 3 - EXECUTION
3.1	RESPIRATOR
A.	The CONTRACTOR shall provide to all workers the appropriate respirator for the work task.
B.	The CONTRACTOR shall provide to all workers full face piece respirator instead of a half mask respirator for protection against lead aerosols that may cause eye or skin irritation.
C.	The CONTRACTOR shall provide HEPA filters for powered and non-powered air-purifying respirators.
3.2	PROTECTIVE WORK CLOTHING AND EQUIPMENT
A.	The CONTRACTOR shall provide appropriate protective work clothing and equipment that prevents contamination of the workers' garments such as, but not limited to: coveralls or similar full-body work clothing, gloves, hats, shoes or disposable shoe coverlets, face shields, vented goggles, or other appropriate protective equipment.
B.	The protective clothing shall be removed at the completion of a work shift only in change areas provided for that purpose.
3.3	HYGIENE FACILITIES AND PRACTICES
A.	No food or beverage shall be present or consumed and tobacco products are not to be present or used in areas exposed to lead.
3.4	CHANGE AREAS
A.	The CONTRACTOR shall provide clean change area for workers exposed to lead.
B.	The CONTRACTOR shall assure that change areas are equipped with separate storage facilities for protective work clothing and equipment and for street clothes which prevent cross-contamination.
C.	The CONTRACTOR shall assure that workers do not leave the workplace wearing any protective clothing or equipment that is required to be worn during the work shift.
3.5	EATING FACILITIES
A.	Eating facilities/areas for workers shall be as free as practicable from lead contamination and readily accessible to workers.
B.	All workers shall wash their hands and face prior to eating, drinking, smoking, or applying cosmetics.
C.	Workers shall not enter eating facilities/areas with protective work clothing or equipment unless surface lead dust has been removed by vacuuming, downdraft booth, or other cleaning method that limits dispersion of lead dust.
END OF SECTION 013523.10
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LEAD EXPOSURE SAFETY PRECAUTIONS & PROTECTIONS	013523.10 - 1
SECTION 015626 - TEMPORARY CONSTRUCTION FENCING
PART 1 - GENERAL
1.1	SUMMARY
A.	This section includes the temporary construction fencing and related components.
B.	Install temporary construction fencing around the work and staging areas, at or within the limit of disturbance shown on Drawing C110, as required to secure the work and to ensure safe passage of people around the demolition area, in accordance with Drawing C110, Demolition Notes 3 and 16; Section 011000; and General Technical Specifications, Article 15. At a minimum, provide temporary chain link fencing between Building 1 and the Allegheny River Trail at the location shown on Drawing C110. Fencing shall not obstruct the Allegheny River Trail except with the permission of the proper authorities.
1.2	SUBMITTALS
A.	Site plan showing layout of fence location with dimensions, location of gates and opening size, cleared area, elevation of fence, gates, footings, and details of attachments.
B.	When required by the CONSULTANT, provide material samples of chain link fabric, framework, and fittings.
1.3	QUALITY ASSURANCE
A.	The company installing the temporary fencing shall have demonstrated successful experience installing similar projects and products in accordance with ASTM F567 and have at least 5 years experience in accordance with the provisions of this section.
PART 2 - PRODUCTS
2.1	TEMPORARY FENCE PANEL SYSTEM
A.	Panel framework to be manufactured from galvanized tubing with a minimum outside diameter (OD) of 1.375 inches. Panel framework to be in good condition, free of defects and damage that demonstrates possible structural failure.
B.	Panels to be a minimum of 8' tall and not greater than 12' in width.
C.	Panels to be constructed from galvanized welded or woven wire fabric. Wire strand to be not less than 11½ gauge. Openings in wire fabric not to be greater than 2" wide or 2" tall.
D.	Panels to be anchored with use of weighted stands.
E.	Stands shall be weighted to a minimum of 50 lbs. so as to prevent panels from falling over under above normal conditions. Stands to be free from defect and in good condition.
F.	Weights may be a sandbag or other device in good condition and free from defects that cause sand to spill out.
2.2	SWING GATES
A.	Swing gates shall be of galvanized steel pipe welded fabrication in compliance with ASTM F900. Gate frame members to be minimum of 1.375 inch O.D. free of defects. Frame members spaced no greater than 8 ft. (2440 mm) apart vertically and horizontally. Welded joints shall be protected by applying zinc-rich paint in accordance with ASTM Practice A780. The gates shall include a positive locking gate latch, galvanized malleable iron or heavy gauge pressed steel post and frame hinges, and lockable drop bar and gate holdbacks when double gates are utilized.
2.3	SLIDE GATES
A.	Slide gate frames shall be fabricated by welding, vertical and horizontal members installed no greater than 8 ft. apart. Welded joints shall be protected by applying zinc-rich paint in accordance with ASTM Practice A780. Gates shall be designed to open or close by applying an initial pull force no greater than 40 lbs. (18.14 kg). The gates shall include match infill of panels, positive locking pressed steel latch.
PART 3 - EXECUTION
3.1	INSTALLATION
A.	Install temporary fence per ASTM F3342 Standard Guide for Temporary Fence Applications for Construction Sites.
B.	Panels shall be anchored to weighted stands so as to not move excessively under normal wind conditions.
C.	Install swing gates and gateposts in compliance with ASTM F567.
D.	Install according to manufacturer's instructions and in accordance with ASTM F567.
3.2	MAINTENANCE
A.	Fence shall be maintained in good condition and shall not be allowed to be in disrepair. All breaks or tears in the fence fabric shall be repaired immediately.
B.	All posts shall be maintained plumb and in straight and uniform alignment. All fallen or dislocated posts shall be reset immediately.
C.	The fencing shall be maintained in such a manner to protect Work from damage and protect the safety of the general public.
D.	Remove temporary fencing at completion of the Work, unless otherwise directed by the OWNER.
END OF SECTION 015626
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TEMPORARY CONSTRUCTION FENCING	015626 - 1
SECTION 017700 - CLOSEOUT PROCEDURES
PART 1 - GENERAL
1.1	SUMMARY
A.	This Section includes administrative and procedural requirements for contract closeout, including, but not limited to, the following:
1.	Site inspection procedures.
2.	Final site cleaning.
B.	See Division 01 Section "Payment Procedures" for requirements for Applications for Payment for Substantial and Final Completion.
1.2	SUBSTANTIAL COMPLETION
A.	Preliminary Procedures: Before requesting inspection for determining date of Substantial Completion, complete the following. List items below that are incomplete in request.
1.	Prepare a list of items to be completed and corrected (punch list), the value of items on the list, and reasons why the Work is not complete.
2.	Advise Owner of pending insurance changeover requirements.
3.	Submit specific warranties, workmanship bonds, maintenance service agreements, final certifications, and similar documents.
4.	Submit asbestos project close-out documentation required by Section 028213, including Monitoring Firm clearance results and signed Waste Shipment Records, and regulated waste disposal documentation required by Section 026610.
5.	Submit compaction test results required by General Technical Specifications, Article 12.
6.	Obtain and submit releases permitting Owner unrestricted use of the Work and access to services and utilities, including utility disconnection confirmations.
7.	Terminate and remove temporary facilities from Project site, along with construction tools and similar elements.
B.	Inspection: Submit a written request for inspection for Substantial Completion. On receipt of request, Consultant will either proceed with inspection or notify Contractor of unfulfilled requirements. Consultant will prepare the Certificate of Substantial Completion after inspection or will notify Contractor of items, either on Contractor's list or additional items identified by Consultant, that must be completed or corrected before certificate will be issued.
1.	Reinspection: Request reinspection when the Work identified in previous inspections as incomplete is completed or corrected.
2.	Results of completed inspection will form the basis of requirements for Final Completion.
1.3	FINAL COMPLETION
A.	Preliminary Procedures: Before requesting final inspection for determining date of Final Completion, complete the following:
1.	Submit a final Application for Payment according to Division 01 Section "Payment Procedures."
2.	Submit certified copy of Consultant's Substantial Completion inspection list of items to be completed or corrected (punch list), endorsed and dated by Consultant. The certified copy of the list shall state that each item has been completed or otherwise resolved for acceptance.
3.	Submit evidence of final, continuing insurance coverage complying with insurance requirements.
4.	Demonstrate that permanent stabilization (minimum uniform, perennial 70% vegetative cover) has been achieved and that temporary E&S BMPs have been removed, as required by the E&S notes on the Drawings.
B.	Inspection: Submit a written request for final inspection for acceptance. On receipt of request, Consultant will either proceed with inspection or notify Contractor of unfulfilled requirements. Consultant will prepare a final Certificate for Payment after inspection or will notify Contractor of construction that must be completed or corrected before certificate will be issued.
1.	Reinspection: Request reinspection when the Work identified in previous inspections as incomplete is completed or corrected.
1.4	LIST OF INCOMPLETE ITEMS (PUNCH LIST)
A.	Preparation: Submit three copies of list. Include name and identification of each area affected by construction operations for incomplete items and items needing correction including, if necessary, areas disturbed by Contractor that are outside the limits of construction.
PART 2 - PRODUCTS (DELETED)
PART 3 - EXECUTION
3.1	FINAL CLEANING
A.	General: Provide final cleaning. Conduct cleaning and waste-removal operations to comply with local laws and ordinances and Federal and local environmental and antipollution regulations.
B.	Complete the following cleaning operations before requesting inspection for certification of Substantial Completion for entire Project or for a portion of Project:
1.	Clean Project site, yard, and grounds, in areas disturbed by construction activities, including landscape development areas, of rubbish, waste material, litter, and other foreign substances.
2.	Sweep paved areas broom clean. Remove petrochemical spills, stains, and other foreign deposits. Remove sediment tracked onto roadways, sidewalks and the Allegheny River Trail.
3.	Clean adjacent structures and improvements of dust, dirt, and debris caused by demolition operations, and return adjacent areas to the condition existing before the start of demolition.
4.	Rake grounds that are neither planted nor paved to a smooth, even-textured surface.
5.	Remove tools, construction equipment, machinery, and surplus material from Project site.
6.	Leave Project site clean, graded, topsoiled, seeded and mulched as shown on the Drawings.
C.	Comply with safety standards for cleaning. Do not burn waste materials. Do not bury debris or excess materials on Owner's property. Do not discharge volatile, harmful, or dangerous materials into drainage systems. Remove waste materials from Project site and dispose of lawfully.
END OF SECTION 017700
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CLOSEOUT PROCEDURES	017700 - 1
SECTION 026610 - REGULATED WASTE DISPOSAL
PART 1 - GENERAL
1.1	DESCRIPTION OF WORK
The work includes the removal and disposal of hazardous and non-hazardous Regulated Waste materials and graphite dust specified herein and the incidental procedures required. The CONTRACTOR shall furnish all labor, materials, services, insurance and equipment required for the removal and disposal of hazardous and non-hazardous Regulated Waste materials in accordance with the guidelines or regulations of the responsible state agency, the local agency, the United States Environmental Protection Agency (EPA) and/or the Occupational Safety and Health Administration (OSHA). All such materials shall be removed prior to demolition (Drawing C110, Demolition Notes 24 and 25). The Regulated Waste disposal work at the project site includes, but is not necessarily limited to the following:
A.	All preparation of the work areas and areas outside the work areas prior to beginning work.
B.	Removal and disposal of all Regulated Waste identified in the Hazardous Building Materials Survey (HBMS) or encountered at the Site during the process of the work, and any other Regulated Wastes generated by this project, except for asbestos waste. Hazardous and non-hazardous Regulated Waste requiring removal and disposal includes, but is not necessarily limited to, the following materials identified in the HBMS:
	Material (HBMS Sections 3.4 and 3.5)
	Location
	Estimated Count/Qty

	Universal Waste – Lamps
	
	

	Fluorescent light tubes
	Throughout
	351

	High intensity discharge (HID) bulbs
	Throughout
	37

	Compact fluorescent light (CFL) bulbs
	Throughout
	22

	Emergency lights
	Throughout
	6

	Universal Waste – Suspected Mercury-Containing
	
	

	Thermostats; potential mercury switches
	2nd floor offices
	4

	PCB Wastes
	
	

	Fluorescent light ballasts (assumed PCB-containing unless labeled "No PCBs")
	Throughout
	133

	Radioactive
	
	

	Smoke detectors (potential ionization type, americium-241)
	Throughout
	5

	Paints and Related Products
	
	

	Acrylic paint, 16 oz bottles
	Entrance stairwell
	18



The HBMS reports that no oil-filled electrical equipment, refrigerant-containing AC units, hydraulic systems, hydraulic oil, medical/bio-hazardous wastes, or cleaning products were observed. Any such materials, and any tanks, drums, batteries, fire extinguishers or other containers of oil, petroleum products, solvents, coatings, acids, or other liquid or solid contents, whether labeled or unlabeled, encountered during the Work shall be removed and disposed of under this Section.

ALL QUANTITIES ARE ESTIMATES. SEE THE HAZARDOUS BUILDING MATERIALS SURVEY FOR SPECIFIC DETAILS REGARDING THE MATERIALS LISTED ABOVE. EXISTING CONDITIONS TO BE VERIFIED BY THE CONTRACTOR.

C.	Graphite Dust: The building was historically used for the manufacture of lubricants, including graphite-based lubricants, and the HBMS reports loose graphite dust on most surfaces within the building. Toxicity Characteristic Leaching Procedure (TCLP) analysis of a composite graphite dust sample found all RCRA metals, copper, nickel and zinc below the TCLP limits; the graphite dust is therefore characterized as non-hazardous waste. The CONTRACTOR shall clean up graphite dust to the maximum extent practical prior to demolition, using wet methods and/or vacuum systems to minimize dust generation, and shall dispose of it as non-hazardous waste at an approved facility. Graphite dust presents respiratory, eye and skin hazards and an explosion hazard in dust/air mixtures, and reacts with strong oxidizing agents. All graphite dust work shall comply with OSHA standards, and ignition sources shall be controlled in areas where graphite dust is present.
D.	Complete cleaning and decontamination of all work areas and contents thereof.
E.	The HBMS did not include a lead-based paint inspection. Painted surfaces shall be presumed to contain lead unless the CONTRACTOR's testing demonstrates otherwise. The CONTRACTOR shall be responsible for compliance with all requirements of the Pennsylvania Department of Labor & Industry and the Occupational Safety and Health Administration (OSHA) regulations regarding lead protection for workers. Evidence of worker training, such as lead awareness training, shall be provided prior to the onset of work. See also Section 013523.10.
F.	An asbestos containing material (ACM) inspection was performed and ACM was found in the areas indicated in the HBMS. If work is conducted prior to or during completion of asbestos abatement, the CONTRACTOR shall be responsible for compliance with all requirements of the Pennsylvania Department of Labor & Industry and the Occupational Safety and Health Administration (OSHA) regulations regarding asbestos protection for workers, and CONTRACTOR shall comply with all applicable requirements set forth in Section 028213, Asbestos Abatement.
G.	The CONTRACTOR is solely responsible for meeting all Local, State and Federal requirements for the protection of personnel and the environment during remediation activities. Testing of demolition debris to determine its disposition as hazardous waste and its proper disposal is the sole responsibility of the CONTRACTOR. Results of such tests shall be provided to the OWNER prior to removal of said material from the site, and waste manifests shall be provided to the OWNER after waste is removed from the site.
H.	Thermostats, smoke detectors, lamps and ballasts shall be inspected individually upon removal. Ballasts not labeled "No PCBs" shall be bulked together in a proper container and disposed of as PCB-containing waste. Items found to contain mercury or americium-241 shall be segregated from other waste. All PCB, universal and hazardous wastes shall be segregated by type, and no mixing of these materials shall occur.
1.2	TERMINOLOGY
A.	Authorized Visitor: The OWNER's representative, the CONSULTANT, or a representative of any regulatory or other agency having jurisdiction over the project.
B.	HEPA Filter Equipment: High-efficiency particulate air filtered vacuuming equipment with a filter system capable of collecting and retaining particulates. Filters shall be of 99.97 percent efficiency for retaining particulates of 0.3 microns or larger.
C.	Owner's Representative: Person designated in the Contract as authorized individual (or his designee) to represent and mediate for the OWNER in administration of the Contract.
D.	Project Monitor: One or more individuals employed by the OWNER to inspect the Work and/or to act as clerk of the works to the extent required by the OWNER. The OWNER shall notify the CONTRACTOR in writing of the appointment of such Project Monitor(s).
E.	Regulated Waste: Solid Wastes that must be handled, stored, and disposed of according to established regulations outside of conventional non-hazardous waste disposal, inclusive of RCRA Hazardous Waste and Non-Hazardous Waste.
F.	Wet Cleaning: The process of eliminating contamination from building surfaces and objects by using cloths, mops, or other cleaning tools which have been dampened with water, and by afterwards disposing of these cleaning tools as contaminated waste.
1.3	CONFORMANCE TO REGULATORY REQUIREMENTS
A.	In addition to detailed requirements of this specification, the CONTRACTOR shall comply with laws, ordinances, rules, and regulations of federal, state, regional, and local authorities regarding handling, storing, transporting and disposing of all waste materials, including 40 CFR Part 273 (universal waste) and 40 CFR Part 761 (PCBs).
B.	Submit matters of interpretation of standards to the appropriate administrative agency for resolution before starting the work, with copy sent to the Owner's Representative. Where the requirements of this specification and referenced documents vary, the most stringent requirement shall apply.
1.4	BUILDING PROTECTION
A.	The waste removals must be conducted in a manner that does not cause releases or undue damage to the existing structure prior to demolition.
1.5	SUBMITTALS
A.	Waste Disposal Plan: Submit a detailed plan of the work procedures to be used in the removal of waste materials and graphite dust. Plan shall be approved prior to start of the work.
B.	Testing Laboratory: Submit the name, address, telephone number, and copy of the PADEP Certified Laboratory License of the testing laboratory selected for analysis of any samples collected as part of the work. Copies of analytical results of any samples collected must be submitted upon receipt.
C.	Disposal: Must comply with 40 CFR Parts 239 through 282.
1.	Submit evidence that all required approvals for transport and disposal of all wastes have been obtained.
2.	Submit copies from the operator of the disposal site that the waste has been received, within 30 days of removal, specifying quantities and dates of delivery.
D.	Employee Qualification: Submit documentation indicating that all employees have appropriate Safety Training for the handling of Hazardous Waste.
E.	Respirator Program: Submit a copy of the company's written respirator program in compliance with OSHA regulations. The CONTRACTOR shall have a copy of his written respirator program available on the job site at all times.
1.6	PERSONNEL PROTECTION
A.	Provide workers with personally issued and marked respiratory equipment in accordance with Article 2.2, Equipment. Where respirators with disposable filters are employed, provide sufficient filters for replacement as required by the worker or applicable regulation.
B.	Provide workers with sufficient sets of protective full-body clothing. Such clothing shall consist of full-body overalls and headgear, gloves and foot coverings. Provide hard hats as required by applicable safety regulations. If work is being conducted in conjunction with asbestos remediation activities or if work will require disturbance of any asbestos containing materials, CONTRACTOR shall comply with all PPE Requirements and decontamination procedures set forth in Section 028213, Asbestos Abatement.
C.	Provide authorized visitors with suitable protective clothing, headgear, gloves, eye protection and footwear, as described herein, whenever they are required to enter the work area.
PART 2 - PRODUCTS
2.1	MATERIALS
A.	Containers: Containers shall be suitable to receive and retain any waste materials until disposed of at an approved site. The containers shall be labeled in accordance with all applicable federal, state, and local laws and regulations according to the waste.
2.2	EQUIPMENT
A.	Vacuums: All vacuums shall be equipped with a high-efficiency particulate air (HEPA) filtration system. Vacuums used for graphite dust shall be suitable for use with combustible dust.
B.	Respirators: All respirators shall be equipped with NIOSH-approved P100 respirator filters.
PART 3 - EXECUTION
3.1	PREPARATION OF WORK AREAS
A.	If electric power equipment is required, provide temporary power sources and equipment per applicable electrical code requirements and ground-fault interrupter circuits as power source for electrical equipment.
B.	Graphite dust and other dust-generating debris shall be thoroughly wetted or collected with HEPA-filtered vacuum systems prior to removal, and the method of removal shall not result in generation of airborne dust.
C.	Maintain emergency and fire exits from the work areas, or establish alternative exits satisfactory to the applicable fire officials.
D.	After preparation of the work areas, remove Regulated Wastes as required.
3.2	CLEANUP
A.	Remove visible accumulations of broken or spilled Regulated Wastes and graphite dust.
B.	Clean all surfaces in the work area and any other contaminated areas with water and/or with HEPA-filtered vacuum equipment.
3.3	DISPOSAL
A.	Submit documentation regarding disposal to OWNER within 30 days of removal.
B.	Procedure for hauling and disposal shall comply with federal, state, regional, and local regulations and standards. Workers shall wear appropriate respirators and personal protective equipment when handling graphite dust and contaminated debris at the jobsite.
END OF SECTION 026610
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SECTION 028213 - ASBESTOS ABATEMENT
PART 1 - GENERAL
1.1	STIPULATIONS
A.	The procedures specified herein are guidelines for minimum performance. The CONTRACTOR is responsible for his own methods of operations and conformance to regulatory codes, rules and guidelines. The CONTRACTOR is required to obtain all permits, licenses, and approvals to perform the work, including any rights to use patented systems.
1.2	SCOPE OF WORK
A.	The Scope of work for this project covers the supplying of all labor, tools, material, equipment, services and appurtenances to accomplish the work specified and indicated in the Contract Documents. The work shall be performed to the complete satisfaction of the OWNER in accordance with the current PA DEP, EPA and OSHA regulations, State Labor and Industry regulations and any other applicable State, Local and Government regulations.
B.	CONTRACTOR shall submit an Action Plan which describes specifically how abatement work is to be completed. At a minimum the Action Plan shall address work area preparation, work practices, decon location, estimated completion dates, respiratory protection and disposal; approval of the Action Plan must be obtained through the OWNER prior to the start of work. Procedures outlined in the Action Plan must be followed throughout the abatement phase. Any changes in Action Plan must obtain prior approval from the OWNER.
C.	The work under this project includes, but is not limited to, the removal and disposal of all asbestos-containing materials (ACM) identified in the Hazardous Building Materials Survey (HBMS), summarized below. All ACM identified in the HBMS is non-friable (EPA NESHAP Category I or Category II). Quantities identified in the HBMS are estimates. The CONTRACTOR shall verify all quantities and locations in the field prior to bidding.
	HA ID
	Material
	Location
	Asbestos Content
	Category
	Estimated Amount

	A
	Red 9x9 floor tile (black mastic: no asbestos detected)
	Front entrance stairwell entrance
	Floor tile: 5% Chrysotile
	Cat I
	72 square feet

	C
	Brown mastic under white/grey 9x9 tile (gray floor tile: no asbestos detected)
	Front entrance stairwell landing
	Brown mastic: 2% Chrysotile
	Cat I
	45 square feet

	F
	Black and white window mastic
	2nd floor wood paneled office window
	5% Chrysotile
	Cat II
	104 linear feet

	K
	Black roof flashing seal
	Northern portion of metal roof
	2% Chrysotile
	Cat II
	8 square feet

	V
	Window mastic
	Reject area eastern window
	2% Chrysotile
	Cat II
	126 linear feet

	CC
	Ceiling board
	Furnace room
	20% Chrysotile
	Cat II
	112 square feet



D.	All ACM identified in the HBMS shall be removed from the structure prior to demolition, in accordance with Drawing C110, Demolition Note 23, the recommendations of the HBMS, and 40 CFR Part 61, Subpart M. Existing and future damage may cause these materials to become Regulated Asbestos-Containing Material (RACM); the CONTRACTOR shall handle all ACM in a manner that does not render it RACM or release asbestos to the air.
E.	The HBMS notes that enclosed wall cavities, areas above fixed ceilings, sub floors, pipe chases and risers, and the interior of HVAC equipment and ductwork were not fully accessible. If any previously unidentified suspect material is encountered during the work, the work in that area shall stop, the material shall be reported to the CONSULTANT immediately and shall be assumed to contain asbestos until laboratory analysis refutes or confirms that assumption.
1.3	CONTROL OF WORK
A.	All work which does not conform to the requirements of the Contract, Drawings and Specifications will be considered unacceptable.
B.	Unacceptable work, whether the result of poor workmanship, use of defective materials, damage through carelessness, or any other cause found to exist prior to the final acceptance of the work, shall be corrected immediately and replaced in an acceptable manner.
C.	If the OWNER finds the materials furnished, work performed or the finished product not within reasonably close conformity with the Drawings and Specifications and have resulted in an unacceptable finished product, the affected work or material shall be removed and replaced or otherwise corrected by and at the expense of the CONTRACTOR.
D.	The term "reasonably close conformity" shall not be construed as waiving the CONTRACTOR's responsibility to complete the work in accordance with the Drawings, Contract, and Specifications. The term shall not be construed as waiving the OWNER's right to insist on strict compliance with the requirements of the Contract, Drawings, and Specifications during the CONTRACTOR's prosecution of the work, when in the OWNER's opinion and judgement such compliance is essential to provide an acceptable finished work.
1.4	QUALITY ASSURANCE
A.	Asbestos Monitoring Firm
1.	The CONTRACTOR shall contract for a Quality Assurance Consultant Project Monitor hereafter referred to as "Monitoring Firm" which specializes in performing air sampling, project monitoring and inspections on asbestos abatement projects. The testing laboratory shall as a minimum be accredited for PCM asbestos air analysis and NVLAP for asbestos bulk analysis.
2.	The Monitoring Firm will be responsible for certifying the project was completed in accordance with all Federal, State, and Local asbestos standards and regulations.
3.	The Monitoring Firm shall review the CONTRACTOR's Action Plan which describes specifically how work is to be completed. Approval of the Action Plan must be obtained through the OWNER prior to the start of work.
B.	Contractor Experience
1.	The Asbestos Abatement Contractor shall have a minimum of three (3) years experience in the asbestos abatement business. He shall have successfully completed three (3) projects of similar or larger size and dollar value to this project and shall not have defaulted on an asbestos abatement project within the last three (3) years. The CONTRACTOR shall be certified by the Pennsylvania Department of Labor and Industry.
C.	Worker Certification
1.	The CONTRACTOR shall furnish proof that his employees have had instruction on the dangers of asbestos exposure, on respirator use, decontamination, and current OSHA and EPA regulations.
2.	Documentation of workers' medical exams, consisting of x-rays and pulmonary function, shall be submitted as may be required by current OSHA and EPA regulations and any applicable State and Local Government regulations.
3.	There must be on site at all times, an EPA Certified Asbestos Abatement Supervisor. The Asbestos Abatement Supervisor shall have successfully completed a 5-day EPA Certified Practices and Procedures Course as per 40 CFR Part 763, Subpart E, Appendix C – EPA Model Accreditation Plan (must provide a copy of certificate from EPA approved course). All asbestos workers shall have successfully completed a 4-day EPA Certified Practices and Procedures Course as per 40 CFR Part 763, Subpart E, Appendix C – EPA Model Accreditation Plan. The CONTRACTOR must provide copies of certificates from Pennsylvania Department of Labor and Industry for all workers, and supervisors as required by regulation.
4.	When required by the Pennsylvania Department of Labor and Industry (PDL&I) the CONTRACTOR, Abatement Supervisor and Abatement Workers shall be licensed by PDL&I. Each worker/supervisor shall have a current photo identification issued by PDL&I available on request by the OWNER when required.
1.5	POSTING OF REGULATIONS
A.	The CONTRACTOR will have at all times in his possession at his office one (1) copy and in view at the job site one (1) copy, current OSHA Regulations 29 CFR 1926.1101 – Asbestos and current Environmental Protection Agency 40 CFR Part 61, Subpart M: National Emission Standard for Hazardous Air Pollutants as related to asbestos stripping, emissions, notification work practices and disposal of asbestos waste.
1.6	REGULATORY SUBMITTALS (CONTRACTOR'S RESPONSIBILITY)
A.	The CONTRACTOR is required to notify the building occupants (if any) and the following agencies in writing ten (10) days prior to starting work for notification and instructions concerning proper disposal of asbestos waste material. A PADEP Asbestos Abatement and Demolition/Renovation Notification must be submitted prior to any abatement and/or demolition activities, as recommended in the HBMS.
1.	Pennsylvania Department of Environmental Protection, Northwest Regional Office, Air Quality Program, using the current Commonwealth of Pennsylvania Asbestos Abatement and Demolition/Renovation Notification Form.
2.	Pennsylvania Department of Labor and Industry, Asbestos Occupations Accreditation & Certification, Bureau of Occupational and Industrial Safety, as required by the Pennsylvania Asbestos Occupations Accreditation and Certification Act.
3.	EPA and PADEP approved asbestos landfill proposed to be used by the CONTRACTOR. Submit completed Waste Shipment Record (WSR) at project's end (see Paragraph 3.5.F).
1.7	AIR TESTING AND MONITORING
A.	Air sampling of the work areas and surrounding environment will be conducted during the performance of this Contract by the Monitoring Firm so as to ensure abatement procedures are in compliance with all codes, regulations, ordinances and this specification.
B.	The CONTRACTOR shall fully cooperate with the Monitoring Firm and all others responsible for testing and inspecting the work.
C.	Air testing and analyses shall be in accordance with current EPA and requirements of Section 29 CFR 1926.1101 of the current OSHA Regulations, as a minimum. Analysis shall be performed by Phase Contrast Microscopy per NIOSH 7400 Method and/or Transmission Electron Microscopy (TEM) per EPA Level I analytical procedures.
D.	Air tests taken prior to start of work (background) and at completion (pre-clearance) will be analyzed by PCM-Phase Contrast Microscopy. Final (clearance) testing shall be by TEM-Transmission Electron Microscopy.
E.	The Monitoring Firm shall give verbal notification to the OWNER of the results of each test within twenty-four (24) hours of the time the samples were delivered to the laboratory. The Monitoring Firm shall confirm the results in writing within three (3) days thereafter.
F.	Prompt reports are necessary so that, if required, modifications to work methods and/or practices may be implemented as soon as possible.
G.	Representatives of the Monitoring Firm shall have access to the work area at all times. The CONTRACTOR shall provide facilities for such access in order that the Monitoring Firm may properly perform its function.
H.	Sampling equipment and personnel will be provided by the Monitoring Firm.
I.	Air sampling shall be performed in each work area prior to commencement of the work at that location. The highest fiber count reading during pre-clearance cleanup monitoring shall be lower than the background readings established by pre-job monitoring or 0.01 f/cc, whichever is lower.
1.8	SCHEDULE NOTES
A.	Consecutive daily air samples will be collected during abatement to yield a minimum of eight (8) hours of sampling time for each active work area.
B.	Exterior work area(s) samples shall be collected daily at decon clean room entrance, load out exit, discharge of HEPA exhaust units, and area(s) adjacent to work area(s) that are occupied or will be re-occupied.
C.	Aggressive air sampling must be conducted when work area is prepared as a negative pressure enclosure.
1.	Work area clearance testing shall be completed before work site protective barriers are removed.
2.	The CONTRACTOR is responsible for performing the thirty (30) minute excursion air sampling per OSHA regulations.
3.	The CONTRACTOR is responsible for performing 8 hour TWA personal air samples in the employees' breathing zone per OSHA regulations.
1.9	AIR FILTERING – (FOR GUIDELINE PURPOSES ONLY)
A.	An approved negative pressure machine may be used in the active work area using HEPA equipped air movement units.
B.	Air may be drawn from clean areas through the decontamination and active work areas, HEPA filtered and exhausted through air movement units to the containment exterior. Replace filters in accordance with manufacturer's instructions and to meet the needs of this specification.
C.	Air movement should be sufficient quantity to ensure a minimum of four (4) air changes per hour.
Example: Active work area = 50' x 50' x 20' H = 50,000 cu. ft.
For four air changes per hour = 4 AC/HR x 50,000 CF/AC = 200,000 cu. ft./hr.
In cubic feet per minute = 200,000 CF/HR ÷ 60 min./hr. = 3,333 cu. ft./minute.
This active work area would require a combination of air movement/HEPA units, i.e. 2,500 CFM and 1,500 CFM.
D.	The exhaust system must be sufficient to maintain a minimum pressure differential of -0.02 inches of water relative to unsealed, adjacent area.
E.	The exhaust system(s) will run twenty-four (24) hours/day until final clearance is obtained and will be maintained in accordance with ANSI Z9.2 and the manufacturer's directions. Continuous operation of exhaust systems is an equipment requirement and is not considered work activity for purposes of the Monday through Friday work restriction in Article 2 of the Agreement.
F.	To ensure continuous operation, the CONTRACTOR shall have a spare negative exhaust unit available.
1.10	ALTERNATIVE AIR FILTERING METHODS
A.	Other approved air filtering methods may be utilized at the CONTRACTOR's discretion, with the stipulation that designated regulatory agencies provide documented approval to the OWNER. It shall be the responsibility of the CONTRACTOR to submit all documentation required to the appropriate regulatory agency for their review and approval.
1.11	PLACEMENT OF WARNING SIGNS AND LABELS
A.	The CONTRACTOR shall furnish and place warning signs at all approaches to asbestos control areas containing concentrations of airborne asbestos fibers. Locate warning signs at such a distance that personnel may read the warning sign and take the necessary protective action required before entering the area. Warning signs shall be in place for the duration of the work. The CONTRACTOR shall furnish and attach caution labels to all disposal containers holding asbestos materials, scrap waste, debris, and other products contaminated with asbestos.
B.	Warning Signs: Provide warning signs conforming to 29 CFR 1926.1101 with the following legend:
DANGER
ASBESTOS
CANCER AND LUNG DISEASE HAZARD
AUTHORIZED PERSONNEL ONLY
RESPIRATORS AND PROTECTIVE CLOTHING ARE REQUIRED IN THIS AREA
C.	Caution Labels: Attach label to the outside of all disposal bags and containers which hold asbestos contaminated materials and are to be removed from the site. Caution labels shall be printed in letters of sufficient size and contrast so as to be readily visible and legible and shall display the following legend:
DANGER
CONTAINS ASBESTOS FIBERS
AVOID CREATING DUST
CANCER AND LUNG DISEASE HAZARD
D.	Identification Labels: Attach label to the outside of all disposal bags and containers which hold asbestos contaminated materials and are to be transported off facility site. Identification labels shall display the following legend:
Waste Generator Name: ______________________________
Generator Location: ________________________________
E.	Transportation marking shall conform to 49 CFR 171 and 172 and shall be provided on all containers with more than one pound of friable asbestos. Transportation marking shall display the following legend:
RQ HAZARDOUS SUBSTANCE
SOLID, NOS
ORM-E, NA 9188
(ASBESTOS)
PART 2 - PRODUCTS
2.1	EQUIPMENT AND MATERIALS
A.	The list of required materials will include, but is not necessarily limited to the following:
1.	Respirators: Provide respiratory protection in accordance with OSHA Regulation 29 CFR 1926.1101 and its appendices, and ANSI Z88.2. Respiratory protection shall be provided regardless of negative exposure assessments. There shall be NO EXCEPTION to this requirement. As minimum protection, negative pressure air purifying respirators shall be worn. CONTRACTOR shall select the appropriate respirator based on an initial exposure assessment or exposure monitoring results. No employee or visitor shall enter any area without this protection until clearance has been obtained. Respirators shall be NIOSH approved. Ensure proper filters are worn using a HEPA as a minimum.
2.	Protective Clothing
a.	Disposable Clothing - such as "Tyvek" by DuPont. Clothing shall consist of coverall, head cover and foot cover. Gloves will be worn for hand cover as needed.
3.	Wetting Agents – The asbestos material will be sprayed with water containing an additive to enhance penetration. The additive or wetting agent will be polyoxyethylene at a concentration of one (1) ounce per five (5) gallons of water or as otherwise specified by manufacturer. A fine spray of this solution must be applied to prevent fiber disturbance preceding the removal of the asbestos material. The asbestos will be sufficiently saturated to prevent emission of airborne fibers in excess of the exposure limits prescribed in the current OSHA standards referenced in these Specifications. Dry removal will not be allowed except with written approval from the CONSULTANT and the regulatory agency having jurisdiction because of freezing work area temperatures.
4.	Polyethylene sheeting: Six (6) mils for protection of floors, walls, doors, windows, fixed equipment, HVAC supply and return openings, and critical barriers.
5.	Clear Polyethylene bags (with warning labels) six (6) mils minimum for disposal. All asbestos that is removed shall be double bagged.
6.	Tape: High quality vinyl or fabric duct tape. Paper masking tape will not be permitted.
7.	Negative Pressure Filtration Equipment: Air movement and filtering equipment equipped with HEPA filters rated at 99.97% removal down to 0.3 microns, and of sufficient capacity to provide a minimum of four (4) air changes per hour for each active work area.
8.	Airless Spray Equipment: Electric airless spray equipment for saturating and mist fiber control. Low pressure (500 psi) equipment must be available on-site and utilized as required.
9.	Vacuum: HEPA rated for surface cleaning and house-keeping. Hand operated and power tools such as, but not limited to, saws, corers, abrasive wheels and drills should be provided with local exhaust ventilation systems with HEPA filter.
10.	Hand Tools: Brooms, plastic shovels, scrapers, brushes, etc., in sufficient quantity to ensure the appropriate level of housekeeping.
11.	Water Filtration System: Shower and contaminated water filtration system.
12.	GFI Equipment: All electrical connections in the work area must be through "ground fault" protected outlets/circuits.
13.	Penetrating Encapsulant: Penetrating encapsulants to be used on this project are International Cellulose Corporation SK-13 Asbestos Encapsulant, International Protective Coatings Corporation Serpiflex Shield, Fiberlock Technology ABC Asbestos Binding Compound Concentrate, and others listed as acceptable in the Environmental Protection Agency – Battelle Laboratory Encapsulant Study or approved equal.
14.	Bridging Encapsulant: Bridging encapsulants to be used on this project are American Coatings Corporation Cable Coating 2B, Decadex Laboratories Firecheck, Fiberlock Technology ABC Asbestos Binding Compound Concentrate, or approved equal.
B.	The CONTRACTOR will have at all times in his possession at the job site Safety Data Sheets (SDS) for wetting agents, encapsulants, solvents, strippers, and any other potentially hazardous materials.
2.2	PERSONNEL PROTECTIONS
A.	Personnel protection is required for laborers, mechanics, supervision and visitors at the work site during the set-up and abatement operations.
B.	Each worker shall be supplied with a minimum of two (2) complete protective work clothes and respirator filter changes per day for the complete duration of the project. Hard hats should be available as appropriate which meet ANSI Z89.1 standards. Safety toe footwear is to be worn underneath the disposable shoe covers and must meet the requirements of ASTM F2413. Eye wear and face protection must meet the standards and specifications of ANSI Z87.1.
C.	In addition to sets of protective work clothes for workers, the CONTRACTOR shall have on hand two (2) additional sets of disposable work clothes, per day and respirators for personnel who are authorized to inspect the work site. Hard hats should be available as appropriate which meet ANSI Z89.1. Eye wear and face protection must meet the standards and specifications of ANSI Z87.1.
D.	Respirators approved for asbestos use and protective work clothes will be worn by laborers and mechanics as a minimum during set-up operations (plastic draping, light-fixture dropping or removal, etc.).
E.	Appropriate respirators will be worn by all personnel in the active work area.
F.	Upon leaving the active work area, filters will be discarded, cartridges removed and respirators cleaned in disinfectant solution and clean water rinse.
G.	Clean respirators will be stored in plastic bags when not in use.
H.	Respirators will be inspected daily for broken, missing, or deteriorated parts.
PART 3 - EXECUTION
3.1	AREA PREPARATION
A.	Heating and ventilating systems serving the areas of work must be shut down prior to starting any work. Notify the OWNER prior to starting any work.
B.	The CONTRACTOR shall isolate the work area for the duration of the work by installing critical barriers completely sealing off all openings in the work area, including, but not limited to, heating, ventilation ducts, doorways, corridors, windows, roof ventilator openings, and wall vents, with six (6) mil plastic sheeting taped securely in place.
C.	The CONTRACTOR shall build decontamination chamber(s) if required to be connected to each active work area for entrance to or exit from the active work area. When required a separate material load out unit shall be constructed.
D.	Duct tape, staples, wood strips and other methods will be used appropriately to attach vertical plastic barriers to walls and to floors. All edges of plastic material shall overlap the adjoining sheet a minimum of twelve inches. All joints (vertical and horizontal) to be continuously sealed with duct tape.
E.	Exterior work on the roof flashing seal (HA K) and exterior window mastic shall be performed using wet methods within a regulated area established in accordance with 29 CFR 1926.1101.
3.2	METHOD OF REMOVAL
A.	Remove and dispose of all Asbestos Containing Materials (ACM) in accordance with the methods and procedures outlined in the United States Department of Labor, Occupational Safety and Health Administration (OSHA) Asbestos Regulations, Code of Federal Regulations Title 29, Part 1926, Section 1926.1101. Non-friable floor tiles (HA A) and the asbestos-containing mastic beneath the 9x9 tile (HA C) shall be removed by non-friable methods; floor tile removal is to be carried out either by Dry Ice or Heat Machines, and asbestos-containing mastic shall be removed using odorless chemical mastic removers. Window mastic (HA F and HA V), roof flashing seal (HA K) and ceiling board (HA CC) shall be removed intact to the greatest extent practical, without sanding, grinding, cutting or abrading.
B.	Dry removal will not be allowed, except as permitted under Paragraph 2.1.A.3.
C.	DELETED.
D.	Work of this section shall be performed in the following manner:
1.	Eliminate air flow into containment area by isolating all supply and return air ducts from mechanical system. Turn off electrical power.
2.	Install six (6) mil polyethylene critical barriers over all doors, wall openings, ceiling openings, electrical outlets, etc. Secure with duct tape on all sides.
3.	Connect required number of negative air units in the work area.
4.	All air from negative air units shall be exhausted outside the building.
5.	Isolation barriers separating occupied areas and work areas shall be framed and covered with ½ inch plywood and two (2) layers of six (6) mil polyethylene.
6.	Duct HEPA filter unit through door. Locate unit to prevent dead air pockets.
7.	Install triple air curtain, six (6) mil polyethylene (typical), over door opening into decontamination unit or load out unit.
3.3	PROPERTY MANAGEMENT
A.	Throughout the work period, the CONTRACTOR shall maintain the building and site in a standard of cleanliness as specified throughout these Specifications.
B.	Contaminated disposable clothing, respirator filters and other debris will be bagged, properly labeled, and sealed at the end of each work day.
C.	All asbestos generated by removal, encapsulation or repair will be bagged, properly labeled, and sealed at the end of each work day.
D.	Respirators will be thoroughly cleaned at the end of each work day and stored for the next day's use.
E.	Retain all stored items in an orderly arrangement allowing maximum access, not impeding traffic, and providing the required protection of materials.
F.	Do not allow the accumulation of scrap, debris, waste material, and other items not required for completion of this work.
G.	At least weekly, and more often if necessary, completely remove all scrap, debris and waste material from the job site.
H.	Unless otherwise noted or directed, materials resulting from demolition operations shall be the property of the CONTRACTOR, shall not be used in the work and shall be promptly removed from the site.
I.	Daily and more often if necessary, inspect the work areas and adjoining spaces, and pick up all scrap, debris, and waste material. Remove all such items to the place designated for their storage.
J.	Provide adequate storage for all items awaiting removal from the job site, observing all requirements for fire protection and protection of the ecology.
K.	Maintain the site in a neat and orderly condition at all times.
L.	Compressed air is not to be used for cleaning purposes.
3.4	FINAL DECONTAMINATION OF WORK AREA
A.	Following careful double bagging of all removed asbestos material by the CONTRACTOR, he shall label bags as required.
B.	Bags shall be wiped with clean damp cloths prior to transportation to approved disposal site.
C.	With critical barriers in place and the negative pressure system operating, the CONTRACTOR shall carry out the first cleaning. Use each surface of a cleaning cloth one time and then dispose of as contaminated waste.
D.	Continue this cleaning until there is no visible debris from removed material or residue on plastic sheeting.
E.	Pressure washing techniques of any kind are strictly prohibited.
F.	Pre-Encapsulation Inspection of substrate is performed by the Monitoring Firm to ensure removal and cleaning of the substrate is adequate. The CONTRACTOR may accompany this inspection. If during the inspection, the substrate or plastic sheeting isn't cleaned to the satisfaction of the Monitoring Firm, additional recleaning will be required to meet the satisfaction of the Monitoring Firm.
G.	Encapsulate substrate and all remaining plastic sheeting within the work area. A colored encapsulant may be used on non-finished surfaces.
H.	NOTE: Final barriers are not to be removed until work is completed.
I.	With critical barriers in place, negative pressure system operating, and immovable objects covered with plastic sheeting, perform a second cleaning as was done in the first cleaning. Wet mop any hard floor surfaces. Hard surfaced flooring such as concrete, terrazzo, VAT and ceramic tile, shall be wet mopped, allowed to dry, and damp mopped a second time with clean mop heads. All mop heads and cleaning cloths are to be discarded in the same manner as asbestos waste.
J.	All surfaces are to be left visually clean.
K.	Perform visual inspection of work area.
L.	If pre-clearance criteria are met, proceed with air testing for final clearance by Transmission Electron Microscopy (TEM) in accordance with Paragraph 1.7.D.
M.	If pre-clearance criteria are not met, repeat final cleaning until acceptable levels have been achieved before proceeding with final clearance testing by TEM. Costs associated with additional cleaning and testing shall be borne by the CONTRACTOR.
N.	After air testing clearance criteria has been met, critical barriers and negative air pressure system can be removed.
3.5	DISPOSAL OF ASBESTOS WASTE
A.	All RACM and miscellaneous ACM debris will be transported to the predesignated disposal site in accordance with the guidelines of the U.S. Environmental Protection Agency 40 CFR Part 61, Subpart M and all local agencies' regulations. Ensure all waste bags/leak tight containers have the facility's name, address, and contact person as required by NESHAP. Drums are to be used to transport bagged ACM as required by regulation(s).
B.	EPA NESHAP Category I & II non-friable ACM that remains non-friable may be disposed of as C&D waste as allowed by regulation. If non-friable materials become friable they must then be disposed of as regulated ACM waste in an approved landfill.
C.	Workers loading/unloading the asbestos materials and machinery operators will wear respirators and disposable work clothing when handling material at the project and disposal site. Asbestos warning signs shall be posted on vehicle as required by regulation.
D.	If drums are used to transport the ACM bags, the bags may be dumped from the drums into the burial site. The drums may be reused. However, if a bag is broken or damaged, the entire drum should be buried.
E.	The landfill area used for dumping shall be certified to receive and bury materials contaminated by asbestos.
F.	Obtain completed Waste Shipment Record (WSR) for all asbestos waste. WSR must also indicate amount of waste in cubic yards. Submit signed WSR with final report/Project Close-out.
3.6	INSPECTIONS
A.	All work procedures detailed in this specification will be strictly adhered to and meet or exceed all current EPA, OSHA, DEP and PDL&I regulations.
B.	All work shall meet with the approval of the OWNER. Work which does not meet with the approval shall be determined to be unsatisfactory.
END OF SECTION 028213
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APPENDIX A

DEMOLITION PLANS

Fuchs Lubricants Co. Site Demolition/E&S Plans
105 8th Street, Emlenton, Venango County, Pennsylvania 16373
Prepared by Moody and Associates, Inc. — October 2026
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APPENDIX B

PRE-DEMOLITION HAZARDOUS BUILDING MATERIALS SURVEY

Fuchs Lubricants Co. Site, 105 Eighth Street, Emlenton, Pennsylvania
Prepared by Moody and Associates, Inc. (Moody Project No. 24-046-MM)
June 24, 2025
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Fuchs Building Demolition
Funds will be used for demolition and removal of all
structures and their contents including proper offsite
disposal, asbestos abatement as required, disconnection
of all existing utilities, capping of sanitary sewer laterals,
and site grading.

Project Locality: Borough of Emlenton, Venango C
Awarding Agency: Department of Community and Economic Development,
ISRP

Contract Award Date: 1/1/2026

26-09058
Building/Heavy/Highway
10/13/2026

County: Venango

: Pittsburgh
(412)565-5300

Toll Free Phone Number: (877)504-8354





